# Gendered Knowledge’s

# Minutes

# 29.01.13

In attendance: Cath Lambert, Sam Lyle

To do list

- CL to send SL all details for recruitment today

- SL to write up job descriptions and recruitment email

- CL to send SL current e-list of interested parties

- SL to draw up wish list for Expert Advisory Board

- SL to get editing rights for CSWG and write blurb about project

- SL to book rooms for interview and first team meeting and organize biscuits

Agreed timeline for recruitment

- SL to send recruitment email by Friday February 1st

- Deadline for application : Monday February 11th at 5pm

Interview date: Friday February 15th 10 – 12 room TBC

- First team meeting Monday February 18th 10 – 12 room TBC