| Recruitment Activity | 2023/24 timeline |
| --- | --- |
| CDA Project call - for projects to be advertised in October 2024 for October 2025 | Launch CDA project call 09 October |
| M4C Open Doctoral Competition and CDA Recruitment launched | 16 October 2023 |
| Application Writing Workshops one in each city: | 04 and 11 November 2023 Leicester workshop-4th November |
| CDA Supervisor Workshop for HEI and Partner Organisation Supervisors | 08 November 2023 CDA Workshops 10.00 - 11.50 CDA student workshop 11.45 - 12.15 CDA current supervisor Q&A 14.00 - 15.00 CDA supervisor Q&A for projects being advertised |
| Deadline for Submitting Applications | 10 January 2024 12.00 hours (UTC+0) |
| University Open Competition Shortlisting: University departments and schools interview and short-list candidates for the Open Competition. (Site Directors may set their own internal deadlines in this period to make sure they have time to check applications before their institution add the information from the interview record and ISF to the online form in Survey Monkey Apply) | 10 January 2024 - noon 15 February 2024 (5 weeks and 1 days ) |
| CDA Shortlisting by Site Directors: Following shortlisting applicants who meet the quality threshold should be invited to interview. Presentations + Interviews coordinated by project host University. The interview panel should comprise: Project Partner Supervisor, University Academic Supervisor, one Site Director from host University and one Site Director from other city-based University. | 10 January 2024 - 20 March 2024 (10 weeks) |
| Open Doctoral Competition: each university uploads the completed interview record form and ISF for applications shortlisted to a Subject Area Panel. Uploading the interview record form and ISF will direct the complete application to the correct Subject Area Panel. Universities to communicate with unsuccessful candidates and transfer them to internal universities competitions where relevant. | Last date for upload: 12:00 noon 15 February 2024 |
| Panellists can access all the applications shortlisted for scoring. | From 16 February 2024 |
| Scoring by Subject Area Scorers.Panellists access the applications access in Survey Monkey Apply and scores for each applicant entered into Survey Monkey Apply. Panellists will be able to see applicant's form, interview record, and ISF | From 16 February 2024 to close of business 20 March 2024 (4 weeks 3 days) |
| Communication to applicants not shortlisted by Universities for scoring- to be communicated by applicant's home university | From 16 February 2024 |
| Final deadline for open application scores to be input in to SurveyMonkey. | close of business 20 March |
| CDA Applicants require a CDA interview form for all CDA applicants shortlisted to the Student Selection Panel top three university ranked applicants go forward to the M4C student selection panel preferred candidate and two reserves). Any applicants who are interviewed and not selected to go forward to the student selection panel should be marked as No in Survey Monkey Apply. | close of business 20 March 2024 |
| M4C team collate scores and calculate quality threshold for awards and reserves | 21, 22, March |
| M4C Team to meet with external advisor | 25 March 2024 |
| Student Selection Panel (including CDAs) | 28 March 2024 |
| Easter Weekend | Friday 29 March - 1 April 2024 |
| Admins to confirm Phd start dates, award length and supervisor info. | 3rd April- deadline noon 8th April |
| Award letters, declines and reserve communication preparation (M4C) | From 03 April - 17 April |
| Award letters and declines sent out by | 17 April 2024 |
| Deadline: Award Acceptances | 08 May 2024 (3 weeks) |
| Awards offered to Reserve candidates as they become available | 18 April and 15 May |
| Deadline for reserves to accept award. End of recruitment. | 22nd May |
| M4C to share award lists with University admins | 28 May 2024 |
| Online Welcome Event | 05 June 2024 |
| Share awarded project titles with pannelists | 10 June 2024 |
| Induction | 01 October 2024 |