## Sheet1
Centre for Interdisciplinary Methodologies - Athena Swan Bronze Award Approved Plan - February 2024
Reference | Area | Action |  |  | EDI Advisory group - lead advisors | [7 empty] | Discuss with in CIM
|  |  | Timeframe | Success criteria / Outcome | Meg | Ching | Erica | Iain | Meng | Nerea | Sanjay (when back) | Responsible in CIM | Celia | Sarah | PGT Directors | PGR director (Nerea) | Research & impact director | PG coordinator (Debbie) | Erica (research administrator) | Comms Director (Greg) | SSLC chair (Timothy) | Senior tutor (Kavin)
Key Priority 1 (KP1) | Embedding EDI and Athena Swan (EDI- AS) principles and good practices in structures and processes by establishing robust and permanent frameworks that promote our vision for inclusive gender and intersectional equality as a central part of CIMs culture and community. | Consolidating structures and transparent equality and inclusion practices Ensuring a majority of staff feel included and encouraged in CIMs EDI collective journey through a routine process of reflective self- assessment that informs improvements in practices and policies |  | All points below implemented - evaluated yearly by EDI- AS advisory group, with a bi-annual survey. | [7 empty] | CIM EDI-AS Director and advisory group
AP 1. | Governance structures and processes | Constitute CIM Equality, Diversity, Inclusion Advisory group; Meets with responsible people on the plan once a term, and including student EDI rep once a year | From September 2023 | Action plan successfully implemented and assessed by May 2025 | Meg | [6 empty] | CIM Centre Director, Centre Administrator | x |  |  |  | x
AP 2 | Dissemination and communication | Athena Swan Sessions at the annual Education and Research Away days | Annually | Majority of participants evaluate the sessions positively in an anonymous survey after the Away days AND Improved positive results in Biannual Athena Swan Staff/student surveys in all areas |  |  | Erica |  |  |  |  | CIM EDI-AS advisory group director working with PGT Director and Research Director; PG coordinator and research administrator collate/summarise responses. | x |  |  |  | x | x | x
AP3 | Data collection for effective and transparent self- assessment | Generate local gendered and intersectional data across all areas of CIM work: Research, Teaching and Service , using a stepped approach. End of first year: Map central admin data and local data to identify gaps; End of first year: focus on improving data related to staff teaching; end of second year, focus on improving student data; end of third year, focus on improving data relevant to research; end of fourth year, data relevant to PSS. Success measure is that by end of each year, we progress towards having granular, intersectional data in each area, that feeds into semi-annual meetings and informs our decisions. | Whole award cycle | Organised data collection processes in place by June 2024 reviewed in semi-annual meetings. |  |  | Erica |  |  |  |  | CIM EDI Advisory Group and Centre Director, Department Administrator, Research Administrator, PG Programmes Administrator | x | x |  |  |  | x | x
AP4 | Biannual assessment | Run staff and student surveys every two years and discuss results with all staff and students to identify areas for further action. | February 25 - Whole award cycle | Progressively more positive evaluations of CIM in surveys improving by 20% overall by end of award cycle | Meg | Ching |  |  | Meng | Nerea |  | EDI Advisory group, Centre administrator and PGT directors |  | x | x
AP5 | Annual presentation | Annual presentation (April) on Action plan Implementation and Progress presented to CIM's two main Committees, Education and Research, for input, and shared at all- Staff meeting to foster discussion on areas for further action | Summer term 2024 – Whole award Cycle | Presentations shared with staff June 2024-2026. | Meg | [7 empty] | x |  |  |  | x | x | x
AP6 | Proactive Equalities Advocacy | Regular communication to staff of university and wider resources to tackle negative behaviours such as bullying and harassment and ways to report. Ensure all staff resources are listed on staff portal, and alert staff by email and at staff meetings when new resources are listed; include in induction of new staff. | June 2024 – Whole award Cycle | 50% increase in staff survey demonstrating knowledge of relevant policies and processes | [6 empty] | Sanjay TBC | Department Administrator, Centre Director | x | x
AP7 | Strategy development | Embedding CIMs shared principles and practices to promote gender responsiveness in our work as central to the writing of our new 10-year strategy. Standing item added to all committees; statement of values in strategy document. EDI advisory group revises the Strategy document June 2024 before submission to guarantee it includes EDI principles and practices. | June 2024 - Whole Award Cycle | Written commitment s embedded in CIMs Strategy document June 2024 | Meg | [6 empty] | Centre Director, CIM EDI-AS Advisory group | x
AP 8 |  | Communicating a proactive vision of inclusion advocacy in Centre Communications to staff, students and beyond (Website) as well as all promotion materials and outreach activities and improve the visibility of CIMs staff and student diversity. Semi-annual meeting includes Centre Comms director to review visibility of CIM's diverse voices. Assess accessibility of website and address concerns. | Whole award cycle | Assess progress qualitatively in semiannual meetings. |  |  |  | Iain |  |  |  | Communications Director, with input from EDI- Athena Swan advisory group director | [7 empty] | x
KP2 | Recruitment and Career Development | Creating a robust process that supports the career cycle starting at recruitment - to ensuring equality of opportunity for all staff to develop a successful career trajectory |  | All points below implemented - evaluated yearly by EDI- AS Advisory Group | [7 empty] | EDI-AS director and advisory group
AP9 | Recruitment | Provide expert outsourced external training by organising regular training sessions on EDI and recruitment for all staff; reflections by hiring panels on EDI pre- and post-recruitment. Develop a group of shared positive actions to take in recruitment, including for PSS, that encourage diverse applicants, including in job descriptions, promotion of announcements in diverse fora, targeted outreach, etc. | Sept 23-June 24 | Clear tactics that encourage applications from women and underrepresented groups in targeted areas. | Meg | [6 empty] | CIM EDI director, HoD. | x
AP10 | Induction | Review induction guidelines and propose a clear framework towards the formalisation of inductions and refresher inductions of new staff Embedding CIM, University EDI and AS principles and practice in inductions Make meeting with head of centre and a member of PS and member of RSE standard . Mentorship program to include induction to university dynamics. Advocate for university to do more to welcome and onboard new staff | February 2024-25 | Add to CIM's annual survey a question on induction satisfaction. To this baseline, the target is to improve positive assessments in survey by 25% by the end of the award cycle. | [6 empty] | Sanjay TBC | Centre Director and Department Administrato r with input from CIM EDI- AS Advisory Group | x | x
AP11 | Career development | Reviewing process, effectiveness, and benefits of PDR and Mentoring - especially with regards to career progression and training needs, including for PSS and RSE. Review good practices to recognise mentoring in workloads. | Nov 2023 to whole award cycle | All staff who wish to have a mentor meet with one at least twice a year. Updated list of mentoring arrangements from November 2023, plan to review in semiannual meetings and assess effectiveness in biannual survey. | Meg | [6 empty] | CIM research and impact directors, with input from Centre Administrator relevant to PSS |  | x |  |  | x
KP3 | Improving a culture of whole-life balance
AP12 | Workoad allocation | CIM EDI advisory group to be involved in reviewing new workload allocation to improve transparency and recognition of potential EDI concerns and Athena Swan commitments. |  | Review whether workload allocation incorporates input from EDI advisory group; seek 10% improvement in biannual staff questionnaire |  |  |  | Iain |  |  |  | Head of Centre, EDI advisory group | x
AP13 | Wellbeing | Conduct bi-yearly information sessions on wellbeing including communication of university wellbeing resources including: -information on support for women going through menopause - resources to tackle negative behaviours such as bullying and harassment and ways to report. | From 2023- 24 : reserved time at the extraordinary staff meeting in week 0 and first meeting of the calendar year. | Improved understanding of wellbeing needs and 25% improved positive responses in biannual staff surveys in terms of wellbeing support, knowledge of relevant policies and processes. | [5 empty] | Nerea |  | Department Administrator with input from University- wide services |  | x
AP14 |  | Reestablish a calendar of in person collective activities 3 times a term to improve a sense of community and avoid disconnection and loneliness among members of staff. Organise a family friendly event every year. | Starting September 2023. | 25% improved positive responses in staff surveys with regards to a sense of community and belonging | Meg | [6 empty] | Director and deputy director of research and impact; Department Administrato r |  | x |  |  | x
KP4 | Educational Diversity, Representation, and Support
AP15 | Student representation | Include permanent EDI Agenda item at the Staff and Student Liaison Committee and issue call for student EDI Champion representative. EDI representative joins staff EDI meetings in spring each year. | From September 2023 | Add a question to biannual survey assessing whether students feel concerns have been heard and issues addressed, aim for 25% progress. |  | Ching |  |  | Meng |  |  | Staff and Student Liaison Committee Chair | [8 empty] | x
AP16 | Student recruitment | Review CIM webpages and prospectuses for prospective MA and PhD students to include statement on gender equality similar to that used in our job adverts Explore partnerships with other international agencies and universities to promote diverse student applications EDI added to student induction. | Feb-April 2024 | Add question to student biannual survey on whether EDI and gender are addressed well, and aim for 25% improvement over baseline. |  |  |  |  | Meng |  |  | Communications Director and Department Administrator, PGT and PGR directors, with input from CIM EDI Advisory Group | [7 empty] | x
AP17 | Representation | Monitor and ensure proportionate. gender representation in departmental admission events, and other student-facing events such as open days | From September 2023 | [7 empty] | Sanjay TBC | PG Director, PG Programmes Coordinator |  |  | x |  |  | x
AP18 | Student Induction and EDI involvement | To communicate EDI vision and practices at PGT and PGR induction sessions: Include clear communication in student inductions on ways to report negative behaviours such as bullying and harassment Emphasise wellbeing support structures and processes in Warwick Communicate dignity at Warwick policies -invite students to follow Warwick Active Bystander Intervention Course and monitor uptake Advocate with Warwick Wellbeing services to recruit Chinese-speaking counselors. | From September 2023 | Feedback from student surveys to assess clear understanding of reporting mechanisms; Wellbeing team recruits Chinese-speaking counselors. Add question to biannual survey and aim for 25% by end of award cycle. | [5 empty] | Nerea |  | Senior Tutor, PG Coordinator, PGT and PGR Directors |  |  | x | x |  | x |  |  |  | x
AP 19 | Curriculum development | Improve collective ownership of core modules to improve gender balance in instructors | Full award Cycle | By Sept 2026 measurable progress in percentage of reading lists constituted by authors who are female and members of underrepresented groups |  | Ching | [5 empty] | PGT Director, CIM Director, input from EDI lead | x |  | x
AP20 | PGR career support | Monitor PGR student support in post-award period with a focus on network of Alumni Organize a once/term call or breakfast with an alumnus or external partner to talk about career experiences with PGR students. | From January 2024 | By December 2026 have an established alumni list and network |  |  |  |  | Meng | Nerea |  | PGR Coordinator, PGR director |  |  |  | x |  | x