Minutes of Meeting

INTEGRATE AMR – Management Committee Meeting #1

Date:	 	7th March 2016

Venue: 	BSR6, Life Sciences

Time:		13:30 – 15:00

Attendees:  Matt Keeling, Nick Waterfield, Steven Brown, Chris Dowson, Matt Gibson, Greg Challis, Rika Nair

Apologies:  Esther Robinson, Deirdre Hollingsworth, Neil Evans, Matthew Turner, James Covington, Dave Roper

| 1. Early Career Fellows |  |
| --- | --- |
| Notes from meeting | Actions |
| Application form amendments - Add emphasis on what is going to be achieved during the fellowship eg. Predicted outcomes? - Applicants should outline realistic future plans, specify which grants/fellowships they are going to apply to in future - Supervisors should commit to supporting the fellow in submitting a grant application during the 6 months | RN to amend and circulate form + guidance Management committee to review. |
| Internal vs External candidates It was commented that one advantage of internal candidates is that they can often ‘hit the ground running’ Advertising for external candidates - Find-a-Postdoc / jobs.ac.uk advert | RN to liaise with HR to to obtain templates. Management committee to review JD |

| 2. Strategy |  |
| --- | --- |
| Notes from meeting | Actions |
| Analysis of Past Collaborations It was agreed that it would be useful to see an analysis of past interdepartmental collaborations of INTEGRATE co-applicants | RN to obtain analysis with assistance from RIS |
| Events and Outputs - Training: Develop modules that can be used to support application for MRC AMR DTC Use examples of: - Oxford/Bristol/Warwick SynBio CDT format - Complexity summer school - Student-run seminars - Workshop: Industry perspective (small and large pharma). Involvement of Unilever was suggested, as they are investigating alternative antimicrobials. Sanofi also suggested. It was agreed that attendees from pharma should be “science, not sales” people - Workshop: Leads against Gram –ves - Workshop: Warwick PI show +tell - Workshop: Wellcome Trust Technology Transfer (invite Tim Jinks) Grants - The importance of applying to large grants (5M +) and agreeing on one vision - MRC DTC, call may open in July - Gobal challenges (use grant to fund international exchanges) - Official Development Assistance – eligible countries (eg. Indonesia) - Wellcome Trust – the most successful unis don’t have a higher success rate, they just submit more applications - Technology platform for Gram –ves - Standalone LINK grants |  |

Funding applications were reviewed and feedback will be sent to applicants separately.