INTEGRATE AMR

Minutes of Meeting

INTEGRATE AMR – Management Committee Meeting #2

Date:		 15th April 2016

Venue:		BSR6, Life Sciences

Time:		09:00 – 11:00

Attendees:  Matt Keeling, Nick Waterfield, Matthew Turner, Chris Dowson, Deirdre Hollingsworth, Esther Robinson, James Covington, David Roper, Rika Nair

Apologies: Matt Gibson, Greg Challis, Neil Evans, Steven Brown

| Notes from meeting | Actions |
| --- | --- |
| Events Public Engagement It was noted that “Public engagement” is a deliverable in our application. Suggestion 1: Involve the Pro VC for Public Engagement Professor Simon Swain Suggestion 2: Public lecture on the topic of AMR Dragon’s Den Style Competition A one afternoon event for teams to pitch ideas. Students to attend. ‘Democratic’ vote SWON Event with Industry 24th, 25th, 26th Sep – interested INTEGRATE participants will be able to attend evening talks on drug discovery/dinner Visit to UHCW Meeting to discuss ideas | RN to contact PA and arrange meeting once we have a n impact strategy in place (consult Katie Irgin first) RN to contact relevant university contacts, external Festivals eg. Cheltenham (done), Big Bang etc RN to organise RN to help coordinate RN to contact Ceri Jones RN to organise |
| Maximise Value of Early Career Fellowships Advertising for external candidates - Find-a-Postdoc / jobs.ac.uk advert Recruit ECFs to specific projects Match funding Use ECF fund to match fund existing university research activities eg. URSS, Final Year Projects, MBio, MChem, MIBTP 3-6 month Internships for PhD students May work better in some departments than others. Amendments to Funding Application Processes Feedback form Feedback form to be added to improve transparency and consistency of review process. Applicants will have a chance to respond to comments. PPF Review process It was agreed that while applications would be circulated to the whole management team, two expert readers would be in charge of reading/researching the applications in detail and providing their feedback (yes/no/review). Readers will be nominated based on expertise in two areas relevant to the application. It was agreed that applications should be received at least 2 weeks prior to the meeting. ECF Review process Two expert readers will be in charge of reading/researching the applications in detail and providing their feedback (yes/no/review). | RN to contact Ann in Maths AMR community to put forward project ideas – RN to look into setting up a “project ideas board” RN to get in touch with relevant university contacts RN to get in touch with relevant university contacts RN to draft and circulate feedback form, management committee to review. RN to add review process to submission guidelines/website RN to update deadline on website to correspond to 2 weeks before management meeting RN to add review process to submission guidelines/website RN to update deadline on website to correspond to 2 weeks before management meeting |
| ECF Review process Two expert readers will be in charge of reading/researching the applications in detail and providing their feedback (yes/no/review). Assessment will be based on quality of project/person/place Readers will be nominated based on expertise in two areas relevant to the application. It was agreed that applications should be received at least 2 weeks prior to the meeting. Assessment will be based on quality of project/person/place Readers will be nominated based on expertise in two areas relevant to the application. It was agreed that applications should be received at least 2 weeks prior to the meeting. | RN to add review process to submission guidelines/website RN to update deadline on website to correspond to 2 weeks before management meeting |