ETATMBA Conference

Ifakara Health Institute, Tanzania

22-23 June 2011

Meeting Notes

Day 1: Overview of training

Present: Senga Pemba (SP), Sidney Neleki (SN), Godfrey Mbaruku (GM), Francis Kamwendo (FK), Marshal Lemerani (ML), David Davies (DD), Chisale Mhango (CM), Doug Simkiss (DS), Siobhan Quenby (SQ), Sam Luboga (SL), Ed Peile (EP), Anne-Marie Brennan (AMB), Paul O’Hare (PO’H), Hamed Mohamed (HM), Paul Kihaile (PK), Staffan Bergstrom (SB)

Introduction (GM)

GM welcomed the group and introduced the visitors.

Running order changed from published agenda to accommodate visit of the Rev Professor Samuel Luboga.

Developing robust assessments and evaluations of training

Evaluation and assessment involves 4 approaches: patient; programme (objectives); institution (quality of learning); stakeholder.

Assessment is defined as checking what the student has learned; evaluation is defined as checking the effectiveness of teaching.

Evaluation requires clarity (can see results); credibility (changes are made if required) and consistency.

ETATMBA is one project.  Results have to demonstrate consistency.  Evaluation has to have consistency across the components in Malawi and Tanzania.  Assessments should focus on how learning has been translated into action; on how “capable” the students are in following training.

Most important stakeholder is the patient, though difficult to assess impact on training.  Other stakeholder is the funder, who is interested in both hard results (“how many?”) and how the trainees have impacted on the systems themselves.

Should aim for constructive alignment, whereby the goals of teaching, learning and assessment are set in direct, balanced relation to each other.

EP commented that our difficulty in thinking about evaluation is that we have to consider both learning outcomes and project outcomes.

What are we evaluating?

1.  Task shifting to NPCs needs to be extended, enhanced, endorsed and supported by the community

2.  All service improvements will be sustainable, scalable, cost-effective and transferrable.

WP2: – to develop, implement and evaluate clinical service improvement through clinical guidelines

Discussion

PO’H: when this WP was written, there was an assumption that there would not be any clinical guidelines, however these do exist.  We are therefore now more focussed on how these guidelines are translated into practice.

EP: need to document that we have examined the guidelines, justified how we have made decisions, explained what we have noted for improvement.

PO’H: we should ensure, in the course of our teaching, that existing guidelines are operating effectively.  Important to use audit to assess the course and NPC function so that this will in turn filter back to inform where changes might be required for the guidelines.

CM: problem is often about constraints in applying the guidelines.

EP: often the real-life scenarios require alternative approaches.

Summary

EP suggested a comparison of the guidelines for NPCs in Malawi and Tanzania would be productive – identifying similarities and differences, considering whether cross-fertilisation would be effective; investigating what works in what place and for what reasons.

WP1; WP3: – Delivering structured education and clinical leadership training; workforce development of NPCs and faculty

EP: should ensure we can identify our baselines, in order to show how we have improved.  How  can this be demonstrated?

Discussion

DS: use of audit and professional projects, the PhD studentships and qualitative discussions with the students.

SQ: closing the “knowledge/do” gap.  Are people putting learning into practice?

EP: how are the NPCs getting advice out and making referrals?

HM: commented that there is lots of informal workforce development but not professional support for the AMOs/NPCs.

EP: the key element of WP1 and 3 is continuing support for the NPCs, eg. via communication, technology and mentorship.  We may suggest changes but we have to say what has been assessed, why the change should be made, how the evidence has been reviewed.  We can’t ignore this justification just because it is inconvenient.

PO’H: original idea was to have technical help to support the NPCs but in fact that isn’t the issue – the NPCs have colleagues to consult.  It is more an issue of the NPCs supporting each other, updating, setting up a professional society.

EP: in assessing baselines, we should consider, eg. exactly what the NPCs do for help, whether that works and if there are elements to be changed.  Development is about whole process, from the receptionist who takes the phone call for assistance, to the ambulance driver to the contact of the duty NPC.  Systems are important – ie. we have to look at how the NPCs fit into the system, at both the broad level of care given and the narrow level of the education being delivered.

Summary

Main deliverable is to train 50 as advanced leaders.  We are committed to evaluating their leadership abilities.

Difference between Malawi and Tanzania – in Malawi, NPCs generally work in isolation; in Tanzania there is strong leadership at the highest levels; hence there is a difference in the definition of “leadership” between the two countries.

Morning break

Feedback from pilot phase training in Tanzania

Introduction by SB and GM.  The 3 commonest delays in maternal and perinatal care are: household delay, transport delay and facility care delay, coupled with unpredictable problems in the infrastructure with flooded and blocked roads.  There is a plan get the health centres self-sufficient so that they no longer need to refer to the district hospitals.

Selection methods – relying on district medical officers to select the best people to train further.  The difficulty with sending people for training is that there is no-one to replace them.

PO’H: commented that there is an ethical issue with the amount of cover provided for the health centres

SB: responded that cover is provided – it is just difficult to obtain.

Curriculum development – “Competency-based curriculum for the training and practice of AMOs in emergency obstetric care and family planning”.

It is expensive in per diems; only one obstetrician in Kigoma.

Curriculum overview – 2 different approaches.  Kigoma has a joint approach, training AMOs and nurse-midwives.  These are the staff who would be deployed to the health centres.  There would be 2 AMOs and nurse-midwives per health centre; this low level of staffing risks burnout.

SQ: commented that there are solutions to staff management, and this is an important aspect of clinical leadership.

EP: said it is a matter of preparing a strategy and making a case, rather than simply stating that there are no funds for more staff.

GM: help has already been requested from the government, but there is no funding available.

Kigoma course details

4 months of training including 1 month internship

Training in extensive theory and practice in obstetrics and anaesthetics, given by an obstetrician and surgeon and a hired anaesthetist trainer in Dar

Some invited external lecturers from outside the country

Teaching takes place in the classroom, on ward rounds and in theatre

Assessment via log books, weekly/monthly/surprise tests, clinical practice outcome, OSCE.

Challenges

budget not compatible with the need

lack of training tools and space

unsatisfactory accommodation

misconception of the actual meaning of training

poor retention of staff.

Development goals

improving infrastructure for training

developing a council to select committed candidates

securing the retention of trained staff at the health centres

sustained support and audit

Discussion

EP: can the Kigoma course would fit into the ETATMBA “advanced training” as the training appeared to be basic.

SB: training is advanced – the NPCs have 3 years of training and a lot of practical work.  However, they are not surgeons, and have to be trained in that.

In Malawi, the NPCs are already surgically trained; they are deployed to district hospitals because the health centres lack facilities.

DD: asked if skills can be cascaded?

SB: responded that skilled individuals are very rare; it is a question of time and money to produce the replication of skills.

EP: asked to what extent there are similarities between the Kigomo course and the Ifakara course – there would need to be clear documentation to show how the courses are being developed and evaluated.

PO’H: reminded the group that from the EC’s point of view, Tanzania is only funded to train AMOs, not nurse-midwives, though this difficulty could be circumvented by classifying the nurse-midwives as NPCs.

Summary

Content of Kigoma and Ifakara courses needs further consideration.

Feedback from pilot phase training in Malawi

CM: Malawian health service delivery is dependent on the NPCs, who have a leadership role in the development of health care.  They perform more obstetric work compared to doctors in Malawi.  The project will be highly relevant for implementing the NPCs’ goals, and its delivery will minimise service disruption.

Selection methods – from the northern and central regions.  Recommendation comes from the hospital chief.

Curriculum overview – curriculum has to meet the College criteria for certification and it must be directed towards the reduction of maternal and neonatal mortality and morbidity.

Evaluation and development – clinical guidelines will be evaluated and NPCs assessed and it is hoped that the evidence will show a reduction in maternal and neonatal mortality.

Summary

Malawi aims to train 50 NPCs, offering a BSc (obstetrics) as a qualification.

Optimising teaching methodologies (DS)

About teaching and learning across knowledge, skills and attitudes.

Malawi model is different because Malawi has different needs compared to Tanzania.  It is not so much a matter of trying to introduce new technologies as optimising the use of what is already available, eg. the HBB American Obstetrics programme already known in Malawi.

Also about addressing need, such as teaching paediatric resuscitation techniques.  Drills, skills and scenarios are utilised and there is a focus on leadership – understanding obstacles and implementing change.

A facilities audit is planned for April 2011.  Reflective diaries, evaluation of training and training others all contribute to the assessments.

PO’H: much emphasis in the pilot study about the ability to train others – the NPCs were senior staff.

Assessment will involve a before-and-after study, OSCEs, MCQs and knowledge, skills and attitude training.  The PhD student will do a more extensive qualitative study on educational development, attitude and skills.

There is a major issue with evaluation because the Malawi model is so different – a group of several short courses compared to one longer course in Tanzania.  We therefore need two types of evaluation – what we have done and the changes we have precipitated.  We have been obtaining baseline data against which we can measure change.

SL: there is a similar situation in Uganda, with a shortage of staff, too few surgeons, hospital and theatres.  SL is trying to organise teams of staff with a variety of skills, led by a doctor, and to systematise training so that it involves one-third teaching, one-third clinical practice and one-third support/mentorship.

Summary

Differences between situation in Tanzania and Malawi.

Need to evaluate what we have done and the changes resulting.

Lunch

Curricula development workshop (EP; DD)

Encompassing audit, leadership, training trainers, clinical systems improvement.

Audit

Covers the questions how are we doing and what can we do better?

There is important emphasis on “we”.  It is not just a matter of how an individual is performing, more about how the whole system works.  If audit is to help, there have to be changes made so that a re-audit shows a difference.

What are the 3 audits most meaningful for the ETATMBA programme?

Discussion:

SB: maternal deaths, fresh stillbirths and neonatal death

SQ: analysing near-misses can be more productive than auditing deaths, as it produces more discussion without the implicit element of blame.

HM: is wary of audit because it can be seen as criticism and can drive underground the need for change.

SB: another term such as “maternal outcomes” helps to avoid the pejorative connotations of audit.

PO’H: it is intended the NPCs to do prospective, not retrospective, audit.

SQ: suggested 7 audits – 1. anaemia (% anaemic at antenatal clinic; HB less than 7.0), 2. HIV treatment (are 97% given ARV drugs?), 3. neonatal resuscitation (how many asphyxiated babies are resuscitated; if not, why not; equipment and skills audit), 4. breech deliveries, 5. eclampsia treatment (how many received MgSO4 ?), 6. PPH (are taught procedures followed?), 7. unsafe abortion (how many come in with sepsis and were they treated properly?).  The idea is to audit, identify a problem, solve it and re-audit.

PO’H: in terms of 3 ideal audits, maternal deaths, fresh stillbirths and neonatal mortality are givens.  Suggests that on top of these, the 3 to focus on are: neonatal resuscitation, eclampsia and PPH.

This was agreed by the rest of the group.

PO’H: further emphasised that these 3 topics are the common threads across the two countries that form the project audits, but that other topics can be added as relevant to local circumstance.

Summary

Audits will cover:

maternal deaths, fresh stillbirths and neonatal mortality

neonatal resuscitation, eclampsia and PPH

Clinical systems improvement

What is working well now?  How can we build on this?  What do we need to improve further?

Discussion:

DS: can we build into audit challenges to the system?  Exposure of deficiencies informs where and how the system needs to be improved.

SQ: empowerment of the NPCs is important – they should feel they can make a change.  Eg the scenarios illustrated deficiencies in the system, and practicing the solutions empowered the NPCs to utilise them in their own work.

PK: leadership and responsibility are important – about identifying patients and acting on findings.

Summary

EP: suggested talking to the clinical systems advisers for their ideas.

Leadership and values

Statements about leadership – leaders declaring and following values is the basis of trust.

What are the qualities of leaders?

Discussion

DD: personal qualities, working with others, managing services, improving services and setting direction.

PO’H: asked how this translates to the students?  Need to be careful to avoid “management” terminology.

DD: if focusing on managing and improving services – what are 3 or 4 competencies to demonstrate this?  Suggestions:

Ability to plan (prioritisation, improving services rather than reacting to events)

Communication (documentation)

Self-reflection / reflective practice

Ability to manage change (of self, others and system)

Balanced judgement

Working with others (mind open to change)

Passionate commitment to patient safety

Summary

DD: commented that this list could form the basis from which competencies are developed.

Training the trainers

How can training capacity be built?  What are the obstacles?  How do we overcome them?

Discussion

PO’H: in Malawi there are insufficient obstetricians to build capacity; has to be done by the NPCs.

SQ: looking for particularly capable students currently undergoing training is a practical method of selecting individuals for further leadership training.

The project is about moving away from external experts teaching the students to building up a locally-trained NPC faculty – a hands-on progression from student to tutor.  Part of this ethos would require that mentoring and support is available, together with an annual meeting or update to keep the development active and sustainable.

SB: commented on the need to monitor the knowledge/do gap following the course, so that you know improvements are continuing.

Situation in Tanzania is that there is a doctors’ support network, but nothing for the NPCs; the doctors are not always interested in helping; there is a sense that NPCs are rivals.

EP: asked if cascade can work – whether NPCs would not be able to pass on their new skills to others?

SB: cascade is in the form of NPCs recommending the course to others, rather than teaching its contents themselves.

CM: in Malawi there is discussion between staff about referrals – what can be avoided or improved.

Summary

DS - assessment drives learning.  By assessing own teaching of another, you are effectively cascading.  It is therefore important to be able to learn from others, whatever their status – they don’t have to be “experts”.

Obstacles – include time out of service, status, resources and reward.

Afternoon break

Joint working and presentation of curricula and assessment (EP and faculty)

Summary of assessment in Kigoma course

Covers MCQs (knowledge), OSCE (skills) and attitude.

Anything that could be improved?

SB: more clinical assessment and more time for training.

Summary of assessment in Ifakara course

Tests, OSCEs, log book.  Structured procedural assessment.

Discussion

DS: assessment is opportunity for “big we”.  The assessment tools can be used to create the narrative underpinning the project.

SP: the internship aspect of the NPC training enables the tutors to address whether individuals are competent.

EP: would assessors feel able to say students are not competent?  The assessment should have “real teeth”.  Are there pressures (political, or to protect the status of the course) which make it very difficult for people to be failed?

HM: commented on the use of self-assessment

EP: this is good personal practice, but cannot be seen as a test of competence.

SQ: we need to be quite specific about the extent of NPC competence – ie they can’t be fit for everything after such a short course.  Possibly using “letters of competence”, in which a list of skills pertaining to an individual is endorsed, would be useful.  Equally is important not to look for blame – eg. someone might not be “competent” to manage a ruptured uterus, but if it happens when there is no other help available, and the NPC attempts to assist, they should not be blamed for an adverse outcome.

PO’H: how would we teach and assess leadership?

EP: possibly utilise peripatetic support to go round the centres to assist.

PO’H: in order to be credible you would expect an external examiner, to provide objectivity and validity.

“Portfolio” assessment could include several aspects of the training, including self-assessment.

SQ: would be ideal to bring the NPCs together to discuss cases with each other, both for learning development and professional support.

CM: reminded about the need to amass sufficient credits to pass a course.

EP suggested:

1. a joint working/sharing of resources (eg. an MCQ “bank”)

2. OSCEs as standard

3. observing practice

4. extending from log books to portfolio work, which has a major role in mentoring and supervision.

Further ideas might include observation and support where possible, and developing peer support.

Summary

EP: suggested the assessments be reviewed for all centres and a synthesis attempted of a minimum list which all centres would cover, with the ability to add further tests if desired.

Day 2: Strategy, research and project management

Present: Senga Pemba (SP), Sidney Neleki (SN), Godfrey Mbaruku (GM), Francis Kamwendo (FK), Marshal Lemerani (ML), David Davies (DD), Chisale Mhango (CM), Doug Simkiss (DS), Siobhan Quenby (SQ), Ed Peile (EP), Anne-Marie Brennan (AMB), Paul O’Hare (PO’H), Hamed Mohamed (HM), Paul Kihaile (PK), Staffan Bergstrom (SB), Angelo Nyamtema (AN)

Overall strategy of delivery and developing infrastructure (PO’H)

In designing WPs we made estimates of requirements

Committed to 6 essential deliverables (refer to colour-coded list)

Suggestions requested.

Discussion

DD: need to raise the website profile

DS: to what extent we share teaching resources between the two countries?

PO’H: may not always be appropriate to share resources, but we do show each other our methods and exchange ideas.

EP: we do need to show what works where and why, but where there are differences it is important to explain exactly why.

PO’H: it can be powerful to say we are delivering in two different ways because of varying local circumstances.

EP: wished to raise a concern about the Kigoma 2 courses as part of ETATMBA, in order for the group to discuss them.  Emphasised that the background to the project states that NPCs in both Malawi and Tanzania can already diagnose, prescribe and perform surgery.  The purpose of the project is to select from this group individuals suitable for advanced leader training, who would in their turn become the local experts to deliver “Gotland in Africa”.  As a comparison:

|  | Kigoma | Ifakara | Malawi |
| --- | --- | --- | --- |
| Level | basic | advanced | advanced |
| Selection | no | ? | yes |
| Leadership in curriculum | no | yes | yes |
| Cascade possible | no | yes | yes |
| Audit | no | yes | yes |

EP is concerned we will compromise the analysis of Malawi and Ifakara by including the Kigoma course.  It would not be a problem to have slight variation between the Ifakara and Malawi courses, but it would be a problem to include the Kigoma course, because it would involve the comparison of a different set of parameters.

SB: disagreed with the term “basic” – the correct term should be “comprehensive”.  Leadership is possible, as is cascade, because new surgeons are being created in Kigoma.

EP: has everyone received level 1 NPC training according to the Tanzanian guidelines in both Kigoma and Ifakara?

SB: confirmed this is the case.  Asked for qualification of the term “advanced” and how this differs from “comprehensive”.

FK: NPCs in Malawi are being upgraded so they have a degree.

SB: this is not happening in Tanzania.

Defining advanced: about more qualifications, more status and more collective power.

EP: the reason we have the project is to extend level 1 training.

SP: level 1 training defined as two-year course in medicine, surgery, obs and gynae, childcare and community medicine.  Beyond this, there is variation in experience depending on where AMOs are posted.  At a health centre, there are few colleagues and services and no opportunity to practice surgery.  But if the AMO is placed in a district hospital, there is an opportunity for much more supported learning.  Health centres are being upgraded and will undertake surgery.  Leadership will emerge from this.

DS: all the AMOs can in theory perform the basics, but in practice they don’t have an opportunity to exercise their skills.  We can therefore still be in line with the project objectives – the longer course provides a catch-up, but the AMOs do fulfil the basic criteria.

EP: we need to fit in with the project aims, which are that people are already performing effectively to an advanced level.  This doesn’t mean the less experienced people should be entirely excluded – they can still contribute to the development of guidelines – but that the analysis should only include the more experienced ones (ie the Ifakara trainees) who meet the guidelines for the “advanced leaders” criteria on ETATMBA.

PK: after initial training, people are posted to district hospitals for at least a couple of years before being sent to a health centre.

SP: the leadership element is not present in Kigoma.  We need to decide what to do.

GM: there is an assumption that after AMO training, individuals will have a mentor and induction.  A fast learner takes 2-3 months to be quite confident.  Previously, they might then be posted to health centres.  Now we have a situation where the government wants to upgrade the health centres, and it would not be appropriate to populate these with newly-trained AMOs who have no district hospital experience.  We therefore would have to stratify the AMOs and select for further training those who have already passed through a district hospital.

SB: suggested Tanzania does more audit; asked what audit Malawi completes.

CM: maternal mortality has to be reported in 72 hours.  There are also conflicting maternal mortality figures.  They need to reduce case fatality rates, and this can best be done by using NPCs with influence and experience.

FK: Malawi is smaller; it is a shorter distance to travel from health centre to district hospital.  Tanzania’s geography makes this less practical.

PK: focusing on safety to practice in both Malawi and Tanzania – how confident is Malawi that the NPCs are safe?  If they are safe, why is the Malawi maternal mortality rate higher?

FK: study compared COs with NPCs and found no difference in outcome.  The ETATMBA project is about building capacity: getting people to think and assess their practice.

SP: it is not just about performing sections, but about a wider spectrum of good care.

CM: asked why the Kigoma 2 course is not the same as the Ifakara course?

EP: the Ifakara course enables much more opportunity for reflective practice and, discussions with tutors.  Can the same level of learning be delivered in Kigoma?

SB: responded that there is not much difference between the two sets of AMOs.

SP: asked him if he would address EP’s query specifically.

SB: responded that the curriculum is identical between Ifakara and Kigoma.

PO’H: is leadership teaching delivered at the Kigoma course?

SP: if the courses are not delivering leadership training, they should be changed.

PO’H: there is scope for adjusting the courses – we are only committed to developing a small baseline number of trainees.

Summary

SP: we can discount the Kigoma 1 course, and can amend Ifakara 1 and Kigoma 2 and subsequent courses to include leadership training.

This discussion concluded with the agreement that the Kigoma course would deliver the Ifakara curriculum and would include leadership training as for Ifakara.

Reports from WP1 (CM)

Developing workforce by NPCs in more advanced obstetric care

Malawi

CM made a short presentation on Malawi.  The government plans to merge the College of Health Sciences, which trains COs, with the University of Malawi to reduce costs.  A degree will be offered.

DS: commented that our NPC advanced training course is planned to be the one adopted by the College of Medicine.

PO’H: selection and engagement is underway.

Tanzania

GM made a short presentation on Tanzania.  NPCs are a good resource to address the limited medical capacity.  Good antenatal clinic attendance rate – 97% attend one or more appointments, enabling care to be planned appropriately.

Morning break

Reports from WP2 (SB)

Developing improved clinical guidelines

SB: described a current guide to emergency obstetric care as not accurate or up-to-date.

Discussion

PO’H: we need an urgent action plan for the development of guidelines – the report to the EC is due by January 2012.

CM: Malawi guidelines are up-to-date.

GM: it would be more productive to revise and update the existing guidelines rather than suggest to the Ministry that they need to be completely re-written.

EP: enquired whether the government would accept an approach that treated the guidelines as a living tool.  We should provide evidence and justification for any revision.

GM: considered that the government would find this acceptable.

FK: we have to provide our own evidence for solutions which work in Africa, not just import western norms.

DS: there are time constraints – any amendments have to be organised in the next 8 months.

PO’H: the priority is to develop the guidelines, not to obtain complete government agreement.

CM: queried if the funding covers dissemination of the new guidelines to government departments.

PO’H: there is some funding available for dissemination in accordance with the project’s aims and objectives.

Summary

Guidelines need to be reviewed as a matter of urgency.

WP3 (DD)

Clinical education leadership and professional networks

Brainstorm on qualities of leadership – [refer to DD document]

EP: DD’s suggestions from yesterday’s discussion map ideally onto the Ifakara course leadership component.

SB: stressed the need to continue the training – was unwilling to wait for guidelines to be developed, though felt this could be accomplished.

SQ: commented that the Tanzanian guidelines are generally comprehensive, and greater depth can be added to the core content.

Summary

Guidelines could be used as a baseline and amended as appropriate.

Lunch

Monitoring and accounting for EC (AMB)

Reiterated the 75% EC contribution and 25% institution contribution.

Warwick as co-ordinator has overall sense of the project, but each consortium member has charge of their own budget and their own accounting.

Funds are fixed so need to be managed effectively.

Timesheets to be completed for everyone employed on the project, for the whole reporting period.

Budget headings

Direct costs (salaries) – for staff costs only.

Direct costs (other) – for all other project-related costs.  They must be eligible costs ie, within the parameters of what the EC was expecting to be billed for.  EC will generally support local rules – that is, if a particular procedure or way of doing something is a standard procedure for your own institution, the EC will allow that cost.  However, you should be careful not to claim for costs designated as ineligible by the EC.

Indirect costs or overheads – structural and support costs which are necessary for the host’s general functioning.  For example, building rental and depreciation costs, water, gas, electricity supplies, maintenance.  As with other costs, only 75% of the total will be funded by the EC.  Your finance department will be responsible for managing this area of the funding – it isn’t available for use on the project.

Audit – a standard sum of EUR 2,588 is allocated for audit.  This is the only item in the budget refunded at 100%.  These funds are not available to be spent on the project.

It is vital to keep clear, local records and files for the day-to-day management of the funds.  Copies of quotes, invoices, receipts, should all be retained and filed.  If travelling by air or rail, keep boarding cards / tickets as proof of travel.

Records can be audited for up to 5 years after the end of a project, so files should be archived securely until 31st July 2019.

Reporting – when submitting reports, think in terms of audit.  The EC don’t like to see large sums of money put against a vague description.  It is better to provide a more detailed description, and to break down the sums spent into plenty of detail.

Summary

Clear record-keeping vital.

AMB to send CM further information on timesheets.

Committees

The following committees were set up:

Steering Committee

Members: Peter Winstanley, Paul O’Hare, Godfrey Mbaruku, Staffan Bergstrom, Neil Johnson (possibly), David Davies, Senga Pemba, Chisale Mhango, Francis Kamwendo, Siobhan Quenby, Doug Simkiss, Anne-Marie Brennan

External Advisory Board

Will involve a teleconference once or twice a year, plus reading steering committee minutes.

PO’H: proposed Samuel Luboga (Uganda)

DS: proposed Tom Lissauer (London; EP to approach Dr Lissauer)

EP: proposed an anaesthetist (unnamed)

AN: will propose a Tanzanian member

CM: will identify a Malawian member

PO’H will identify a lay member

PO’H: proposed Nynke van den Broek (Liverpool School of Tropical Medicine)

Quality Management Committee

To comprise PO’H

AMB: will identify Tanzanian and Malawian members

Ethics Advisory Committee

Dr Anne-Marie Slowther

AMB: will identify Tanzanian and Malawian members

Summary

Potential committee members to be approached as detailed above, as soon as possible.

Research and research capacity in Malawi and Tanzania (DS)

Research protocol involves:

Comparing skills and behaviour before and after training and practice; evaluating delivery and implementation training, exploring changes in health care outcomes comparing intervention with controls.

Plan to train 50, then a further 50 (ideally trained by the Malawi faculty).

Primary outcome is perinatal mortality, pragmatically defined as fresh stillbirths and neonatal deaths up to the time of discharge from the health care facility.

Secondary outcomes are fresh stillbirth rates, neonatal mortality rates, maternal death rates, recorded data (eg PPH, c-section, eclampsia), availability of resources (eg blood, drugs) and use of resources.

Study design – before-and-after for evaluation of the educational programme; cluster randomised trial for evaluation of perinatal mortality.

How can we build research capacity in Malawi through the project?

Discussion

GM: PhD students can use the project as a platform to develop their own studies and research.

PO’H: the CARTA route has been abandoned as the structure is such that an award-winning student must be taken on – this is unsuitable for ETATMBA.

FK: there is an issue with the College of Medicine not offering PhDs – students have to be registered at another university.

Summary

PhD students need to be registered immediately.

Professional networks and support (DD)

What kinds of support are required?

Should encompass a mixture of reflection in action (just-in-time support) and reflection on action (peer support, mentor support, advice, guidance and updating).

In terms of professionalisation of the NPC network – would a society or association be suitable?  Could it build on an existing network?

Discussion

FK: NPCs in Malawi have an association of their own.  Previously were affiliated to the Medical Association but for the last 3 years have been trying to build up their own association.  FK in favour of some kind of fellowship with the obstetricians.

GM: during training, AMOs can consult colleagues and senior staff; there is less support once qualified.  Hoping to provide support with mobile phones and utilising a toll-free number for texting and voice messages.  Also able to utilise the fibre optic cable networking through all east African countries (including Malawi).  Some local support networks of AMOs exist, but these are tenuous and lack power.

PO’H: asked if GM could find out if toll-free number could be adapted for use in the project.  Also if SB’s Ericsson contacts could assist.

GM: agreed to investigate this.

PO’H: suggested that for the purposes of ETATMBA that those trained on the project should develop the professional network.  Felt there was a separation between the political and educational elements of an association, and suggested the educational element should be prioritised.

EP: disagreed with this separation, and suggested a professional association may be stronger and more energetic if it encompasses both education/development and working terms and conditions.

SQ: suggested working straightaway with the current students to vote in a committee and establish some basic rules and regulations.

DD: should examine the set-up, support and development of a professional network.

DD, FK and GM will draft a paper on the basis of the three domains as they exist in Tanzania, examining how this can be replicated in Malawi, and will develop an action plan based on that.

Summary

GM to investigate the use of a toll-free mobile number for the project.

SB to investigate if Ericsson contacts could assist.

Afternoon break

Sustainability: Action plan (PO’H)

WP1

D1.1 – recruiting and training 50 NPCs as advanced leaders (month 24)

On course.

DS: we must be able to provide delivery of assessment tools to show the course is worthwhile.

Chair of assessment group?

DD will lead; AMB to assist.  Group will consist of SP for Tanzania and CM for Malawi.

WP2

D2.2 - Delivery of working guidelines (month 12)

Chair of group?

SB will lead; AMB to assist.  Group will consist of CM for Malawi, AN for Tanzania, DS and SQ.

CM: commented that there are new guidelines in Malawi which haven’t yet gone to press.

PO’H: suggested these are circulated as soon as possible for comment.

DD: reminded that if it appears deliverable might not be met, we should inform the EC well in advance of the deadline to negotiate an alternative.

D2.3 - Delivery of evaluation report on the impact of the interventions (month 36)

PO’H will lead.

SB: asked for clarification on evaluating impact of intervention.

DD: the research protocol was structured to answer this query.

SB: expressed concern about using up allocation of person-months.

DD: commented that under-using is less of a problem than running over the budget.  The PhDs should help to absorb person-months.

WP3

D3.4 - Developing the programme and engaging medical staff (month 24)

This is all well underway.

D3.5 - Pilot professional support and mentoring network (month 24)

FK, GM and DD to establish baseline as above, which will inform action plan.

PO’H: we should aim to bring the trainees back for a one-day conference within about 2 years.  We could aim for a couple of national conferences for the NPCs in year 2.  A couple of NPCs could be invited to the international conference.

WP4

D4.6 - Website development (month3)

The website is active; development to continue (AMB and DD).

Summary

CM to circulate the new (in press) Malawi guidelines to the group for comment

Groups to be set up as detailed above.

Overview of the whole list of deliverables and milestones

“Faculty development programme” to be established and developed to cascade the teaching in both Malawi and Tanzania.

SP we can start by selecting suitable people on the current training course.

DD will help support this, with the assistance of FK for Malawi and SP from Tanzania, together with SQ and SN.

SB: expressed concern over the large number of person-months and how to utilise these.

PO’H: we anticipated the PhDs using the person-months.  These need to be started as soon as possible.

DD: the most important aspect is to meet the deliverables.

There is funding for Malawi to employ and administrator and Tanzania also have someone who could assist.  It may be useful for these staff to visit Warwick for training.

EP: there is a need to support appropriate NPCs and to develop leadership.  This should be formalised early, for the first courses, to start to model and demonstrate that the new trainees are the faculty of the future.  The work is only finished when we can show we have produced a faculty which can take training forward.

Summary

Selection of potential advanced leaders to commence immediately.