ETATMBA Teleconference

Thursday 14th November 2013 at 08:30hrs GMT
NOTES
Present:  David Ellard (Chair), Doug Simkiss, Francis Kamwendo, Chimwemwe Mvula, Staffan Bergström, Anne-Marie Brennan
Unable to contact: Godfrey Mbaruku, Senga Pemba, Chikayiko Chiwandira
1. Apologies
David Davies, Alan Davies, Chisale Mhango, Siobhan Quenby, Paul O’Hare
DE informed the committee that PO’H will be off sick for the next 3 weeks.

2. Minutes of last teleconference held on 17th October 2013
Approved.
Matters arising from minutes:

Action points where relevant are covered below.

DD not present so no update on the action points relating to him.

DS confirmed Queen Dube will be able to assist with the forthcoming Module 7 in Malawi.

GM visited Warwick as planned and had useful discussions on planning the research.

3. WP1 Training
GM not present so no update for Tanzania.

DE reported that Module 7 is about to take place in Malawi.

4.
WP2 Guidelines
Tanzania – SB reported that he has not received any information from FK on the updates to the guidelines (action point from the last meeting).

Action: FK to update SB (cc AMB) with the latest copy of the guidelines and supplementary information on the group involved in this update.

5.
WP3 Clinical education, leadership, networks
DD absent, so no update for this WP.

6.
WP4 Dissemination

DE reported that the process paper is developing well and should be submitted before the end of the year.
AMB has been attempting to contact Ed Peile for an update on the papers he is drafting, but has received no response.
Action: AMB to remind Ed Peile to send update.
7.
WP5 – Project management
a) AMB reported no further information from the EC.  The Desk Officer will send notice once the re-written Annex 1 has been sent for external review.
b) The MoH have returned some financial information for the first reporting period, but there was insufficient detail and AMB requested the missing detail be supplied.  C. Mvula has been in touch with the MoH finance office who have expanded the descriptions, but nothing has been received in Warwick yet.

Action: C. Mvula to contact the MoH finance office to request this information is sent to AMB by Friday 22nd November.

8.
Module 7, Malawi
The team depart to Blantyre on 15th November for the two-week teaching module.
DS said that some assistance will be required to run the OSCEs.

There is some earlier work from the students to review and ideas for the second professional project will be developed while the team are in Malawi.
Action: DE to send DS a summary of ideas considered at present.

9.
Any other business
None.
10.
Date of next teleconference

The next teleconference will be on Thursday 19th December at 8.30am UK, 10.30am Malawi and 11.30am Tanzania.
