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2nd Meeting minutes

Time and Date: 8pm, 7th October 2015
Venue: 3M-Nano Conference, Songyuan Hotel, Changchun, China

Apologies: Kyle Jiang, Sergei Fatikow (UOld), Jin Tong (JLU), Ahmad Johari Mohamad (UMP)

Attendance: 	Xianping Liu (UoW),  Wilhelm Pfleging (KIT), Y. Zheng (KIT), Yang Yang (UoB), Yanling Tian (Tianjin), Zuobin Wang (CUST), Jiyu Sun (Jilin Univ), Tuukka Pöyry (TUT), Ran Ding (CUST)

Minutes

1.0 Start of meeting, agenda and welcome
2.0 Round table introduction of the consortium members
Warwick, Xianping Liu	
KIT, Wilhelm Pfleging and Y. Zheng
Birmingham, Yang Yang  
Tianjin: Yanling Tian
CUST: Zuobin Wang
Jilin: Jiyu Sun
TUT, Tuukka Pöyry
3.0 Progress on Research exchange
The project has been running for over 10 months and there is bit urgency for each member to implement the proposed research exchange, so far we have:
Warwick: 
5 month-persons (2 month-persons from UMP, 3 month-persons from Warwick to CUST) so far,
KIT: 
Planned to send Patrick Fomferra (KIT, student) to CUST from 4th January 2016 -
4th March 2016
Birmingham: One person/month
TUT: to be implemented
UOld: to be implemented
4.0 Possible funding for Chinese Partners
Zuobin Wang reported that there was an agreement signed for Chinese partners to be funded by Chinese government. The agreement has been downloaded from EU website and now attached here for reference.
5.0 Consortium WPs
WP1: Knowledge base and road mapping (Warwick lead)
WP2: Surface modelling and characterisation (UOld lead)
WP3: Micro/nano fabrication of functional surfaces (KIT lead)
WP4: Functional surface devices and testing (TUT lead)
WP5: dissemination and exploitation (UoB lead)
WP6: Project management (Warwick)
Please each beneficiary/partner send me a paragraph regarding rough plan and time schedule for road mapping, technologies, applications and disseminations

6.0 Deliverables and Actions
Paper publications and patents
Joint publications are particularly encouraged/required
· Discussions on joint review papers on design and development of functional surfaces
-      Applications and selected demonstrator designs proposed will be further discussed 
-      Short project description for each exchange/secondment. This should be circulated to let all members. Wilhelm Pfleging (KIT) has made an example as attached here. 

It is worth to note that, we need to follow the guideline set by EU on all our future journal /conference paper publications. Here is the quoted instruction:
Information on EU funding — Obligation and right to use the EU emblem
Unless the Agency requests or agrees otherwise or unless it is impossible, any communication activity related to the action (including in electronic form, via social media, etc.) must:
(a) display the European Union emblem and
(b) include the following statement:
“This project has received funding from the European Union’s Horizon 2020 research and
innovation programme under the Marie Skłodowska-Curie grant agreement No 644971”
[image: C:\Users\essrp2\Documents\logo_en.gif] or [image: ]

7.0 Further Funding
Discussions were held on possible funding for H2020-MSCA-ITN and there are definitely common interests in the group. Any interest party should email Xianping Liu about their interest and potential contribution. The deadline of proposal submission is 12 Jan. 2016. 
8.0 Next meeting
The next project meeting will be mid-term project meeting and will be held in conjunction with 3M-Nano 2016 in Chongqing, China from 18- 22 July within the conference. We will have special session for FabSurfWar. Please submit your papers to the conference call.
A formal mid-term report will be required from each consortium member before the meeting. A summary presentation (PPT) will be required in the meeting.
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