| Original Application Objectives | First Annual Report (6 months) April 2020 | Second Annual Report (12 months) April 2021 | Third Annual Report (12 months) April 2022 | Fourth Annual Report (12 months) April 2023 |
| --- | --- | --- | --- | --- |
| Short Term |  |  |  |  |
| Evaluation of national policy relating to the 2 concepts of continuity of midwife and single point access. | After consultation with stakeholders the Theme decided not to undertake this work and informed NIHR of the change in the first Annual Report. | n/a | n/a | n/a |
| Co-design and evaluate local initiatives to improve care for gestational diabetes. | After consultation with stakeholders the Theme decided not to undertake this work and informed NIHR of the change in the first Annual Report. | n/a | n/a | n/a |
| Conduct a study of service provision for anal sphincter injury | Delayed due to COVID. | Study has been re-developed and is now entitled “Geographical inequalities in service provision for Childbirth Related Perineal Trauma (CRPT)”. The initial study was inconclusive but on investigation the scope had not been correctly set. | Overtaken by service delivery changes: Trusts have national funding to address the question, so studying the impact of the existing pockets of service is no longer relevant. DISCONTINUED. | n/a |
|  | New: Exploratory study developed to establish the current pathway for the management of neonatal jaundice in the community. | Progress hampered by the contractual arrangements, the complexity of the data systems and limited contact we have been able to obtain from the clinical area to enable us to understand the data. | Findings have been shared and interpreted in collaboration with midwives, neonatologists and clinical scientists, and presented to frontline staff; publication in preparation. | Publication still in preparation |
|  | New: Developing a cluster controlled randomised trial across the Black Country Local Maternity System (4 NHS Trusts) to evaluate two ways of delivering training to midwives on place of birth choices for healthy, low-risk women (BEEM Trial). | We agreed it was not longer possible due to the pressures of COVID 19 and changes to the working practices of community midwives. The BEEM Trial has been replaced, at the request of our stakeholders, with work looking at the effect of COVID 19 on postnatal services. | n/a | n/a |
|  |  | New: Effect of COVID-19 on postnatal services. | Study 1 expected to commence summer 2022 Study 2 autumn/winter 2022. | Study 1- Analysis of national HES data exploring maternal and neonatal re-admissions is underway. Study 2- exploration of local data from five maternity Trusts using the same Electronic Patient Record (BadgerNet) should begin shortly following delays in contracting. Interviews with 13 community matrons have been completed and analysis is almost complete, with a view to publication. |
|  |  | New: Survey of practice into guidelines around and women’s experiences of Induction of Labour. | Survey recently completed - 54 maternity units participated. It will provide the first evidence of any logistical problems for maternity services. | Survey across two local Trusts of women’s experience of induction of labour submitted for publication (awaiting peer review comments). National survey of policy and practice of induction of labour submitted for publication (awaiting peer review comments). First national workshop to share local quality improvement projects attended by 40 Trusts in January 2023 and publication in preparation. This study has also been presented at the British Maternal Fetal Medicine Society (BMFMS) Meeting in Birmingham in November and posters were presented in Perinatal Society of Australia and New Zealand (PSANZ) in Melbourne, Australia and the Royal College of Midwives (RCM) Research Conference in March |
|  |  | New: Attendance at Emergency Departments. | Study has completed and identified an area of Quality Improvement work to improve women’s pathway. | Local improvements in the pathway for women bleeding in early pregnancy have been highlighted. No publication planned as data difficult to interpret as no mandated recording of pregnancy. |
| Longer Term |  | New: Perinatal Mental Health. | Analysis nearing completion. | Still underway - taking longer than expected due to changes in staff and capacity within the team. |
| 1. Influence national adoption of policy. | n/a at this stage. | New: Uptake of Results in Obstetric Trials in NHS. Paused due to Covid. | Restarted. Amending the study design to better align with post-COVID health professional capacity to participate, after which we will re-open the study. | Study commenced in autumn 2022 and interviews are nearing completion. Publication planned. |
| 2. Roll out successful local implementations for wider evaluation. | a) Birmingham Symptom Specific Obstetric Triage System (BSOTS) continuing its national roll-out in maternity units. | BSOTS continuing its national roll-out in maternity units. | System continues to be adopted by Trusts. a) Planning an implementation study working with the Organisational Science Theme to examine how complex interventions become embedded in routine practice across healthcare settings, which will aid our understanding of what facilitates successful implementation of BSOTS. b) Working with the AHSN to secure some funding to review and improve the website and the training and support materials available. | BSOTS now implemented in 82 maternity units with over 50 in the process. It is now the recommended national triage system with England and the Royal College of Obstetricians and Gynaecologists (RCOG) will shortly publish their Good Practice Paper on Maternity Triage which has been authored by Professor Kenyon and Dr Nina Johns (who co-developed BSOTS). In is also implemented in two maternity units in Australia within another near to implementing it. Professor Kenyon has recently attended a conference in Australia and several other sites in Australia and New Zealand are keen on taking BSOTS forwards. Birmingham Women’s and Children’s are currently funding two midwives 40% of the time for nine months (until the end of September 2023) to support implementation across the UK. a) Survey of 74 maternity units who have implemented BSOTS began in September 2022 – completed by 65 (88% response rate). Analysis underway and publication planned. Purposeful sampling of maternity units to explore variation in sucessful implementation underway with interviews and survey planned with nine maternity units. (Working with Organisational Science theme) b) No funding secured though AHSN who have asked for the BSOTS resources to be moved off their website by the end of the year. |
|  |  |  | b) New: Improving Clinical Escalation in the Midlands | Regional initiative led by Deputy Chief Midwife (Janet Driver) to implement Escalation toolkit https://www.rcog.org.uk/about-us/quality-improvement-clinical-audit-and-research-projects/each-baby-counts-learn-support/escalation-toolkit/ across the East and West Midlands (21 Trusts). We are undertaking an evaluation of the uptake over the next 15 months to understand barriers and facilitators to successful implementation which will feed into the national safety teams. This involves interviews, focus groups and a survey and began in December 2022 following University Ethical approval. |

Table of Theme 4 Maternity Projects