Postgraduate Certificate (F1PH) and Award  (F1PJ) in Transferable Skills in Science for Advanced Researchers

# 11. Propose and Manage a Budget

Rationale

Being able to develop a well thought through and properly costed budget is one of the core business skills whatever field you work in. In addition it is important to be able to monitor the budget and to regularly compare how much is being spent against the predicted figures in order to assess any potential shortfall or underspend.

Your research project is a short, well defined piece of work that can be used to develop a model budget against which you can track and measure your spending.

NB.  You are not expected to take full financial control of your research for this task, merely develop a budget for a period of time and track your expenditure against that.

### Detailed Requirements:

Develop a budget for a three month period of your research work. This can be based on the rolling 3 month plan developed in the Research Planning task (Task 2) or a new 3 month plan drawn up specifically for this process.

The budget should cover the all Directly Incurred Costs (excluding your salary, pension & NI contributions). This covers all costs directly associated with the project such as consumables, travel, equipment purchases and time on core facility equipment, but not indirect and estates costs. Break the budget down into months 1, 2 & 3.

Record your expenditure and at the end of each month and compare it with the predicted figures and estimate the potential over/underspend at the end of the three months.  Indicate how you can address any overspend, if possible, in the remainder of the budget period.

The Excel sheet below can be used as a template for this.

### Portfolio Requirements

Minor Option: 1 CAT point

A detailed budget for the three month work plan listing all items included in the budget.

The three monthly summaries indicating predicted vs. actual expenditure with any suggestions for managing over spends.

### Transferable Skills

Budget development, financial planning and management

### Support and Training Available

RSS/LDC	Making Successful Grant Applications Course (covers costings and budgets)

LDC		Practical Project Management for Researchers course