Task Name	Duration	Date	Deliverables
Causes of cost overrun / Site Management factors / Financial Factors / Information & Comm. / Design and Documentation / Environmental factors / Political Factors / Human Resource factors / Other Related factors	40 days	1 October to 10 November 2013	Chapter Two of Research
Models and Theories / Analogy and Stochastic / Statistical cost Models / Mathematical cost models / Bottom up Approach / Top down Approach / Activity Based Cost Mode / Bayesian Modelling / Structural Equation Model / Fuzzy Modelling	40 days	11 November to 20 December 2013	Chapter Three of Research
Research Methodology / Research Philosophy & Paradigm / Research Approach / Research Strategy / Research Design / Data Collection / Quality of the Research Design	70 days	6 January to 6 April 2014	Chapter Four of Research
Results / Data Gathering / Modelling / Discussion / Results	90 days	6 April to 6 August 2014	Chapter Five of Research
Findings and Conclusion / Findings / Conclusion / Recommendation / Implication of study / Limitation	40 days	6 August to 6 October 2014	Chapter Six of Research
Review / Evaluation of write up / Proof reading and correction	30 days	6 October and 6 November	Review
Submission / Final Review / Printing / Submission	30 days	December 2014	Submission