MA in Educational Leadership (Teach First)

Improving Schools in Areas of Socio-Economic Disadvantage

SUGGESTED TIMETABLE FOR CASE STUDY RESEARCH

| Week 1 | Saturday 11/18 October 2014 | Induction (11 October - Midlands; 18 October - North East) |
| --- | --- | --- |
| 2 - 6 | 20 October - 23 November (5 weeks) | General reading about leadership and research design. |
| Week 7 | Saturday 22/29 November | Teaching Day at University (22 Nov - Midlands; 29 Nov - NE) |
|  | Before the start of the Christmas holidays | Identify a suitable topic/research focus; Consult head and colleagues. |
| 8 - 12 | 1 December 2014 – 4 January 2015 (5 weeks including Christmas Holidays) | Identify literature relevant to topic; read about research design; write assignment outline and complete ethical approval form. |
| 13 | 5 January 2015 | EMAIL tutor assignment outline and ethical approval form; Write early draft of introduction with research questions. |
| 14 or 16 | Saturday 17/31 January 2015 | Teaching Day at University (17 Jan - Midlands; 31 Jan - NE) |
| 15 | WB 19 January 2015 | Receive feedback on outline (Midlands first, then North East) Adjust research design, as needed. |
| 16 - 18 | 26 January 2015 - 22 February (3 weeks) | Read about data collection instruments. Design data and pilot collection instruments. Adjust as needed. |
| 19 | WB 16 February 2015 (Half-term?) | Write a draft of literature review and methodology sections. |
| 20 - 24 | 23 February - 29 March 2015 | Collect data (five/six week period). |
| 25- 26 | 30 March - 11 April 2015 | Write draft of analysis section (Easter holidays?). |
| 27 | WB 13 April | Write draft of conclusion. |
| 28 - 29 | 20 April - 3 May 2015 - | Finalize your submission. |
| 30 | Tuesday 5 May 2015 Midnight | Submit assignment electronically via Tabula. |