## Sheet1
Targetted Recommendation | Practical Considerations (MI Statement) | Actions | What have we done? | Status
Work to address any equality, diversity, and inclusivity considerations for technical workforces through implementation of targeted technicianspecific initiatives, and/or ensuring inclusion within wider all-staff initiatives, such as those linked to Athena Swan and the Race Equality Charter. Acknowledge that workforce characteristics of technical communities are often not uniform (e.g. reported diff erences by discipline area), with different approaches potentially needed for different communities. | *MI universities will ensure technician representatives are on their Athena Swan and Race Equality Self-Assessment Teams. *MI universities will adopt technicians specific EDI initiatives (e.g. supporting technical colleagues to attend the Herschel Programme) | *Work with ED&I on Mental Health issues in the technical community to include: Sessions on mental health awareness and wellbeing; mental health awareness day for technicians; mental health subgroup or contracts within the technical community. *Work with MI team on EDI initiatives, including incorporating the EDI checklist into recruitment processes. *Encourage technicians that identify as women to apply to the Herschel Leadership Programme * Monitor the EDI data over time in terms of representation and level *Outreach to target under represented groups * Encourage Technician to give a presentation on the Hershal programme * Case studies demonstrating EDI considerations (e.g. part-time working, flexi, WFH - TSMs to outline current EDI practices in their areas *Mental health open discussions - potentially using advocates of this from the technical community. | *TSM involved with TALENT EDI group. *Panel composition for professional services posts amended to more closely align with EDI checklist recommendations *Published and tracking data of man:woman split at each grade | Sarah Bennett and Thea Mangels to work on this area
Review how staff contributions are recognised and rewarded at department- and institution-level, and whether inclusivity exists across all job families. | *MI Universities will ensure that internal processess allow technical members of staff to be PIs, CIs and named researchers on grants *MI Universities will have clear guidelines on how technical staff are costed on research proposals *MI Universities will have guidelines that state that technical colleagues should be recognised as contributors on research outputs *MI universities will formally recognise technical colleagues as supervisors on student projects where appropriate. | *Work with R&IS on funder requirements and acknowledgement methods for Technicians. *Attend department meetings to publicise the need for fair attribution and monitor. *Consider the culture in the research environment from the technicians perspective. *Discuss and consider other methods of recognition with technicians. * Ask for input from academic and research and teaching staff on how they value their technical colleagues and how they might wish to recognise them in the future. *Implement process for supporting award nominations | *Published fair attribution guidance with mechanisms for follow up. *Worked with TALENT and UKRI on the Funding report and on the section within the commission addressing this. *We have flagged the ability for technical staff to be Pis /CoIs with RIS and taken part in the Research Technical Professional Working Group with EPSRC/UKRI. *Evidence of impact on opportunities for technical staff to lead proposals with 4 successful grants across 3 funding bodies. *We are running national events discussing funding. *Quarterly Technician Commitment Award for Outstanding Achievement launched Spring 2023 *Technical member of staff as PI on PhD project sponsored by industry
Encourage appropriate inclusion of technical staff as authors, co-authors, or contributors on published papers and presentations, including providing clear guidance for appropriate inclusion at relevant stages, and sharing examples of inclusion within newsletters etc.
Provide transparent guidelines for how technical staff can be costed on to grants, sharing examples of best practice.
Enable opportunities for technical staff to be considered as co-investigators, co-supervisors, for grants or projects.
Encourage and support events for visibility, outreach, and public engagement specifi cally for and/or including technical staff . Including e.g. showcase events, conferences, public engagement, open days, visits to local schools and colleges, T-level placements (in England), and work experience placements. | *MI Universities will run and/or support outreach activities to promote technical careers (e.g. supporting the Technicians Make it Happen scheme) | *Hold a mini conference for Technicians across the science faculty to encourage networking/collaborations. *Run annual events for Technicians including updates and showcasing opportunities. *Develop website to make it more usable as a source of information for the technical community. *Hold regular focus groups/technician meetings to discuss ongoing issues and specific topics to feed into the action plan. *Prepare a University video showcasing the work of Technicians to be used for promoting careers and also for recruitment. *Update induction processes to include introductions to the work of technicians. *Consider a more formal science faculty work experience placement scheme for schools. *Promote outreach activities in schools incorporating Technician as a career pathway. *Host T-Level placements across multiple departments *Use our technical workforce to promote the role of technicians through outreach activities. * RTP Forums * Focus Groups (January/February 2024) aimed at specific topics to feed further into the action plan | *Continue with regular Steering Group Meetings feeding in input from technicians. *Continue with regular Twitter Feed as a means of communication. *Continue to promote Technician Newsletter and incorporate more features of interest. *Set up a subgroup/working groups to involve Technicians to work on specific parts of the action plan. *Revise and update the Brochure. *Prepare a University video series showcasing the work of technicians *Research Culture funds - Outreach demos *Hosted 4 T-Level placements in WMG *Provided funds for outreach demonstrators | Paul Johnson to work on some areas Liz Harrison and Emma Brown to work on some areas Ian Hancox to work on RTProf through TSN
Support and/or deliver the collection, reporting, tracking and analysis of data on employer- and sector-wide technical workforces. For HE institutions: we call on you to submit staff records to HESA for all of your contracted technical staff (even those in England and/or NI for whom this is no longer mandatory, as of 2018/19). For all institutions: we call on you to track the size and make-up of your technical workforces. | *MI universities will submit technician staff data to HESA that is attributed to the appropriate SOC code. *MI universities will collect and analyse data on their technical workforce | *Publish roadmap of technical job roles at the University. *Publish technician numbers by category/grade/diversity and monitor/report annually. *Provide support pages on TechNet website to cover recruitment, careers advice, recognition. | *Published data on number of staff and gender at each grade *Roadmap is drafted but not published *Plans to design a careers day for technical staff in generalist/managerial roles | Liz Harrison to work on this with Emma Brown
Support the development and implementation of a new, simple, and fit-for-purpose classification for technical roles in higher education, research, and innovation at all levels, such as by creating a new job family specifically for technical roles, separate from academic, administrative, or any other job family
Take a strategic approach to the sustainability of technical skills and careers, and appropriate succession planning through horizon scanning and identifying current and potential future skills gaps. | *MI universities will appoint/identify an institutional strategic lead from a technical background, either as a new position or through modification of an existing role to ensure dedicated time for strategic oversight activity. | *Consider a jobswap/job rotation process for core technicians to enable reskilling and to provide development opportunities. *Consider a secondment process for technicians including wording on internal adverts for roles that may be suitable for secondment opportunities. *Implement a suggested transition skills programme for those wishing to develop their soft skills. *Propose a development programme in line with TALENT programme. *Collate and record development activity undertaken by technicians. | *Appointed Director of Research Technology and Technical Strategy *Appointed Deputy Director of Technical Strategy with focus on talent pipeline *Promoted and make use of the TALENT development sessions | Ian Hancox and Paul Johnson to work on these
Appoint an institutional strategic lead, e.g. Director of Technical Skills, to lead this agenda
Expand entry routes to technical roles and careers by encouraging applicants from both vocational pathways and academic pathways. | *MI universities’ role profiles for technical positions will be inclusive of vocational pathways. *MI universities will host T-Level placements. *MI universities will further utilise their Apprenticeship Levy to fund professional development for technical staff (and all staff). *MI universities will invest in trainee and apprentice technicians. *MI universities will commit to dedicated time for technical staff to undertake professional development (for example, 10 days per annum as per the Researcher Development Concordat). *MI universities will promote and support professional development for technicians. *MI universities will have technical representation on every technical vacancy recruitment panel. *MI universities will provide clearly defined career pathways for technical roles. *MI universities will explore pilot progression opportunities for expert Technical Specialist roles, akin to academic progression routes | *Review how and where technical roles are advertised and provide guidance on future recruitment campaigns, including social media *Review the current recruitment process and tailor to the needs of technicians providing a recruitment checklist. *Consider a more formal science faculty work experience placement scheme for schools. *Apprenticeships for new technicians and retention and development of current technicians. *Host T-Level students across appropriate departments | *Implementation of Technician Job Family in April 2021 with all technical staff mapped onto the Technician Career Pathway *MI Jobsite set up for advertising technician roles; all roles are also circulated to technicians *Agree and publish process for the future evaluation of technician roles to include technician input on any evaluation/matching panel. *Provide a section on the TechNet website for advice and guidance on career progression including a checklist of potential requirements at each grade. *Consider the implementation of development plans for technicians to be discussed annually at PDR; provide a template. *2 days development time and implemented work shadowing programme. *WMG role to focus on apprentices and T-Levels and institutional Deputy Director of Technical Strategy with focus on talent pipeline to expand good practice to other departments *Hosted first cohort of 4 T-Level students in WMG *Introduction of Technical Specialist Promotional Pathway to be piloted in 23/24 | Paul Johnson to work on first 3 areas, Ian Hancox on final two
Invest in apprentices and trainee technician positions, hosting placements for qualifications (e.g. T-Levels in England) and work experience placements for local schools and colleges.
Utilise the Apprenticeship Levy for training and developing technical staff
Consider piloting new opportunities for progression via Technical Specialist pathways, and/or provide opportunities and mechanisms for staff to move across career pathways and job families.
Ensure provision and protected time for training and professional development, supporting technical staff to take advantage of development opportunities, such as technical training, placements, and/or professional registration. Define a minimum yearly allowance of days for technical staff to undertake professional development.
Ensure inclusion of technical staff and/or technical expertise within endto-end recruitment processes when hiring for technical roles. This should include utilising technical expertise when compiling role profi les, advice on where to advertise, and technical input on recruitment panels. |  | *Review how and where technical roles are advertised and provide guidance on future recruitment campaigns. *Review the current recruitment process and tailor to the needs of technicians providing a recruitment checklist. *Prepare a set of pre prepared paragraphs and department photos for use in recruitment documentation. *Prepare a template CV for technicians to use for internal recruitment purposes. *Open up Technician Job Family across other University faculties. | *Changes to recruitment panel guidance to allow technical staff. *Our implemented job family. *Careers day for technical staff in generalist/managerial roles | Liz Harrison to work on this with Emma Brown
Ensure visibility of clearly defined career pathways and standardised job descriptions for technical roles and careers. Standardised job descriptions will likely have baseline commonalities, plus flexible opportunities for specialisation where needed. Ensure diverse inclusion of technical expertise during process and any reviews thereof.
Ensure representation of technical staff on department-, faculty-, and institution-level decision-making committees, boards, panels, and similar groups, through either a dedicated seat or designated technical advocates within senior leadership and/or existing members. This includes processes and committees to develop institution-wide strategies and long-term goals. | *MI universities will have technician representatives on appropriate decision making committees. | *Work with departments and governance to encourage and enable Technician input on Committees. *Attend/input to University Research and Teaching Committees to discuss Technician Commitment with research and teaching staff. *Propose a model for a positive way of interacting with research and teaching colleagues. *Work to get Technician Commitment updates on Department Meeting Agendas by requesting departments to have a slide update at each meeting which is produced and presented for them (with Technician input). *Look at ways of working to adapt/change teaching practices and methods. *Encourage teaching staff to discuss methods of teaching practices with technicians to get their input on best practice. | *Technical membership on Research Culture Forum and Research Committee. *Attended Department meetings to update on Technician Commitment *Focus groups and sub-committee to discuss research culture and positive opportunities *Engaging Technicians (in SLS) to put together module for Technologies | Thea, Robb, Tim and Adrian to work on these.
Ensure considered inclusion of technical staff within all relevant communication channels and initiatives.
Encourage formation of partnerships with organisations and initiatives that can provide technical training and wider technical networks. These partnerships can help to facilitate delivery of more technician-specific training across or within disciplines, and provide further opportunities for placements, secondments, equipment and knowledge exchange, and sharing of best practice. | *MI universities continue to build relationships with organisations that support the technical community (e.g. Science Council, industry partners etc) |  | *MI TALENT work as a partnership. *Signatory of Technician Commitment. *Co-Lead on the UK Institute of Technical Skills and Strategy *Member of staff on Technician Council *Organising committee membership of Technology Specialist Network, with multiple members. *Staff members of networks and professional societies such as Technical Managers in Universities and Royal Society of Chemistry
Sign the Technician Commitment and engage with its initiatives and network of signatories.
Be inclusive of technical staff and their considerations in conversations on sector-policy developments. | *MI universities will include technicians and/or considerations relating to the technical workforce in sector policy conversations *MI universities will support technical staff to partake in sector policy discussions and consultations (e.g. recent roundtables on BEIS People and Culture strategy) | * Include Technicians in conversations *Encourage attendance at Executive Programme for Strategic Tech Leaders *REF28 People's discussion feedback for technical voice | *MI Funds | Ian Hancox to work on this including through ITSS
Support technical staff to contribute to and/or attend government events and initiatives to develop policy.
|  | Key: *Not started *Started *Complete but may be also ongoing | Key: *Started or initial project complete with follow up. *Complete