## Revision Log (hidden)
Revision Log
Date | Description
2015-06-22 | Original Release
2015-07-17 | Added Eight Disciplines (8D) Problem Solving Template
Added Corrective and Preventive Action (CAPA) Template
Added Project Dashboard Template
2015-07-22 | Added Problem Definition and Statement Template
Added Pros and Cons Template
2015-07-30 | Added "Score 1 to 5" on House of Quality (HOQ) Template
Changed "Benefits" to "Costs" on Financials Template
Renamed Project Correlation to Project-Strategy Correlation and moved location behind Project Scoring Scheme template
Updated font color from blue to black in several templates
Updated background color from blue or green to white in several templates
2015-08-04 | Revised Improve Phase of the Lean Six Sigma Checklist: Checklist - LSS
2015-08-07 | Changed Budget to Capital in the Project Scoring Scheme template
Changed >4<12 to >4<8 and >12 to >8 in the Project Scoring Scheme template
2015-08-08 | Added Goal - SMART template
2015-08-16 | Added Cancelled and Not Started options to Status dropdown on all templates
Added Yes - green and No - red colors, Set all Yes/No to Yes
Table of Contents

## Overview
Overview
Every project contains some level and amount of risk. To manage and mitigate project risks, include the risk management plan as a key artifact in the project toolbox. Unlike issues, risks are not yet directly impacting the project and may be mitigated and prevented from turning into an issue. Should a risk turn into an issue, it will be more time consuming and costly to recover from than the original risk, had it been mitigated. A risk management plan may be used when the project: • Results in a new process, product or service • Impacts safety, quality or customer service • Is large, complex and costly Benefits of a risk management plan include: • Increase focus and attention on risks • Proactive approach for preventing risks from becoming issues • Provide a consistent approach for analyzing, prioritizing, communicating and managing risks • Provide an approach to efficiently and effectively mitigate risks • Save cost and time by identifying, prioritizing, and managing risks
Risk Management Plan Process: 1. A risk is identified during the project lifecycle 2. Risk is logged on the risk management plan template 3. Project team assesses and prioritizes the risk based on probability and impact to project health, scope, schedule, and budget 4. Project team determines response type (accept, avoid, reduce, or transfer) and response plan to mitigate the risk 5. Project team monitors and controls the risk via the response plan 6. Process is repeated when additional risks are identified The risk management plan template is a simple yet useful document to help you keep track of and manage your project stakeholders throughout the project lifecycle. It can be customized by adding or changing column headings to meet the needs of your organization.

## Risk Mgmt Plan
Risk Management Plan
Project Name: | [6 empty] | Project Manager:
|  |  |  | Probability: | Impact: | Priority Score = Probability Score x Impact Score
|  |  |  | 5 > 75% | 5 = Critical
|  |  |  | 4 > 50% | 4 = Severe | High Priority Score (Red) - Response Plan required
|  |  |  | 3 > 25% | 3 = Major | Medium Priority Score (Yellow) - Response Plan as needed
|  |  |  | 2 > 10% | 2 = Moderate | Low Priority Score (Green) - Response Plan optional
|  |  |  | 1 > 0% | 1 = Minor
| Who | When | What |  |  |  | Who | What | When | How | Other
# | Who Identified | Date Identified | Risk Description | Probability | Impact | Priority Score | Owner | Response Type | Due Date | Response Plan | Comments/Status
1
2
3 | [11 empty] | Avoid
4 | [5 empty] | 0 | [5 empty] | Transfer
5 | [5 empty] | 0 | [5 empty] | Mitigate
6 | [5 empty] | 0 | [5 empty] | Accept
7 | [5 empty] | 0
Who Identified: Enter the name of the person who identified the risk
Date Identified: Enter the date the risk was identified
Risk Description: Enter a description of the risk
Probability: Use the dropdown to select a probability the risk will occur (1 >0%, 2 >10%, 3 >25%, 4 >50%, 5 >75%)
Impact: Use the dropdown to select an impact or severity level for the risk (1 = Minor, 2 = Moderate, 3 = Major, 4 = Severe, 5 = Critical)
Priority Score: Priority score is calculated based on the probability and impact selections (probability X impact = priority score)
Owner: Enter the owner of the risk mitigation
Response Type: Use the dropdown to select a mitigation response type (accept, avoid, reduce, transfer)
Due Date: Enter a due date for the response
Response Plan: Enter a description of the response plan
Comments/Status: Enter any appropriate or necessary comments for the risk