## 1. RR Template
Risk & Issues Register
INSERT DEPT NAME HERE
INSERT DATE LAST UPDATED HERE
Risk ID (Area) | Risk / Issue Description | Risk Category | Compliance Impact? (Y/N) | Contributing factors | Risk Owner | Action Owner/s | Initial Risk (pre-mitigation) |  |  | Active Mitigation | Current Risk |  |  | Planned Mitigation | Target Date | Target Risk |  |  | Direction of Travel | Acceptable against Risk Appetite? | 12+ Current Score Reporting Required? (Y/N) | Risk Closed? | Date Risk Closed | Evidence for Closure
[7 empty] | Likelihood | Impact | Risk Score |  | Likelihood | Impact | Risk Score |  |  | Likelihood | Impact | Risk Score
CCSG-S&WH-001 | If there is not enough Marketing resource allocated to the business then there is a risk that this will result in lower customer engagement, inability to fulfil strategic objectives and will affect future profitability. This would have a reputational, financial and legal impact upon the University | D, F, R, L, P |  | - Reliance on central marketing team and budget allocation - Limited in-business knowledge - External competition with large/national marketing teams | Head of Business Development | Head of Business Development and Head of Marketing | 5 | 5 | 25 | - Annual marketing strategy aligned to key business areas and budget lines - Marketing prioritised in line with financial contribution - Working with TA6 (external agency) on membership marketing - largest financial targets | 5 | 4 | 20 | - Discussion on taking all marketing (including memberships) in-house to CCSG Marketing team rather than via TA6 - Embedding marketing strategy into business tactical plan and delivery planning - Explore new systems inline with CCSG IT development that will align us to competitors and offer a better customer experience (e.g. email software) - Push for a CRM system | 2021-07-31 | 2 | 4 | 8 |  |  | No | No
[7 empty] | 1 | 1 | 1 |  | 1 | 1 | 1 |  |  | 1 | 1 | 1
[7 empty] | 1 | 1 | 1 |  | 1 | 1 | 1 |  |  | 1 | 1 | 1
[7 empty] | 1 | 1 | 1 |  | 1 | 1 | 1 |  |  | 1 | 1 | 1
[7 empty] | 1 | 1 | 1 |  | 1 | 1 | 1 |  |  | 1 | 1 | 1
[7 empty] | 1 | 1 | 1 |  | 1 | 1 | 1 |  |  | 1 | 1 | 1
Note on C5: List all that apply: - Delivery/Performance - Finance - Reputation - Legal - People & Wellbeing - Health & Safety - Environment & Sustainability
Note on F5: Senior level - ultimately responsible for the management of the risk
Note on G5: Tactical level - responsible for driving mitigation and providing updates on the risk
Note on K5: Bullet points. Any active measures being taken to reduce the risk.
Note on O5: Bullet points. Any planned measures to reduce the risk
Note on P5: Target date for the planned mitigation. Tip: If the planned mitigation is a long duration project/programme, key milestone dates are more helpful than a date a year+ in the future.
Note on T5: Inidicates how the current score has changed from last time the risk was reviewed. Options: Up Down Static
Note on U5: Is the risk 'acceptable' against the faculty/group/dept risk appetite? Provide a brief reasoning. Definitions to be developed in 2025.
Note on V5: If the CURRENT RISK SCORE is 12+, then it should be reported at group level/at risk forums. This highlights the medium and high risks to other risk owners and senior staff.
Note on Y5: What is the justifictaion for the risk being closed? Has the traget score been met?
Note on H6: Choose score option - 1 = Very Low; 5 = Very High 1 2 3 4 5
Note on I6: Choose score option - 1 = Very Low; 5 = Very High 1 2 3 4 5
Note on L6: Choose score option - 1 = Very Low; 5 = Very High 1 2 3 4 5
Note on M6: Choose score option - 1 = Very Low; 5 = Very High 1 2 3 4 5
Note on Q6: Choose score option - 1 = Very Low; 5 = Very High 1 2 3 4 5
Note on R6: Choose score option - 1 = Very Low; 5 = Very High 1 2 3 4 5
Note on A7: Jebson-Hambly, Kimberly: Professional Services Group - Secretary to Council risk number 1

## 2. RR Completion Guidance
RR Completion Guidance
For columns/fields where further description and guidance may be required, please refer to the below. If you still require assisstance with any aspect of the Risk Register, please contact the Risk & Resilience Team at risk.management@warwick.ac.uk
Risk ID | In Excel you should use the following format: <Dept/Faculty abbrevation-first three letters of the dept-Sequential number>. Example: FAC-SEM-003 which denotes 'Faculty of Science, Engineering & Medicine, risk number 3'.
Risk/ Issue Description | This should be about recognising the cause, the risk, and the consequences - Due to [cause], [risk] may occur, which would lead to [consequence]). Use of an IF / THEN structure is particularly helfpul when describing. Example: IF the TTR guidance is not followed and the codes not adhered to, THEN there is a risk that substantial fines will be incurred, impacting finance and reputation.
Risk Category | The aspect(s) of University management most affected by the risk. There can be more than one category against each risk. Options include: Delivery/Performance - Finance - Reputation - Legal - People & Wellbeing - Health & Safety - Environment & Sustainability
Contributing factors | Please provide these as bullet points. Contributing Factors are things which contribute to: a) Increasing the likelihood of the risk happening b) Increasing the impact if it did happen c) Increasing both
Initial Risk | This section of the RR is about the risk score pre-mitigation. See Tab 3 for guidance on scoring.
Active Mitigation | Please provide these as bullet points. Please provide the following details of mitigation measures that are in place now: a) The mitigation measure b) How it helps reduce the likelihood and/or impact Example: Weekly surveys are being held to increase the knowledge and awareness of staff. This helps to reduce the risk likelihood.
Current Risk | This section of the RR is about the risk score post-mitigation. See Tab 3 for guidance on scoring.
Direction of Travel | Has the current risk score reduced (DOWN), increased (UP) or stayed the same (STATIC) since last review.
Planned Mitigation | Please provide these as bullet points. Please provide the following details of mitigation measures that will be in place in the future: a) The mitigation measure b) How it will help reduce the likelihood and/or impact Example: Monthly inspections of the equipment will take place as of Dec 2025 in order to ensure the safety of the machinery. This should reduce the likelihood of the risk. NOTE: Planned mitigation should be transferred to the 'Active Mitigation' field once it is has been actioned. This ensures that risk scoring/management is dynamic.
Target Date | Please set a feasible target date for addressing the risk. Target dates should not be too far in the future where possible, so that mitigation is dynamic and actively making a difference to the risk score.
Target Risk | This section of the RR is about the target risk score for the future. See Tab 3 for guidance on scoring. It is the aspirational risk status, taking into account the planned mitigation. It is generally expected that this will be lower than the Current Score.
Risk Appetite | Is the risk acceptable/tolerable based on the appetite defined and agreed. More guidance on this in 2025.
12+ Current Score Reporting Required? | In this field please indicate 'Yes' or 'No'. Risks with a Current Score of 12+ should be marked as 'Yes'. Those risks that do not meet this criteria should be marked 'No'.
Risk Closed? | Risks should only be closed once they have been mitigated to an acceptable level. The Risk Owner should always give consent for closure.
Evidence for Closure | It is important that there is evidence which justifies the closure of the risk.

## 3. Impact & Likelihood Scoring
Guidance on Scoring Impact & Likelihood
Use the guidance below to score the impact and likelihood of the risk. The overall 'Risk Score' should be a multiplication of these two figures. E.g. Impact 4 x Likelihood 3 = Risk Score 12. Refer to Tab 4 for guidance on what each Risk Score means.
Likelihood Scoring
| Likelihood | Score | Description
| Extremely likely | 5 | Something that will be occurring in the next few weeks or is very likely to occur during the current business / operational planning cycle. Over 75% chance of risk occurring.
| Probable | 4 | Something that is likely to occur during the next business / operational planning cycle. Between 50% and 74% chance of risk occurring.
| Possible | 3 | Something that could happen at some point over the current strategic planning cycle. Between 25% and 49% chance of risk occurring.
| Unlikely | 2 | Something that is unlikely to occur based on current intelligence. Between 10% and 24% chance of risk occurring.
| Highly unlikely | 1 | Something that is highly unlikely to occur based on current intelligence. Less than 10% chance of risk occurring.
Impact Scoring
IMPACT CATEGORY
| Impact | Score | Delivery/Performance | Finance | Reputation | Health & Safety | Legal | People & Wellbeing | Environment & Sustainability
| Very High | 5 | - Multiple Depts unable to continue service delivery - Resolution required at Executive level - Prolonged disruption to operations - Major decreases across a broad range of KPIs - Failure to deliver one or more strategic goals | - Major impact on finances available to affected business area (£10 million+) | - Sustained (for a number of days within 1 week) adverse international / national media coverage - Cancellation of events, withrawal of donations, cancellation of conferences - Significant reduction in confidence and trust from existing and/or prospective students and large increase in actual and threatened student drop-outs - Widespread and prolonged reduction in public confidence - Criticism at Government level - Major unjustified impact on human rights or diversity | - Fatal incidents - Health effects - affecting more than one person or chronic medical disability due to, for example, exposure to a probable carcinogen - Property damage - the loss of one or more buildings | - Prosecution of University - Successful, substantial claims/fines against the University outside the limits of our insurance - Knowingly failing to comply with legislation - Failure to meet Government requirements | - Loss of a number of members of the Executive Team - Redundancies affecting >100 people - Major drop in staff morale - Major reduction in student numbers (>20%) - Huge increase in staff accessing EAP, very high levels of stress related sick leave across a number of areas, wellbeing reports made to Managers in several Depts/areas - Significant increase in student drop-outs/non-continuation rates, high increase in students accessing wellbeing support | - Major and widespread contamination of groundwater and/or soil - Significant and prolonged air pollution - Extremely damaging impacts on Biodivesity and protected species - Large quantities of non-recyclable waste materials produced
| High | 4 | - One Dept unable to continue service delivery - Resolution required at Executive level - Medium to Long term University-wide disruption to operations - Serious decrease in performance across several KPIs - Failure to deliver on a priority strategic goal | - Serious impact on finances available to affected business area (£5-10 million) | - Persistent (frequent/regular news coverage) adverse national media coverage - Threats of Event cancellation and donation withdrawal - Significant reduction in confidence and trust from existing and/or prospective students and significant threat of student drop-outs - Temporary reduction in public confidence - Criticism at Local Government level or intervention by the UK Research & Innovation and/or Office for Students office - Serious unjustified impact on human rights or diversity | - Injury - permanent disability or other reportable injury/disease, for example, amputations or major fractures. Severely life shortening diseases. - Health effects - affecting one person, toxic by inhalation/contact with skin or swallowed. Damage to eyes, respiratory system, skin sensitisation, effects on fertility, prolonged exposure risks, limited evidence of carcinogenic effects. - Property damage; major. Extremely flammable and explosive substances. - Lost time; > 3 months | - Potentially successful claims/fines against the University outside the limits of our insurance - Failure to comply with legislation - Failure to deliver on stated Government priority | - Loss of one member of the Executive Team - Redundancies affecting between 60-99 people - Serious drop in staff morale - Serious reduction in student numbers (10-15%) - Significant increase in staff accessing EAP, high levels of stress related sick leave across several areas, wellbeing reports made to Managers in more than one Dept - Increase in student drop-outs/non-continuation rates and increase in students accessing wellbeing support | - Significant but limited (in terms of area) contamination of groundwater and/or soil - Moderate and prolonged air pollution - Damaging impacts on Biodivesity and protected species - Large quantities of non-recyclable waste materials produced
| Medium | 3 | -Multiple teams within a Dept unable to continue service delivery - Resolution required at Faculty/Group level - Short to Medium term disruption to Faculty/Group activity - Significant decrease in specific KPIs - Adverse effect on objectives | - Significant impact on finances available to affected business area (£1-5 million) | - Sustained adverse local media coverage - Poor public sentiment - Moderate reduction in confidence and trust from existing student community and moderate threat of student drop-outs/non-continuation rates - Limited and temporary reduction in public confidence - Short term customer dissatisfaction - Internal or external audit criticism - Significant unjustified impact on human rights or diversity | - Injury; loss of consciousness, lacerations, concussion, serious sprains, minor fractures, deafness, asthma, burns or injury resulting in absence from work. - Health effects; acute health effects, e.g. harmful if inhaled/contact with skin/ or swallowed, dermatitis, ill-health leading to minor but permanent disability. - Property damage; serious but confined to a work-room or area. Oxidising, flammable and highly flammable substances. - Lost time; > 4 days – 3 months | - Significant claims/fines against the University, within our insurance cover - Failure to deliver on multiple other Government policies | - Loss of a number of senior managers - Redundancies affecting between 30-59 people - Significant drop in staff morale - Significant reduction in student numbers (5-10%) - Slight increase in staff accessing EAP, small increase in stress related sick leave in a concentrated area of the University, wellbeing reports to Managers in one Dept - Very small increase in student drop-outs/non-continuation rates and some increase in students accessing wellbeing support | - Moderate contamination of groundwater and/or soil - Moderate-Minimal air pollution - Limited (in terms of area affected) but significant damaging impacts on Biodivesity - Moderate quantities of non-recyclable waste materials produced
| Low | 2 | - One team unable to continue service delivery - Resolution required at Department level - Short term disruption to Departmental service delivery - Minor decrease in specific KPIs - Failure to achieve an internally agreed objective | - Minor impact on finances available to affected business area (£100k - £1 million) | - Isolated adverse media coverage - Minor damage to reputation - perception, feedback surveys, SM activity - Very limited and temporary reduction in public confidence - Reduction in confidence and trust from existing student community and minor threat of student drop-outs/non-continuation rates - Internal criticism - Minor unjustified impact on human rights or diversity | - Injury - Wisespread bruising, minor cuts, light abrasions - Health effects - mild irritation of skin or eyes, headaches, ill-health leading to temporary discomfort - Property damage; minor - Lost time; < 3 days | - Minor claims, complaints within our insurance cover - Failure to deliver on one Government policy | - Redundancies affecting between 10-29 people - Minor drop in satff morale - Minor reduction in student numbers (1-5%) - Slight increase in staff accessing EAP, small increase in short term stress related sick leave in one Dept, possible wellbeing reports to Managers in one Dept - A small increase in students accessing wellbeing support | - Minimal contamination of groundwater and/or soil - Minimal air pollution - Limited (in terms of area affected) and moderately damaging impacts on Biodivesity - Moderate-minimal quantities of non-recyclable waste materials produced
| Very Low | 1 | - Negligible impact on service delivery - Resolution required at team management level - Minor reduction to department service delivery - Negligible decrease in specific KPIs - Partial failure to achieve an internally agreed objective | - Negligible impact on finances available to affected business area (£0 - 99k) | - Negligible adverse media coverage - Minimal damage to reputation - Minor and temporary reduction in public confidence - Temporary and minor reduction in confidence and trust from existing student community - Low level internal criticism - Negligible unjustified impact on human rights or diversity | - Very minor injuries; minimal cuts & bruises - Property damage; minimal - Lost time; < 1 day | - Negligible claims or complaints - Failure to deliver on aspects of Government policy | - Neglible drop in staff morale - Redundancies affecting between <10 people - Neglible reduction in student numbers (<1%) - Minor increase in short term stress related sick leave in one Dept (only) and some minor concerns about staff wellbeing flagged to Managers in one Dept - Minor increase in students accessing wellbeing support | - Trace contamination of groundwater and/or soil - Trace air pollution - Limited (in terms of area affected) and minimal undesireable impacts on Biodivesity - Small quantity of non-recyclable waste materials produced

## 4. Overall Risk Score
Guidance on Risk Score
Use Tab 3 to calculate the Risk Score. Once you have this figure you can refer to the below to define how low or high your risk is.
Impact | 5 Very High | 5 | 10 | 15 | 20 | 25
| 4 High | 4 | 8 | 12 | 16 | 20
| 3 Medium | 3 | 6 | 9 | 12 | 15
| 2 Low | 2 | 4 | 6 | 8 | 10
| 1 Very Low | 1 | 2 | 3 | 4 | 5
|  | 1 Highly Unlikely (-10%) | 2 Unlikely (10-24%) | 3 Possible (25-49%) | 4 Probable (50-74%) | 5 Extremely Likely (75%+)
Likelihood
Risk is defined as being 'Very High'
Risk is defined as being 'High'
Risk is defined as being 'Medium'
Risk is defined as being 'Low'
Risk is defined as being 'Very Low'