## 2019-20
Project/Task | Lead | Others | Lead | Support | Status | Date | [10 empty] | Committees | Date
[6 empty] | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01 | 2020-01-01 | 2020-02-01 | 2020-03-01 | 2020-04-01 | 2020-05-01 | 2020-06-01 | 2020-07-01 | UHSEC | 2019-11-04
Establish Audit/Inspection Close Out Metrics (95%) | JP |  | JP | CF/MP | Completed | [12 empty] | 2019-12-19 | bar: 2019-09-01
Establish Incident Close Out Metrics (95%) | JP |  | JP | CF/MP | Completed | [12 empty] | 2020-02-06 | bar: 2019-09-01
Create Dashboard for Incident and Inspection Close-out | JP |  | JP | MP | Completed | [12 empty] | 2020-04-02 | bar: 2019-09-01
Monthly review of Objectives for Incidents/Inspections | JP |  | JP | All | Completed | [12 empty] | 2020-05-28 | bar: 2019-09-01
Policy Document Annual Review |  |  | JP | All | Completed | [12 empty] | 2020-07-23 | bar: 2019-10-01
Leadership and Management Document Review |  |  | JP | All | Completed | [11 empty] | UHSC | 2019-11-06 | bar: 2019-10-01
Risk profile review |  |  | JP | All | Completed | [12 empty] | 2020-03-04 | bar: 2019-10-01
Legal register review |  |  | JP | All | Completed | [12 empty] | 2020-06-10 | bar: 2019-10-01
New HODs Training |  |  | JP | CF | Completed | [11 empty] | GMBSC | 2019-10-24 | bar: 2019-10-01
6 Monthly Bsi Audit | JP | All | JP | All | Completed | [12 empty] | 2020-01-09 | bar: 2019-10-01; 2020-04-01
Internal Audits |  |  | SD | All | WIP | bar: 2019-11-01; 2020-02-01; 2020-05-01
OH Contracts Review (Fusion and Cohort) | JP |  | JP | CG | Completed | [12 empty] | 2020-04-23 | bar: 2019-10-01 to 2019-11-01
Self-Reporting Assessments | MP | HSAs/HSOs | JP | MP | Completed | [12 empty] | 2020-07-09 | bar: 2019-10-01 to 2019-11-01
New Policy/ Procedure Global Travel Risk | CF | IG, MB | CF | All | WIP | bar: 2019-10-01 to 2019-11-01
Fire Drills Accommodation | MP | HSAs/HSOs | SW | MP | WIP | bar: 2019-10-01 to 2019-11-01
Management Review (ARC and Exec) |  |  | JP | CF/GH | WIP | bar: 2019-11-01; 2020-05-01
Assets and PPM (incl inventory) Phase 2 (proof of concept) |  |  | JB | JP | WIP | bar: 2019-11-01 to 2019-12-01
SHE Software - Risk Assessment (to include training) |  |  | JP | All | WIP | bar: 2019-11-01 to 2019-12-01
Health surveillance (Estates) | JB | IG, JKP, JW | SD | CG | WIP | bar: 2019-11-01 to 2019-12-01
Fire Drills (non-accomodation) |  |  | SW | MP | WIP | bar: 2019-12-01 to 2020-03-01
Update Lone Working Arrangements |  |  | CF | HSOs | WIP | bar: 2020-02-01
Update Student Placement Arrangements |  |  | CF | HSOs | WIP | bar: 2020-02-01
Moodle Courses From Leadership Document (x4) | SD | HSAs/HSOs | LG | JP | WIP | bar: 2020-02-01
ITS Risk Assessments |  |  | GH | GD | bar: 2020-02-01
Contractor Control Audit | GH | HSAs/HSOs | GH | SD | WIP | bar: 2020-03-01
Hazard Management System Review/Update - QuEMIS |  |  | JP | CF | WIP | bar: 2020-03-01
PUWER Audit (SEM Faculty) | CF |  | CF | HSOs | bar: 2020-03-01
Fire Risk Assessments | SW | SW | SW | GH | WIP | bar: 2020-03-01 to 2020-05-01
Chemical Inventory Tool (Implementation | JP | CF, JB | JP | CF/JB
CCSG 45001 Audit |  |  | GH | GD | bar: 2020-03-01 to 2020-05-01
Review of departmental H&S Plans |  |  | CF | GH | bar: 2020-03-01
Update Bio-Security Plan |  |  | IG | CF | bar: 2020-03-01
Non-ionising radiation audit/review |  |  | JB | CF | bar: 2020-03-01
Self-Reporting Assessments follow-up |  |  | MP | All | bar: 2020-03-01
COSHH Audit (SEM) |  |  | CF | JB/IG | bar: 2020-04-01
First Aid Quota review |  |  | JP | All | bar: 2020-04-01
CCSG Safety Campaigns - Transport - Allergens |  |  | GH | GD | bar: 2020-04-01
Fire Strategy Assessments |  |  | SW | GH/MP | bar: 2020-01-01 to 2020-05-01
GAP Analysis of ISO 45001 - Warwick Accommodation |  |  | SD | GH | bar: 2020-06-01

## 2020-21
Project/Task | Lead | Others | Lead | Support | Status | Date | [10 empty] | Committees | Date
[6 empty] | 2019-09-01 | 2019-10-01 | 2019-11-01 | 2019-12-01 | 2020-01-01 | 2020-02-01 | 2020-03-01 | 2020-04-01 | 2020-05-01 | 2020-06-01 | 2020-07-01 | UHSEC | 2019-11-04
Establish Audit/Inspection Close Out Metrics (95%) | JP |  | JP | CF/MP | WIP | [12 empty] | 2019-12-19 | bar: 2019-09-01
Establish Incident Close Out Metrics (95%) | JP |  | JP | CF/MP | WIP | [12 empty] | 2020-02-06 | bar: 2019-09-01
Create Dashboard for Incident and Inspection Close-out | JP |  | JP | MP | WIP | [12 empty] | 2020-04-02 | bar: 2019-09-01
Monthly review of Objectives for Incidents/Inspections | JP |  | JP | All | WIP | [12 empty] | 2020-05-28 | bar: 2019-09-01
Policy Document Annual Review |  |  | JP | All | WIP | [12 empty] | 2020-07-23 | bar: 2019-10-01
Leadership and Management Document Review |  |  | JP | All | WIP | [11 empty] | UHSC | 2019-11-06 | bar: 2019-10-01
Risk profile review |  |  | JP | All | WIP | [12 empty] | 2020-03-04 | bar: 2019-10-01
Legal register review |  |  | JP | All | WIP | [12 empty] | 2020-06-10 | bar: 2019-10-01
New HODs Training |  |  | JP | CF | Completed | [11 empty] | GMBSC | 2019-10-24 | bar: 2019-10-01
OHSAS Audit - 6 Month | JP | All | JP | All | Completed | [12 empty] | 2020-01-09 | bar: 2019-10-01; 2020-04-01
OH Contracts Review (Fusion and Cohort) | JP |  | JP | CG | WIP | [12 empty] | 2020-04-23 | bar: 2019-10-01 to 2019-11-01
Self-Reporting Assessments | MP | HSAs/HSOs | JP | MP | WIP | [12 empty] | 2020-07-09 | bar: 2019-10-01 to 2019-11-01
New Policy/ Procedure Global Travel Risk | CF | IG, MB | CF | All | WIP | bar: 2019-10-01 to 2019-11-01
Fire Drills Accommodation | MP | HSAs/HSOs | SW | MP | WIP | bar: 2019-10-01 to 2019-11-01
Management Review (ARC and Exec) |  |  | JP | CF/GH | bar: 2019-11-01; 2020-05-01
Assets and PPM (incl inventory) Phase 2 (proof of concept) |  |  | JB | JP | bar: 2019-11-01 to 2019-12-01
SHE Software - Risk Assessment (to include training) |  |  | JP | All | bar: 2019-11-01 to 2019-12-01
Health surveillance (Estates) | JB | IG, JKP, JW | SD | CG | bar: 2019-11-01 to 2019-12-01
Fire Drills (non-accomodation) |  |  | SW | MP | bar: 2019-12-01 to 2020-03-01
Update Lone Working Arrangements |  |  | CF | HSOs | bar: 2019-12-01
Update Student Placement Arrangements |  |  | CF | HSOs | bar: 2019-12-01
Contractor Control Audit | GH | HSAs/HSOs | GH | SD | bar: 2019-12-01
Moodle Courses From Leadership Document (x4) | SD | HSAs/HSOs | LG | JP | bar: 2019-12-01
ITS Risk Assessments |  |  | GH | GD | bar: 2020-01-01
Hazard Management System Review/Update - QuEMIS |  |  | JP | CF | bar: 2020-01-01
PUWER Audit (SEM Faculty) | CF |  | CF | HSOs | bar: 2020-01-01
Fire Risk Assessments | SW | SW | SW | GH | bar: 2020-02-01
Chemical Inventory Tool | JP | CF, JB | JP | CF/JB | bar: 2020-03-01 to 2020-04-01
CCSG 45001 Audit |  |  | GH | GD | bar: 2020-03-01 to 2020-04-01
Internal Audits |  |  | SD | All | bar: 2019-11-01; 2020-02-01; 2020-05-01
Review of departmental H&S Plans |  |  | CF | GH | bar: 2020-03-01
Update Bio-Security Plan |  |  | IG | CF | bar: 2020-03-01
Non-ionising radiation audit/review |  |  | JB | CF | bar: 2020-03-01
Self-Reporting Assessments follow-up |  |  | MP | All | bar: 2020-03-01
COSHH Audit (SEM) |  |  | CF | JB/IG | bar: 2020-04-01
First Aid Quota review |  |  | JP | All | bar: 2020-04-01
CCSG Safety Campaigns - Transport - Allergens |  |  | GH | GD | bar: 2020-04-01
Fire Strategy Assessments |  |  | SW | GH/MP | bar: 2020-01-01 to 2020-05-01
GAP Analysis of ISO 45001 - Warwick Accommodation |  |  | SD | GH | bar: 2020-06-01