[image: image1.png]Athena SWAN




ATHENA SWAN CHARTER

[image: image7.jpg]THE UNIVERSITY OF

WARWICK




ANNUAL REPORT

JUNE 2013
CONTENTS











PAGE
SUMMARY








       1
1. INTRODUCTION







        2
1.1 Athena Steering Group




       2
1.2 Athena Network Group




        3
2. SUMMARY OF WARWICK ATHENA SWAN SUBMISSIONS

        4
3. GOOD PRACTICE INTIATIVES IMPLEMENTED AS PART

OF THE ATHENA SWAN PROCESS




        8
4. WHAT IS PLANNED NEXT?





    
        8
APPENDIX 1: PROGRESS MADE AGAINST THE BRONZE ACTION PLAN       10
APPENDIX 2: ATHENA SILVER SUBMISSION ACTION PLAN

      25   
APPENDIX 3: GOOD PRACTICE INITIATIVES IMPLEMENTED AS PART         38

OF THE ATHENA SWAN PROCESS

SUMMARY
The University of Warwick became a member of the Athena SWAN Charter in 2009.  The Charter recognises and celebrates good employment practice for women working in Science, Technology, Engineering and Medicine (STEMM) in Higher Education and attempts to address gender inequalities within disciplines.  Commitment to the Charter is enabling the University to raise its Equality and Diversity profile, both internally and externally, and is providing a framework on which to build on current good practice.  Further information about the Athena Charter can be found at: http://www.athenaswan.org.uk/html/athena-swan/
This is the second annual report on the University of Warwick Athena SWAN work since the successful submission for a Bronze Institutional award in 2009/10.   
The report summarises the progress that has been made against the Bronze Action Plan since the award and comments on new initiatives that have formed part of the Athena Silver application that was submitted in April 2013 (see Appendix 1 for a detailed account of progress made against the Bronze Plan and Appendix 2 for the Silver Action Plan).  Warwick has built upon its Bronze award by maintaining momentum on established initiatives and, importantly, identifying new and creative interventions and support which successfully enhance the career opportunities for staff.  Many of the principal accountabilities originally identified in the Bronze Plan have now been accomplished or partially accomplished, and work is continuing to be progressed on some of the actions that were given a longer timeframe for achievement.
Many of the Athena initiatives form part of the University’s Equality Objectives 2012-2015 and progress (as of May 2013) against the objectives can be seen at:

 http://www2.warwick.ac.uk/services/equalops/singleequalityscheme/)

Attention during 2012/13 has focused on the development of a new Athena Action Plan which has been submitted as part of the University’s Silver Award submission in April 2013 (Appendix 2), and in supporting other STEMM departments’ that are currently working on progressing their own departmental Athena work.

1.
Introduction
1.1
Athena Steering Group
The Warwick Athena Steering Group continues to meet termly and the membership, as can be seen below is unchanged from 2012.  The Athena Steering Group is chaired by Professor Tim Jones, Pro-Vice Chancellor for Knowledge Transfer, Business Engagement and Research (Science and Engineering).  The Athena Steering Group provides University-level strategy for Athena taking oversight of University-wide activities to ensure that Warwick does not disadvantage women within its talent pool, and considers new initiatives, issues of concern and monitors the career progression of women in STEMM based Faculties.
The key aim of the Athena Steering Group is to review and develop strategies for the implementation of appropriate activities within the Athena agenda and to encourage the career development of women in STEMM within the University of Warwick.  The Steering Group addresses issues that either cannot be managed at departmental level or where there is institutional wide impact.
The Group Membership consists of:

Professor Tim Jones, Pro-Vice Chancellor for Knowledge Transfer, Business Engagement and Research (Science and Engineering) – Chair



Professor Pam Thomas – Chair of the Board of Faculty of Science



Professor Peter Winstanley – Chair of the Board of Faculty of Medicine



Professor Alison Rodger – Chair of the Athena Network Group



Mr Michael Blair – Acting Deputy Director of Human Resources



Mrs Leonie Walls – Human Resources Manager, Equality and Diversity



Mrs Sandra Beaufoy – Human Resources Adviser, Equality and Diversity

The Terms of Reference of the Athena Steering Group include a vision statement as follows:
The Athena Steering Group’s role is to take oversight of University-wide activities to ensure that Warwick does not disadvantage women within its talent pool, thus attracting and retaining the best staff and creating a working environment that enhances academic performance and general well-being.  The particular focus of the Group is on STEM disciplines and their progress towards obtaining Athena SWAN awards.  The Group reports to Senate via the Equality and Diversity Committee and directly to Steering.

The role of the group is to:

1.  Address gender inequalities within Science and Medicine disciplines.

2. Consider innovative means of providing sustainable academic careers for women.

3. Construct and agree an Action Plan to assist the University achieve Athena Silver recognition (submission in April 2013).

4. Ensure actions identified in the Action Plan are undertaken within a given timeframe.

5. Assist and advise departments on prospective submissions for Athena status.

6. Highlight Athena initiatives and the Action Plan across the University.

7. Provide an Annual Report to the Equality and Diversity Committee on progress of Athena submissions.

8. Promote, through its focussed approach, the positive working culture and collegiate environment within the University.

One of the primary aims of the group is to support and encourage STEMM departments within the University to progress their Athena SWAN Awards and move on to the next level of award.  

1.2  Athena Network Group

The Athena Network Group is an informal group with representation from all the STEMM departments as well as staff from HR, RSS, LDC and SCS.  More recently, staff from non-STEMM disciplines are requesting that they be permitted to attend the Network meetings to become familiar with the principles of Athena and share best practice.  The group is co-chaired by Alison Rodger (Chemistry/MOAC) and Sandra Beaufoy (HR Adviser – Equality and Diversity). The group continues to meet on a regular basis to up-date departments on current initiatives, progress on Athena work, scrutinise other department’s submissions and to encourage and support departments with their Athena work.  Minutes of meetings of the Network Group are posted on the Athena web page:

http://www2.warwick.ac.uk/services/equalops/athena/network_group/meetings/
News of successes and up and coming events related to Athena Work are also posted on the Athena web pages: http://www2.warwick.ac.uk/services/equalops/athena/.

Members of staff from Warwick have also attended other national meetings where Athena SWAN features as part of the agenda discussions, as well as giving presentations on Warwick’s Athena work. In particular, staff from Warwick Medical School are frequently asked to attend workshops/meetings to present on the challenges they faced whilst putting together their bronze and silver submissions.  In December 2012, Warwick hosted the Athena SWAN Midlands Regional Network Meeting, where the primary purpose of the meeting was to allow institutions the opportunity to share best practice and to discuss challenges faced by institutions.

2. Summary of Warwick Athena Swan Submissions
The Athena SWAN Bronze Institutional Award, achieved in 2010, recognises the University’s good practice with regard to its staff and students within the STEMM disciplines. Work on the institutional Bronze Action plan has been progressed sufficiently that the decision was taken for the University to submit for a Silver Award in April 2013, the outcome of which will be known in September 2013.  Joining Physics and Chemistry as Silver departments, is Warwick Medical School, who have made significant progress since their Bronze Athena SWAN Award gained in April 2012.  Warwick Medical School, along with Queens at Belfast, are the only two medical schools with Silver Athena awards and subsequently now meet the Medical Research Councils condition for future grant funding, which comes into force in 2015.  
The submission process for Athena SWAN Awards changed in 2010, with the introduction of a Bronze level award for departments who are signed up to the principles of Athena but have identified that they have some way to go to reach Silver Award level.  A further change in 2011 meant that submissions could be made in either April or November.  Renewal applications can only be submitted in the November round.  Applications that fail in the April round have the option of re-submitting in November.  An institutional annual charge of £1000 was introduced in April 2012 for HEIs signing up to the Athena Charter.
The table below depicts the ten Warwick STEMM departments’ eligible to apply for Athena Awards and details progress that each of those departments has made.  All awards are renewable after a three year period, but it is hoped that within that time period, each department will have sufficiently moved their action plans forward to be ready to submit for the next level of award.  

University Award: - Bronze Level (2010) – one of the requirements to enable the University to progress to Silver level was to have “a significant number of STEMM departments” either awarded or submitted for Athena awards.  Therefore the Athena Steering and Network Groups have proactively supported individual departments to prepare their submissions, as well as focussing on University wide initiatives.  This drive has resulted in every one of Warwick’s ten STEMM departments either having obtained or have submitted for an Athena award by April 2013 - Table 1 below depicts the position of each of the ten STEMM departments:
Table 1: Status of STEMM departments with or submitted for Athena SWAN awards

	Department
	Coordinator
	Level Awarded
	Proposed Submission Date
	Level of Award to be applied for

	Physics*
	Sue Burrows
	Silver (2010)
	
	Gold (Nov 2013)

	Chemistry
	Alison Rodger
	Silver (2010)
	
	Gold (April 2014)

	WMS
	Annie Young
	Silver (2013)
	
	Gold (2015)

	Psychology
	Mia Khan
	Bronze (2012)
	
	Silver (April 2014)

	Engineering
	Suzanne Evans
	Bronze (2013)
	
	Bronze

	Life Sciences
	Laura Green
	Bronze (2013)
	
	Bronze

	WMG
	Jane Coleman
	Pending
	April 2013
	Bronze

	Comp Science
	Alexandra Cristea
	Pending
	April 2013
	Bronze

	Mathematics
	Nav Patel 
	Pending
	April 2013
	Bronze

	Statistics
	Wilfrid Kendal
	Pending
	April 2013
	Bronze


*The Physics Department was awarded the Institute of Physics JUNO Champion Award in 2009 which automatically qualified the department for an Athena Silver Award – this award was renewed in 2013.  
Representatives from Life Sciences, Engineering, Chemistry and Warwick Medical School all attended the Athena Awards Presentation Ceremony held in Edinburgh in June 2013 and can be seen in the following pictures collecting their awards.

Staff collecting Departmental Athena awards at a presentation ceremony at the Royal Society of Edinburgh on 6th June 2013.  The awards are being presented by Professor Dame Julia Higgins.
[image: image2.jpg]



Dr Julia Smith and Professor Annie Young receiving a Silver Athena Award on behalf of Warwick Medical School


Professor Mike Shipman and Ms Katherine Branch receiving a Silver (renewal) Athena award on behalf of the Chemistry Department.


Professor Laura Green and Ms Rebecca Freeman receiving a Bronze Athena Award on behalf of Life Sciences



Dr Jonathan Pearson and Professor Wanda Lewis receiving a Bronze Athena Award on behalf of the School of Engineering.
3. Good Practice Initiatives Implemented As Part Of Athena SWAN process
Departments with, or who have submitted for, Athena awards have found that working through the process has been an excellent way to analyse critically their current procedures and policy implementation, not to mention the culture of the department.  Overall the process itself leads to better communication and staff engagement, and gives individuals a channel to voice their ideas or concerns.
Through tasks identified in the University Bronze action plan and in conjunction with those STEMM departments who have been involved in the process, a significant number of innovative and good practice initiatives have been identified and put in place.  In order to ensure the initiatives are effective and meeting their objective it is important to identify ways of measuring their impact, and where possible the impact has been reported in Appendix 3 with gives a wide selection of the initiatives that have been put in place, both at institutional and departmental levels. Below is an outline of some of the key initiatives:
· Annual series of Communication and Impact courses for female scientists

· One to one support on career planning

· Creating a variety of networking opportunities, including the Senior Women’s Group and the Returning Parents Network Group

· Equal Pay Audit

· Career Progression and Promotion Events

· School holiday child-care provision

4. What is planned next?
As discussed earlier, the University has submitted for an Institutional Silver Athena award and is awaiting the outcome which will be known in September 2013.  Meanwhile progress on the Athena agenda is continuing with a variety of obvious and innovative activities both locally and nationally as described in Table 2.  Warwick now has a dynamic platform of activity supporting female and male staff that has taken some years to establish.  Extensive publicity across faculties has enabled links with Social Sciences needed to take us into the next stage of development.  Moving forward it is planned to undertake academically credible research at Warwick to determine the underlying causes of female staff leaks both more generally in the UK and internationally.  Preliminary work has been started which we hope will pump prime applications for research funding to investigate the issues faced.
Warwick has also initiated collaborative research with Monash University to share best practice and research issues around the under-representation of females in STEMM departments.  Senior staff visited Monash in February 2013 to discuss possible gender-related research and the two institutions are currently sharing statistical data to identify common trends.  Women in Science initiatives at Monash are being considered for translation to Warwick.
Moving forward the Equality Challenge Unit, who administer the Athena SWAN process, is introducing a Gender Equity Charter mark which will extend the Athena SWAN model to the arts, humanities and social sciences.  Warwick Business School and the History Department have put themselves forward to take part in a trial of the Charter, with a view to submitting a full application for the accreditation early in 2014.  It is hoped that once the Charter is fully launched, other Warwick departments will wish to participate
Sandra Beaufoy

HR Adviser, Equality and Diversity

August 2013
[image: image6.png]THE UNIVERSITY OF

WARWICK




APPENDIX 1: Progress on the ATHENA SWAN Bronze Action Plan 2010 to 2013

This Action Plan is intended to guide the work of the SWAN Self Assessment Group over the period 2010 to 2013
	Key Areas for Assessment
	Actions
	Accountability
	Timescales
	Progress and Actions Taken since Bronze Award

	1. Review how best to promote female representation on University Committees
	(i)  Investigate whether due to the smaller numbers of senior female academic staff, the same individuals are over-burdened with committee duties


	Senior University Management, Deputy Registrar’s Office (DRO), HR
	1-2 years
	· Rotation of committee membership ensures that early/mid-career scientists have the necessary professional development to serve on committees.

· Heavy Committee responsibilities are reflected in Workload Allocation Models (for both men and women).

· Committee membership to be monitored annually to ensure appropriate gender balance whenever possible.

· Strategic University Committee Membership is displayed on the Governance Section of the webpages to ensure transparency of membership.

	2. 
	(ii) Review how Committee roles should be reflected in women’s promotion aspirations. 
	
	
	· Committee membership to be taken into account with other heavy administrative responsibilities for promotion submissions.

· A statement has been included on the Annual Review Form completed by all staff, to record work carried out to promote collegiality/team work.

	3. 
	(iii) Investigate ways of encouraging female academics to put themselves forward for wider University opportunities.
	
	
	Consultation with early and mid-career females to understand and implement mechanisms to encourage them to put themselves forward for wider University tasks – such as mentoring, networking opportunities and flexible working conditions.  Assistance with child care arrangements/costs whilst attending workshops and conferences - See Silver Action Plan §4.a.vii which is continuing to address these issues.

Warwick is also collaborating with Monash University in Australia on sharing best practice (e.g. senior female work shadowing scheme) and intends to undertake research on relevant gender initiatives.  Initial meetings were held to discuss possible projects in Feb 2013 – See Silver Action Plan §6.iii

	4. Female representation on departmental committees
	Review the level of female representation on SET departmental committees e.g. promotion, management, and other committees where this is seen important internally by female members of staff.


	SET Departments, E&D Committee, HR, DRO
	1-2 years
	Depending on the percentage of females in department, key decision-making committees to have both men and women on them wherever possible.  Care is taken not to overload women in achieving this goal by using women external to department where female numbers are small (appropriate care also has to be taken to ensure that committee membership is prudent to the business of the committee and not just to ensure female representation).  Athena work has raised the profile of this requirement significantly within STEMM departments and those who have awards or have submitted for awards have addressed this issue.

The University has established the policy that recruitment panels should have both men and women on them unless there are exceptional circumstances (such as last minute illness of a key panel member and lack of availability of another female of appropriate seniority).  If necessary a female representative will be sought from another academic department.  All panel members must have undertaken an on-line training package on equality aspects of recruitment and selection.  It is the responsibility of the Chair of the Panel to ensure that all members of the recruitment panel have undertaken the appropriate training.  LDC monitor usage of the online module, so can report to the Equality and Diversity Committee on usage.
The initiatives undertaken by the University and the departments are developing a wider pool of female academic talent that can be represented at both University and departmental level, and assists female career development.

	5. Promotion Criteria


	(i) To review the longitudinal data for promotions in SET departments and to determine any generic reasons or underlying development needs regarding why promotion recommendations may not have been successful.


	ASC, HR, Local SET Promotions Committees


	1 year


	· All promotion documentation has been up-dated and communicated via Heads of Department, web site and through Network Groups.

· Heads of Departments have been made aware of the importance of communicating promotion criteria to all staff and to provide the appropriate guidance to staff, through line managers and Departmental Promotion Groups.

· Nomination forms for promotion that academic Heads of Departments complete have been modified by HR.  This will improve the data monitoring of which academic staff in departments requested promotion and then who was subsequently put forward for consideration.  The form also requests information of the support mechanisms that will be used to assist those staff not put forward for promotion.  These forms will be monitored annually.

	
	(ii) To put in place any local development opportunities and /or mentoring to support career development and to ensure that female staff understand how to prepare themselves for promotion at the appropriate time.
	
	
	· Many STEMM departments are hosting their own Promotion events, which have proved very successful and have received good feedback from staff.

· Mentors are available through departments and the Learning and Development Centre.  STEMM Heads of Departments through their departmental Athena submissions have made their staff aware of the importance of communicating promotion criteria to all staff and to provide guidance and support.  Many STEMM departments have hosted their own female promotion events to encourage and support female staff who aspire to further their academic careers. 

	
	(iii) Ensure that the application of promotion criteria to part time staff is understood locally.
	
	
	Promotion information – criteria and process – is sent on an annual basis to departments.  This information is also published on the University website.  Information is reviewed regularly to ensure inclusivity of both part and full time staff. 

	
	(iv) Clearer dissemination of the promotion process. 
	
	
	

	
	(v) Enable a greater local understanding of the promotions process by University and SET departmental expectations.
	
	
	

	6. Credit for collaborative work at all levels
	Ascertain how Academic Staff Committee currently gives credit to academic staff working on collaborative work e.g.

Credit for publications

Credit for research grants

Credit for administration and teaching and to ensure this is understood locally and to revise the processes locally and centrally if necessary.
	Senior University Management, HR, SET Departments
	1-2 years
	The Annual Review form that is completed by all staff has been amended in 2012 to include a statement emphasising any collaborating work undertaken.  This has been agreed by the Trade Union UCU – see statement: ‘You may wish to include an additional summary of various activities that would not normally feature on your CV, e.g. academic visits, grants applied for (even if not awarded – you can access this information from RSS) administrative duties, new collaborations that have not yet resulted in publications, particular examples of successful teamwork, etc. This is your opportunity to inform your head of department (via your reviewer) about all aspects of your work over the past year.’

The University will begin to monitor responses from departments on how staff are responding to this statement, which will feed into the Academic Staff Committee. Further Action on Silver Plan. 

	7. Part time working
	Consider how to balance ‘fixed and variable’ contributions from part time staff – i.e. quantity of output versus accomplishment of a category of task.
	HR, SET departments
	1-2 years
	A statement has been added to promotion documentation sent to departments (and on the web) that makes it clear that staff with special circumstances who wish to submit for promotion have the opportunity to disclose this circumstance  (e.g. part time staff  to mitigate differences in their rate of progression of quantity of publications).  These circumstances can then be taken into account by the Vice Chancellors Promotions Group.

	8. Transparent work load models


	(i) Ensure that the workload model in SET departments is transparent and communicated effectively.
	SET departments


	1 year


	Departments are now required to have a workload model with which the departmental community is happy. Currently this ranges from models that count every academic and academic-related task with different weightings to one developed by individuals in discussion with the head of department. The University has decided that one model does not fit all. As long as staff feel they understand their own contribution and know the mechanisms by which they can query it, the University has devolved responsibility to departments.



	
	(ii) Embed transparency of workload models into departmental practices whilst still acknowledging subject-specific needs.
	
	
	

	
	(iii) Such information to be included in induction packs.
	
	
	

	9. Post-doctoral researchers role at Warwick
	(i) Set up local structures so postdoctoral researchers feel supported and mentored at an exciting but insecure time of their career.
	Senior University Management, HR, LDC, SET departments, Research Staff Forum
	1 year
	The University has established a Postgraduate Certificate in Transferable Skills in Science (PGCTSS) - See Silver Action Plan § 4.a.xiv - for research fellows which provides a structure for their individual non-technical training and development. Work is in progress to integrate the PGCTSS with the RSC Chartered Chemist accreditation. Neither the Forum nor the PGCTSS are specifically targeted at women. However, we note that women disproportionately take up the opportunities they provide and we work to ensure that women are made aware of them and feel the opportunity is targeted at them. The PGCTSS includes a formal mentoring structure. We ensure fellows can benefit from mentoring by a senior female academic should they wish.

	
	(ii) Support departmental initiatives to develop postdoctoral researchers.
	
	
	

	
	(iii) Share best practice between departments.
	
	
	Warwick has a very active Research Staff Forum, with a representative from that group serving on the formal University Research Committee.

	
	(iv) Consider how postdoctoral researchers should be represented on the Science faculty research committee.
	
	
	The University has successfully achieved the HR Excellence in Research Award in Jan 2013 and has a further Action Plan with particular emphasis on the training and development of its research staff.

	10. Mentoring encouraged for all staff


	(i) Formalise local mentoring processes, investigate making training for mentors mandatory and determine an appropriate formal monitoring process.
	SET Departments, HR, LDC


	1 year


	· Mentors are available through departments and also through the Learning and Development Centre.  All females in STEMM departments are offered coaching by LDC and take up is monitored.

· All LDC mentors have received appropriate training and LDC can monitor staff who have been mentored through their programmes.   Departments have lists of selected mentors for new members of staff.

	
	(ii) Review mentoring at various levels within SET departments by: investigating the effectiveness of existing mentoring arrangements for staff on probation through local SET probation committees
	
	
	STEMM departments going for Athena awards are all reviewing their mentoring processes to investigate the effectiveness of their individual programmes.  These will be monitored and reported in individual departmental actions plans.  



	
	(iii) Reviewing the opportunity of supporting mid-career staff with a professorial mentor of their choice.
	
	
	During the period since the Bronze award, particular focus on activities has been directed towards Early Career Researchers and it is only recently that the AS Steering Committee has engaged fully with mid-career staff.  Activities will therefore form part of the Silver Athena submission - See Silver Action Plan § 4.a.viii

	
	(iv) Encouraging Professorial staff to have a co-mentoring relationship.
	
	
	

	11. Warwick Leadership Programme
	To investigate the option of a Women-only Leadership Programme with LDC to look at gender specific challenges in management.
	SET Departments, HR, LDC
	1 year
	The Learning and Development Centre ran two focus groups for female academics and researchers in 2011 on the key issues facing women moving into leadership roles.  There was not a clear consensus on the value of a women only leadership programme as Warwick already has an extremely good programme in place, which the female academics gave feedback that it was entirely adequate for their needs.  To date 13 academic and senior administrative staff from STEMM departments have successfully taken the Warwick Leadership Programme.  The Learning and Development Centre will continue to monitor attendance and success of the programme and will continuously review if there is a need/desire to run a female only leadership course.

	12. Role Models
	Develop strategies to create and bring forward role models in areas where female representation is less by e.g. reviewing departmental seminar programmes.
	SET Departments
	1 year
	SET departments are now ensuring greater numbers of females are asked to give departmental seminars.

More encouragement for female staff to join Networks and to publicise appropriate Networks in induction material and at research forums.

	13. Training and support for women
	Integrate into annual review process a particular emphasis on career development for the next step particularly for women, e.g. Warwick Leadership programme, experiential development.
	LDC, HR, SET Departments
	1 year
	As mentioned above an additional statement has been included in the Annual Review Form for staff to elaborate on collaborative work.  Staff undertaking Annual Reviews have all received Reviewer Training which includes emphasis on career development for staff.

The Learning and Development Centre now run various modules for staff (both male and female):- Envisioning and Enabling Innovation; Communication and Impact; Writing and Presentation Skills.  They also provide funding for Research Active Staff Networks, EPSRC funds for Impact Career Development & Leadership.

All up-take of these sessions are monitored and reviewed on a regular basis by LDC.

	14. Child Care facilities and assistance
	Review how to provide more assistance for working parents with school aged children (4-14 years) during school holiday periods and promote any actions under the University’s work life balance approach.
	Nursery, DRO, HR
	1 year – on-going
	The University is year on year increasing the summer clubs available to children of staff and students.  Summer 2011 accommodated:

Mad Science Club – places for up to 35 children, Tennis and Climbing (9-16 years of age), Tennis, Rookie Lifeguarding and Team Sports (8-12 years of age); Tots and Parents (3-4 years of age), Mini Tennis Red (5-8 years of age).  A similar programme was also held in Summer 2012 with the addition of further activities, e.g.: Bear Rock Cubs Club (aged 8 and over), Junior Tennis Club (10-16 years of age).  The Warwick Arts Centre has also established Youth Theatre Groups which run on a Saturday morning and Monday evenings.  The Groups are divided into the following age groups: 8-11 years; 11-15 years; 14-16 years and 16-18 years.

In 2013 it is anticipated to pilot a Summer Scheme for school aged children (4 – 14 years of age) which will be held every day, all day, for working parents.  If successful this scheme will be rolled out to cover half term holidays which are particularly problematic for working parents and for students as the half term breaks usually fall within the University term time - See Silver Action Plan § 4.a.xiv

	15. Outreach work
	Develop SET Department Open Days which particularly target female candidates
	All SET Departments
	1 year – on-going
	All STEMM Departments have representation at the AS Network Group and have actively shared best practice and ideas for outreach work.  Individual departments have listed their current outreach activities within their own submissions, but brief examples are given here:

Physics and Chemistry both have dedicated Outreach Officers who are extremely proactive in visiting local schools (primary, secondary and sixth form)  to give talks and demonstrations and have also engaged in national projects such as the Big Bang Fair.  They also both organise a series of public lectures.  Physics are involved in a scheme called ‘Physicist of the Year’ where local schools are asked to nominate the best students (year 11 or 12) for work undertaken on a Science project.  In June 2012 the outreach officer (female) took 19 year 9 girls to CERN in Geneva where they met scientists and were shown around the facility; the girls were chosen from nine different schools of different socio and economic groups within Coventry.  The aim of the project was to encourage young girls to consider studying physics and engineering at a higher level.

Engineering run an annual Headstart course, aimed at 16 and 17 year olds who are taking STEMM subjects.  In 2012 Engineering also ran a Dragonfly day as a pilot.  Dragonfly is an initiative providing the opportunity for girls on the Headstart course to become mentors to younger female students.  They are also planning to participate in the Arkwright Scholarship initiative.

In 2013 Maths are enhancing  the support provided to Warwick applicants with STEP/AEA through web/on-line lecture delivery; 2 professional development days for teachers with STEP/AEA; Saturday Royal Institution Master classses; problem-solving day/s for potential applicants (age-group 16-17) (most likely 2 including one for females only) and an additional Maths and Beyond Day.

Some departments either already or are considering as part of the Athena submissions to run female only open days.

	16. External and internal publicity
	Ensure that both women and men continue to feature in any external and internal SET publicity activities to ensure representative balance.
	University Publicity Office, SET Departments
	1 year but on-going
	Warwick has a professional publicity office that advises staff on all aspects of publicity.  This facility is available to ALL staff regardless of gender.  Warwick has also developed a national “Communication and Impact for Female Early Career Researchers” course - See Silver Action Plan § 4.a.i
All publicity material does reflect the diversity of the campus environment and images contain people with and without protected characteristics.

	17. Celebrate successes in teaching excellence
	Ensure all results and successes are in departmental newsletters and web pages.
	All SET Departments
	1 year – on-going
	The Warwick Awards for Teaching Excellence (WATE) give students and colleagues the opportunity to recognise and celebrate excellence in teaching and the support of learning throughout the nominee’s career at the University.  There have been 14 winners from STEMM departments of which 3 of these have been female.  Communication of the awards is placed on the University website InSite and in the University Newsletter, Communicate.  Individual Departments also publicise the winners within their own departments.

STEMM departments that have made submissions for Athena awards have all addressed the issue of celebrating successes. They communicate successes both within their departments and in the wider University Community.

	18. Options for variable work patterns
	Review the local application of opportunities for variable work patterns in SET Departments and what may be alternative options e.g. short term part time work for postdoctoral researchers and permanent staff.
	SET Departments, HR
	1 year
	It has been identified that all STEMM departments have ad-hoc arrangements for flexible working that meets the needs of the department and the staff member.  

Timings of meetings have been addressed as far as possible to be in core hours, so that staff with parental responsibilities are able to attend.

Some departments employ post docs coming to the end of their contracts on further short term contracts to cover additional teaching or maternity leave.  

Postdoctoral staff whose fixed term contracts have ended, are sometimes appointed on an Associate Fellow basis, which whilst not being paid, still gives them access to University facilities, such as the library and IT, which helps them to continue to pursue their research career.

	19. University Staff Survey – PULSE
	Consider the results of the 2010 Annual Survey and update action plan accordingly in conjunction with local SET Departmental PULSE Action Plans.
	SET Departments, SAG, HR
	1 year – on-going
	66% of staff in the Faculty of Science and 66% of staff in the Faculty of Medicine gave a positive score to the questions within the Work-Life Balance and Working Conditions theme of the 2010 PULSE survey.

65% of staff in the Faculty of Science and 60% of staff in the Faculty of Medicine gave a positive score to the questions within the Equal Opportunities and Diversity theme of the 2010 PULSE survey.

There was no survey in 2011 and the 2012/13 survey closed on 20th February 2013, the results of which will not be known in time for the Silver submission.  However the results of each survey will continue to be monitored and any issues of concern will be addressed appropriately.

	20. Developing more media spokes-people
	Advertise LDC and PGCTSS Science Communication courses across SET departments. Offer departmental courses in science communication, Involve the Communications Office in this.
	LDC and MOAC Doctoral Training Centre
	1 year
	Since the Bronze submission, LDC has worked tirelessly with STEMM departments to ascertain appropriate courses for academic and research staff.  There has been a vast improvement in the quality and number of courses now available to staff, which include communication, assertiveness, written and spoken skills etc.  MOAC have run two very successful science communication courses to Postdoctoral staff – approximately 25 PDRAs attended each course.  Feedback from attendees was very good.

As mentioned early in this Action Plan and within the Silver Submission, the first of an annual series of Communication and Impact courses for female scientists has been held.  Feedback from the course has been excellent, and the course will continue and uptake monitored - See Silver Action Plan § 4.a.i

	21. Information availability
	Ensure information is locally available and understood about e.g. maternity cover for people on various short-term contracts.
	RSS, HR
	6 months
	During AS Network meetings, emphasis has been given to STEMM departments to ensure that their web pages are up to date and have the appropriate links to policies and processes.  STEMM Departments have or are currently improving induction documentation given to new staff, regardless of their contract type.

	22. Health and Safety
	Ensure appropriate H&S information is readily available to all staff e.g. to ensure that information for pregnant women in SET departments reflects the impact of SET roles. To make available an on-line induction package to complement other central and induction activities.
	Health & Safety Office, HR, Departments
	1 year
	The Health and Safety Office has undergone a restructure during 2012 and therefore some of this action has not yet been completed (on-line H&S induction package).  However, the H&S web site is undergoing a review and data is being updated.  A project on access to buildings and facilities is also on-going and involves Departmental Disability Contacts working closely with the H&S Office.

The staff maternity policy has been reviewed and a student maternity policy is in the final stages of review and will be uploaded to the website shortly.

STEMM departments are ensuring that appropriate H&S documentation is provided to new and existing staff as operational needs or legislation changes.

	23. Bullying and Harassment
	To refresh and reinforce the information and advice on the process of reporting and dealing with B&H incidents and to publicise the Dignity at Work contacts for SET departments.
	All staff, HR
	6 months – on-going
	Dignity at Work and Study Policy regularly reviewed/updated (due to be reviewed again in Autumn 2013).  Bullying and Harassment questions in Staff Survey to try to identify any “hotspot” areas, to be dealt with accordingly.

Equality and Diversity web pages updated regularly to ensure legislation is current. Equality and Diversity Training Schedules organised for every term and attendance recorded and monitored.

Usage of e-learning modules on ‘Diversity in the Workplace’ and ‘Recruitment and Selection’ monitored by LDC.

Staff encouraged to take modules as part of their induction process.

Awareness days organised and publicised.

2 new Dignity contacts were recruited in 2012 (1 female and 1 male).  Both have been trained.

In conjunction with HR, some departments have held training sessions, using realistic scenarios on Bullying and Harassment and during those sessions the role of a Dignity Contact has been explained.

	24. Promotion Information
	Publicise and communicate the promotion criteria and how to be put forward for promotion in each SET department to assist career development and planning.
	SET Depts, HR
	1 year
	Covered in Action Plan Number 3 above.

	25. Collection of SET data
	Request the University to review whether data on staff and students can be monitored and available from a central source. To improve data collection
	HR, Academic Office
	1 year
	Considerable progress has been made on this action.  STEMM departments now have central sources to contact (HR for Staff data and the Management, Information and Planning Office for student data).  Both offices have tailored reports to match Athena submission requests for data, so once a department requires their data to analyse trends, this is made available to them.  Further work is currently being discussed to enable departments to be able to run further reports themselves, but this is still at an early stage but it is anticipated that work may be completed within an 18 month period - See Silver Action Plan § 5.b.i

	26. Balance of ‘fixed and variable’ contributions between part-time and full-time staff
	Request that data on fixed-term versus open-ended contracts by department be monitored and available from a central source in a format to meet the needs of SET departments. To improve data collection.
	HR, Academic Office
	1 year
	The systems team in HR has improved the presentation of this data, which is available upon request from departments.  Individual STEMM departments have responsibility to monitor and detect any trends from this data, which can then inform their Athena submission.

	27. Flexible Working
	To review the feasibility of the University recording statistics on up-take of flexible working with cooperation from departments who agree to flexible working requests.

To ensure information is readily available on a range of flexible working opportunities.
	HR, Departments
	1-3 years
	All staff should be able to find the official policy and also the departmental practice that implements it for issues such as: flexible working; returning parents; maternity and paternity and adoption leave.

It has been identified that many ad-hoc flexible working arrangements exist in departments but are not formally recorded (done by local arrangement with line manager).  In an attempt to capture data, HR have developed a form for department to use to start to record these ad-hoc arrangements so that the University can begin to monitor flexible working.

	28. Audit policies
	To support an equal pay audit as and when the University has determined its obligations under the Single Equality Act
	Senior Management, HR
	1-3 years
	All University policies and reviewed and updated on an annual basis by the HR Policy Team and the Governance Team.

An Equal Pay Review was completed in 2011 and the results published on the E&D web pages.  Separate reviews were taken for staff in grades 1a-8 and in Grade 9.

The University is under statutory obligation to undertaken an Equal Pay Review and to publish the results of that Review.  The Review is undertaken in compliance with statutory obligation and in accordance with JNCHES Guidance on Equal Pay Reviews of 2007.  

The Review has been reported to the Equality and Diversity Committee and the Joint Consultative Committee and discussed with Trade Union representatives prior to submission for publication.  The Review was undertaken by grade in line with Hay job evaluation methods.

The University Senate approved a recommendation to a light touch review on an annual basis for Levels 1a-8, with a detailed review through a formal route every 2 years.  For level 9 (professorial/senior management), where a disparity on gender data was identified, a review will be carried out on an annual basis with the ownership resting with the Vice Chancellor’s Advisory Group.



	29. Support departments in preparing Athena submissions
	Provide advice and support to departments for their individual submissions.

Expand the knowledge of the work of the Athena SWAN group and disseminate information more widely.
	SWAN Self-Assessment Group
	1-3 years
	An Athena SWAN Project Officer was appointed in March 2012 to work with the HR Adviser for E&D, the Athena Steering Group and Athena Network Group to advise and guide STEMM departments in preparing their Athena submissions.  

A ‘quick start’ framework was devised to assist departments to start work on their Athena Submissions.

The AS Network Group continues to meeting on a monthly basis and has representation from staff from all STEMM departments.  This network shares best practice, discusses the challenges of working through Athena submissions and assists with proof reading submissions and action plans.

Out of nine STEMM departments, 4 currently have awards, 5 submitted in November 2012 (awaiting outcome) and the remaining 3 departments are due to submit in April 2013.

Warwick Medical School was the first medical school to achieve an Athena Bronze award – they have subsequently submitted for Silver in November 2012 round.  In June 2012, Warwick Medical School and HR hosted an Athena SWAN workshop which was designed to share best practice and the challenges faced when completing their Bronze submission.  It was attended by 22 institutions and received some very positive feedback.

Warwick staff have attended and presented at various Athena events.  Warwick is a member and also hosted a meeting of the Athena Regional Network Group.

Window on Warwick presentations on the Athena SWAN process have taken place in 2012 to engage with staff from non-STEMM departments to share best practice. 


Appendix 2: Action Plan

Athena SWAN Silver Award Application: University of Warwick
Actions are grouped in career stage order.  
Warwick now has a diverse portfolio of activity.  Part of the Action Plan is to ensure that this is dynamic, growing, responsive and increasingly grass roots driven.  The Action Plan therefore has quite a lot of monitor/ensure continuity/effectiveness, etc.
	Key Issue
	Ultimate Goal
	Actions
	Action plan code and Reference to relevant section in application
	Measurable Outcome
	Accountability
	Timescales
	Estimate of Effort Required
	Progress Log

	UNDERGRADUATE STUDENTS

	1. Under-representation of women

AS Principles 1,2,4
	Increase in undergraduate female population in physical and mathematical sciences
	(i) Outreach events aimed at female students embedded into departmental activities. 


	§ 3.b.i
	Increase in applications and enrolments from women for Physical and Mathematical STEMM undergraduate courses. 

To continue the trend of increasing female u/g numbers as shown in Table 3.4(i)
	HoD, Admissions Teams in STEMM departments 
	2013–2016 
	High
	

	
	
	(ii) Women given a high profile on all STEMM publicity material and websites.
	
	
	
	
	
	

	POSTGRADUATES STUDENTS and POSTDOCTORAL RESEARCHERS (where actions are common to both categories)

	2. Retention of women in Academia following postgraduate study and postdoctoral research

AS Principles 2,4,5,6
	Recruitment and retention of female staff in STEMM
	To change attitudes on viability of academic careers for women by further increased use of Postgraduate Certificate in Transferable Skills in Science (PGCTSS) to provide quantitative positive support for female students and researchers.
	§ 4.a.xv – see Table 4.1


	Monitor use of PGCTSS and feedback to provide qualitative data to show whether women have positive views of academic careers.

Review feedback from PGCTSS with the view to discovering whether further tailored courses are required.

	Academic Lead (AR)


	2013–2016


	Hih
	 



	
	
	Support departmental initiatives for students and events such as WIS (currently led by Chemistry and Life Sciences)
	
	Success of initiatives and events

	
	
	
	

	Key Issue
	Ultimate Goal
	Actions
	Action plan code and Reference to relevant section in application
	Measurable Outcome
	Accountability
	Timescales
	Estimate of Effort Required
	Progress Log

	POSTDOCTORAL RESEARCHERS
	 
	 
	 
	 
	 
	 

	3. Lack of understanding on how to pursue an academic career

AS Principles 5,6

	(i) Embed Development Tool for all  PDRA’s to improve their prospect of pursuing an academic career
	Encourage PDRAs to take the accredited Postgraduate Certificate in Transferable Skills in Science for PDRAs.  Encourage PDRAs to use LDC resources.  Invite PDRAs to new annual “Demystifying Promotion Process”.  Have breakout groups for PDRAs.


	§ 4.a.xv – see Table 4.1
	Review Exit interview information to determine how many PDRAs leave to take up a career in academia and to what extent the PGCTSS and other initiatives have supported them. Discovering whether further tailored courses are required.

Monitor numbers of women registering for courses and to monitor feedback.
	Academic Lead (AR)
	On-going
	High
	

	
	(ii) To enable PDRAs to track their learning & development
	Introduction of an online space designed to support PDRAs. The Portfolio offers both a portal to a wide range of opportunities and resources, as well as a personal portfolio enabling researchers to build a record of their training, experiences and achievements throughout their research degree.
	§ 4.a.xiv – see Table 4.1
	PDRAs feel supported and enhance their career prospects as measured by response to online questionnaire. 
	LDC
	2013–2016
	Medium
	

	
	(iii) Support initiatives such as the ‘Irene Joliot-Curie Conference’ for female chemists waiting to move into independent academic careers
	Ensure Irene Joliot-Curie conference takes place annually.
	§ 4.a.x – see Table 4.1
	The continuation of the conference series
	Royal Society of Chemistry

Warwick and Imperial Chemistry Depts
	
	
	

	Key Issue
	Ultimate Goal


	Actions


	Action plan code and Reference to relevant section in application
	Measurable Outcome
	Accountability
	Timescales
	Estimate 
of Effort
 Required


	Progress Log

	4. Retention of female PDRA after maternity/ adoption leave

AS Principles 2,4,5,6
	Support of female PDRAs before, during & following maternity/ adoption leave
	(i) To ensure that the University continues to liaise with the RPNG to ensure that support is being utilised and fit for purpose.
	§ 4.a.vi – see Table 4.1
	Monitor the retention of women returning from maternity/adoption leave.
	HR, RPNG
	On-going
	High
	

	
	
	(ii) Collect & review data of career progression of female academic and research staff returning from maternity leave.


	
	Ensure breaks for maternity leave are taken into consideration at shortlisting & interview stage.
	
	
	
	

	
	
	(iii) Offer such PDRAs visiting fellowships at end of contract 
	
	Measure uptake of this offer
	
	
	
	

	5. Improve PDRA experience

AS Principles 5,6
	Provision of a Postdoctoral Newcomers Meeting to improve beginning of PDRA experience
	Linked with the RSF, a post-doctoral newcomers meeting will to continue to meet on a regular basis, so that new PDRAs have an opportunity to meet with key people from across the University, so they can understand readily what support is available to them in their role.
	§ 4.a.xii – see Table 4.1
	Informed PDRAs who feel welcomed and supported in their role. Email survey to ask new comers at 6 month time point if they feel they have a support network
	Research Committee, RSF, SIGs
	2013–2016
	High
	

	6. Communication and Impact

AS Principles 1,2,4,5
	Provision of relevant & useful training and development courses. Raise confidence of ECRs & provision of networking opportunities

	(i) To continue with the annual series of Communication & Impact courses for female scientists. (Nationally & 1-2 courses at Warwick)
	§ 4.a.i - see Table 4.1
	Review feedback from courses with the view to discovering whether further tailored courses are required. 
	Academic Lead (AR) / LDC
	
	
	

	Key Issue
	Ultimate Goal
	Actions
	Action plan code and Reference to relevant section in application
	Measurable Outcome
	Accountability
	Timescales
	Estimate of effort required
	Progress Log

	EARLY CAREER RESEARCHERS

	7. Mentoring and Coaching

AS Principles 1,2,4,5

	Improve uptake of mentoring & coaching support to facilitate career progression of females in STEMM. Create a culture where it is “expected” that ECRs both mentor and are mentored.
	(i) Support STEMM women to:

· Follow up on requests for mentoring

· Raise confidence levels

· To prepare for promotion

· Provision of one-to-one mentoring

· Development of job portfolios

· Access to procedural information
	§ 4.a.ii - see Table 4.1


	Increase of staff engaged in mentoring and coaching.

Increase numbers of females putting themselves forward for promotion.
	LDC / STEMM Heads of Depts.
	2013–2016
	Medium
	 

	
	
	(ii) Develop experience of Early Career Researchers on financial decision making (2 ECR’s are on the decision panel judging applications for conference child care support fund – see§ 4.a.vii).
	§ 4.a.vii – see Table 4.1
	Female staff feel engaged and confident in their careers.
	
	
	
	

	8. Creating Networking Opportunities

AS Principles 5,6

	(i) Biannual Women in Science Symposium


	To ensure a ‘grass-roots’ committee is appointed each year to organize these Symposia and to monitor attendance and ensure discussions are engaging with the student/post-doctoral research community.

Provide admin, finance and academic support as required.
	§ 4.a.iii - see Table 4.1

	High attendance at event.

Prominent publicity and web presence for events. 
	Student/Post-doctoral community

E&D Adviser to monitor & flag need for action to AS Steering if required.
	2013–2016

	Medium

	

	
	(ii) Support post-doc forums in departments
	 To continue to help with funding for departmental events. Ensure local person in departments sets dates.

	
	Informed and engaged local communities.
	LDC/RSS
	
	
	

	
	(iii) Termly Welcome Lunches for PDRAs
	Ensure funding is available
	
	Prominence of role models. Attendance. Informed and engaged community. 
	RSF/RSS
	
	
	

	Key Issue
	Ultimate Goal
	Actions
	Action plan code and Reference to relevant section in application
	Measurable Outcome
	Accountability
	Timescales
	Estimate of Effort Required
	Progress Log

	MID-CAREER ACADEMICS & RESEARCHERS

	9. Annual events to raise profiles of female staff in STEMM

AS Principles 1,2,4
	
	(i) To celebrate annually an event to recognise International Women’s Day that engages with female staff and provides role models.


	§ 4.a.iv - see Table 4.1
	Informed female staff who are committed and engaged with the wider university community.
	HR, Academic Community, Registrar’s Office


	2013–2016
	Medium
	

	
	
	(ii) Organise high profile celebration of AS and women’s successes in the University.
	
	Prominence of Role Models
	
	
	
	

	
	
	(iii) Nominate outstanding women for honorary degrees.
	
	An increase in women receiving honorary degrees & a prominence of role models. 
	
	
	
	

	10. Enhancing opportunities for mid-career females

AS Principles 1,2,4
	Recruitment, retention and progression of mid-career females
	Launch of Women’s Network Group with termly meetings for mid-career staff to discuss relevant initiatives with a view to improve work life balance and promotion prospects.

Next meeting is scheduled for 21 May 2013
Promotion and appointment requirements take account of leave.

	§ 4.a.v - see Table 4.1
	Appropriate forum to consult on issues raised by the group and outcomes to be measured. New initiatives proposed.

Ensure breaks for maternity leave are taken into consideration at the shortlisting and interview stages for jobs/promotion. 
	Chair of the Faculty of Science
	2014 
	High
	 

	 11. Monitor the gradual drop of women in STEMM against age profile
	Progression and retention of female academics
	Carry out further investigations on how to support women in mid-career as the net drop is gradual at each career stage and could be mainly due to the age profile of women in STEMM academia. 

	§ 3.b.ii
	Steady progression of female academics
	HR Data Systems
	2013-2016
	Medium
	

	Key Issue
	Ultimate Goal
	Actions
	Action plan code and Reference to relevant section in application
	Measurable Outcome
	Accountability
	Timescales
	Estimate of Effort Required
	Progress Log

	12. Conference attendance is essential for academics but can be difficult if staff have childcare responsibilities

AS Principles 1,2,6
	More parents  attending conferences (which are essential to their academic & research careers) 


	(i) An annual fund has been established to assist with payments for extra childcare costs incurred when individuals attending conferences/workshops (£100 per claim).
(ii) From 2013 the fund is part of the Science & Medicine Faculty budgets.
 
	§ 4.a.vii – see Table 4.1

	Childcare not an issue for conference attendance, measured by actual take up of available funds.

Roll out to other Faculties.
	Chair: Science & Medicine Faculties / AS Network

Chairs of Faculties
	2013–2016
	Medium

	

	13. Occasional Childcare

AS Principles 1,2,6

	Occasional childcare available to parents wishing to attend workshops/ conferences linked with their work

	Monitor effectiveness of new initiative: Nursery now takes a child on a one-off basis if a parent needs cover to attend a conference and the child does not usually use the facilities.
	§ 4.a.viii – see Table 4.1
	Childcare not an issue for local conference attendance, measured by actual take up of places on a one-off basis.
	University Nursery, AS Network
	On-going
	Medium
	

	14. Turning research outputs into a commercial proposition 

AS Principles 1,2,4

	More female participation in developing commercial impact of research
	Warwick has been awarded £2.2 million from The Impact Acceleration Account awarded by EPSRC.  The money will go towards a number of initiatives to boost the University’s impact on the wider economy. Ensure women feel it is appropriate to apply. 

	§ 6.ii
	Participation by gender will be monitored and any female case studies publicised to encourage other female scientists to engage with this initiative.
	RSS
	
	Medium
	

	Key Issue
	Ultimate Goal
	Actions
	Action plan code and Reference to relevant section in application
	Measurable Outcome
	Accountability
	Timescales
	Estimate of Effort Required
	Progress Log

	15. Clarity on Promotion & Career Progression

AS Principles 1,2,4

	 All staff clear about what is required in the next step in their careers and how to achieve it.
	(i) Gain information through focus groups about ignorance on this issue. Ensure all new staff, but especially associate professors, feel they know how to progress to the next steps through Warwick’s promotion process. To find out what support is offered/taken-up in departments, what barriers they face, how these can be overcome or lessened.
	
	Action to be developed if particular blocks to women’s progression are identified.

Retention and promotion of female Associate Professors.
	HR, LDC
	Annually
	High
	 

	
	
	(ii) Ensure recently updated information on web remains useful.  
	
	Investigate the pattern of promotion applications and success rates of women in STEMM. 
	E&D Adviser, AS Network
	
	
	

	
	
	(iii) Annual Event ‘Demystifying the Promotion Process’ established to provide academic led information about what is needed for promotion at each career stage.
	§ 4.a.xiii – see Table 4.1


	First event held in April with 40 attendees and 10 speakers. Based on feedback this will be at least annual.
	HR, Academic Staff Committee, VC’s advisory group 
	
	
	

	
	
	(iv) A Women’s Leadership Programme to be established if there is demand. 

           Further consultation to be undertaken by LDC to see if there is demand for a Women’s Leadership programme.  Determine best format balance between meeting, mentoring, shadowing (following Monash initiative that is very successful)

	§ 4.a.v – see Table 4.1
	Demand and success of a Women’s Leadership Programme

Run one such course annually.
	LDC
	
	
	

	Key Issue
	Ultimate Goal
	Actions
	Action plan code and Reference to relevant section in application
	Measurable Outcome
	Accountability
	Timescales
	Estimate of Effort Required
	Progress log

	ALL STAFF
	
	
	
	
	
	
	
	

	16. Managing maternity leave

AS Principles 1,2,4
	To ensure employees feel welcomed back into the workplace at a time when their levels of confidence may be low
	Endeavour to arrange for a member of the RPNG to accompany new returning parents to their first meeting.

Ensure RPNG keeps running and its format is dynamic.

Ensure all departments are using the 

two maternity checklists which have been produced:

a. For staff about to go on maternity leave so they are clear of any issues they need to be aware of.
	§ 4.a.vi – see Table 4.1
	Monitoring usage and feedback from RPNG. Retention of women returning from maternity/ adoption leave.


	HR, Departments 
	On-going
	Medium
	 

	
	
	b. To be issued to the line manager approximately 1 month before the employee returns from maternity/adoption leave to ensure department is ready for the employee’s return.
	
	
	
	
	
	

	17. Car parking spaces for parents working at the Medical School & Life Science campus to enable them to visit children at the Nursery
AS Principles 1,2,4
	Parking reserved for parents visiting babies
	Review the one year pilot project (started March 2013) to allow for dedicated parking spaces at WMS/Life Sciences campus for parents (in particular nursing mothers) of children in the University nursery as parking is extremely limited at WMS/Life Sciences campus.
	§ 4.a.ix – see Table 4.1
	Monitor usage, collate feedback from parents (working mothers feeling supported whilst continuing to breastfeed their children). 

Consider the possibility of rolling it out to main campus.
	WMS, Security Services
	2013–2016
	High
	

	Key Issue
	Ultimate Goal
	Actions
	Action plan code and Reference to relevant section in application
	Measurable Outcome
	Accountability
	Timescales
	Estimate of Effort Required
	Progress Log

	18. Lack of general understanding of flexible working options

AS Principles 1,2,4,6

	
	The Flexible Working Policy was updated in May 2012 to give greater clarity to the fact that parents of children under 17 or disabled children under 18 or carers have a legal right to apply for flexible working and gives clear guidance and links to the government website.
	§ 4.a.xi – See Table 4.1
	Ensure information is in all induction packs and existing staff are told via insite as well as E&D pages. Monitor any increase in the request for flexible working hours.
	HR, All Departments
	On-going
	Medium
	

	19. Parents of School-age children looking for support during the school holidays

AS Principles 1,2,4,6

	School holiday child-care provision
	A project team has been established to investigate potential options for school holiday childcare provision at the University. Consultation is already underway with stakeholders. Plans for a pilot Holiday Scheme to take place in July-August 2013.
	§ 4.a.xvi– see Table 4.1
	Provision of good quality/inexpensive childcare during school holidays.

Measure take up and feedback on the pilot scheme will be monitored.

Dependent on feedback further Holiday childcare programmes taking place may be developed over all school holidays.
	Registrar’s Office
	2013–2016
	High
	

	20. Recruitment

To attract more females to apply for research and academic positions

AS Principles 1,2,3,4,6

	More applications from and appointments of females
	Exploration of possible changes to recruitment advertising in order to attract more applications to academic positions from females. Adverts to include statements such as job share, part-time considered to encourage females with caring responsibilities to continue their academic careers.  

	§ 4.a.xvii – see Table 4.1
	More applications from females for research and academic positions.  Achievement of a more gender balanced academic workforce.
	Deputy Director of HR

Academic Department Administrators
	2013-2014
	Medium
	

	Key Issue
	Ultimate Goal
	Actions
	Action plan code and Reference to relevant section in application
	Measurable Outcome
	Accountability
	Timescales
	Estimate of Effort Required
	Progress Log

	AS ISSUES

	21. “AS Issues” kept live at Warwick
	Evolving programme of activity
	AS Steering group to monitor whether departmental and University activities are evolving at grass roots level.
	Action Plan
	All initiatives are reviewed after two years: completed ones are retired, it is noted how many new ones are established, and initiatives which are not yet fulfilled are critically evaluated.


	Athena Steering and Network Groups


	
	
	

	DATA

	22. Improved data collection 

AS Principle 1

	Departments able to access their own data easily and the ability to create appropriate tables and graphs for Athena SWAN and other submissions
	Since 2009 we now collect required data.  Next step is to make it easily available.

To design, implement and pilot a ‘Dashboard’ for university staff and student data, which will enable individual departments to create and produce bespoke departmental reports.
	§ 5.b.i
	Institutional and departmental data readily available in required formats to which individual departments will have access.
	HR Systems team, Strategic Planning & Analytics Office, All STEMM Departments
	2013–2016
	High
	 

	GOVERNANCE

	23. Analysis and monitoring of policy & procedures

AS Principle 3
	To ensure that PULSE staff survey is fit for purpose and informing the University of issues to be tackled & those things that it is doing well.
	PULSE and the AS process have highlighted a number of issues, some resulting in the development or enhancement of university-wide initiatives included those listed in Table 4.1.

Results of the 2013 PULSE survey will be analysed and any relevant AS issues identified & included on the next AP within Warwick’s next institutional submission.
	§ 6.i 
	Retention of staff, who are committed and engaged with the wider university community.

To ensure issues identified through the analysis of the survey results are addressed and dealt with accordingly and added as an action to this plan.

	HR
	2013–2016
	High
	

	Key Issue
	Ultimate Goal
	Actions
	Action plan code and Reference to relevant section in application
	Measurable Outcome
	Accountability
	Timescales
	Estimate of Effort Required
	Progress Log

	24. Fellowship Programmes for ECR’s

AS Principles 1,2,4,6
	Explore opportunities for research and scholarship to support and nurture early career researchers
	Explore opportunities for research and scholarship to support and nurture ECR’s. To closely monitor all activities including gender balance of applications to and awards made through IAS programmes and works to ensure consistency with AS Principles.
	§ 6.iii
	Increased number of fellowships programmes and development of ECR’s
	Institute of Advanced Study Director and team
	2013-2016
	Medium
	

	25. Joint Research Project on Gender issues 
AS Principles 1,2,3,4
	To benchmark and share best practice 
	To collaborate with staff at Monash University on gender related projects identified after sharing staff and student data.  Addressing ”universal” trends within that data, by comparing and sharing best practice in policies and processes.
	§ 6.iv
	To share best practice and initiatives internationally to encourage recruitment and retention of females in STEMM subjects.
	HR Advisor (E&D)
	2013–2016
	Medium
	

	26. The Leaky Pipeline

AS Principles 1,2,4
	To properly understand data in AS submissions
	EPSRC and ESRC have been consulted about establishing a research project to identify what is underlying the fairly obvious leaky pipeline data sets in STEMM and academia in general.

A one-day international cross-discipline workshop to be run over summer 2013 to determine the next stage.
	
	Publications to inform and address the underlying reasons of under-representation of females in STEMM disciplines.
	ESRC/Warwick academics/HR plus Post-doctoral researcher employed on projects
	2013–2016
	High
	

	27. REF2014 Submission

AS Principles 1,2,3,4
	To monitor gender balance of staff submitted for the REF
	To carry out an Equality Analysis on the University REF2014 submission, in line with Warwick’s REF Code of Practice and the Equality Impact Assessment.


	§ 6.v
	Results of analysis indicate that a fair process has been undertaken and any disparities further investigated
	HR, Strategic Planning & Analytics Office
	2013-2014
	High
	

	LEADERSHIP

	Key Issue
	Ultimate Goal
	Actions
	Action plan code and Reference to relevant section in application
	Measurable Outcome
	Accountability
	Timescales
	Estimate of Effort Required
	Progress Log

	28. National Impact of Warwick’s Athena SWAN activity

AS Principles 1,2,3,4,5,6
	To be seen as a national and international leader in supporting staff, particularly women in academia
	Keep track of external AS activities generated by Warwick staff and monitor the subsequent impact 
	All actions identified within submission and individual STEMM dept. submissions
	Reports in places beyond Warwick’s control, e.g. recent report in Medical and Dental Schools Athena SWAN Newsletter
	AS-N
	2013-2016
	Low
	

	
	
	Continuing programme of innovative actions led by Warwick on the national scene
	All actions identified within submission and individual STEMM dept submissions
	Warwick’s initiatives developed into sustainable activities, e.g. Irène Joliot-Curie conference is in process of being handed to the Royal Society of Chemistry to run
	AS-N
	2013-2016
	High
	


APPENDIX 3: A selection of University or National initiatives resulting from the Athena SWAN process at Warwick grouped into Actions designed (i) exclusively for women, (ii) for women but open to men, and (iii) for both men and women but with issues of more significance to women than men included. 
	Motivation
	Initiative
	Description
	Impact

	(i) Actions designed exclusively for women 
	

	Lack of self-confidence of early career researchers and less effective networking of women


	First of an annual series of Communication and Impact courses for female scientists


	Recognising that this is not merely a Warwick issue but a wider problem, we chose to develop a national “Communication and Impact for Female Early Career Researchers” course. The first of which was held in January 2013 with external course leaders. The second is scheduled for January 2014. The focus was on personal impact and indirectly on Networking by gathering early career researchers from across all STEMM disciplines. http://www2.warwick.ac.uk/fac/sci/wcas/events/communicationandimpact/

	2013: 16 Institutions attended 1st course with 30 female attendees.

Typical feedback: “Thank you for a wonderful opportunity. I really enjoyed the course; I also valued meeting other female scientists from other subject areas and learning some highly beneficial new skills.”

	Mentoring and Coaching
	One to one support on career planning
	Improved communication on the availability of mentoring and coaching support through the Athena Departmental and Network groups has led to a significant uptake in 2012 of women requesting this type of support. 

LDC has also provided coaching support as well as 1-1 sessions with research active staff (approx. 15 staff).

All Assistant Professors as part of their probation terms undertake PCAPP which also provides mentor support.
	Year
	F
	M

	
	
	
	2009
	5
	-

	
	
	
	2010
	6
	5

	
	
	
	2011
	4
	6

	
	
	
	2012
	18
	6

	
	
	
	Total
	33
	17

	Lack of women-women networking opportunities
	Creating networking opportunities


	Monthly female academic and academic-related staff lunches held in STEMM departments.

	Departments monitor attendance

	
	
	Women in Science (WIS) Symposium: 2-day biannual symposium focusing on stories of success, leadership skills, CV development and networking.  Previous WIS Symposiums were held in September 2010 & 2011 respectively. The next one is planned for September 2013 with a satellite meeting (see below) in March 2013. The symposiums are organised by the student/postdoctoral research community. 

	30 delegates in 2010 and 20 delegates in 2011 – the symposium is now biannual


	
	
	(WIS) Event entitled WIS – An Evening with…. Science Career Success Stories – took place on 27 March 2013. LDC funded this event and promoted it via montly e-newsletter. Speakers included two of the 2012 UNESCO-L’Oreal Fellowship winners. Dr Vita Majce, an early career fellowship winner gave a presentation on starting a career in academic research and Professor Frances Ashcroft, University of Oxford, on her career in science whilst maintaining a work life balance. This event was open to all Warwick Science Departments.

	88 people registered for the event, but only 70 people turned up (~90% female, 10% male).  

Positive feedback was received.  Many commented on the format, saying that they enjoyed listening to 2 scientists at different career stages and that both speakers were honest about the issues they had faced so far.  There was a good range of questions from both genders.  The wine and cheese afterwards was well attended and led to many lively discussions. 


	
	
	Female postdoctoral researcher forum in Life Sciences is an online forum for Life Sciences postdocs.  A monthly coffee morning/lunch has been running since October 2012. Events are organized by  postdoctoral students. Some meetings have invited guests, e.g. two early career academics (Assistant Professors attended to talk about career progression for postdocs wanting to stay in academia).

	The coffee mornings usually attract between 10 and 30 researchers. Postdocs have welcomed the opportunity to engage in discussions. 



	
	
	Physics hosted an International Women’s Day on 8th March 2013 where staff attended talks on writing grant applications, and networking opportunities.  This will be an annual event. 

	17 females and 3 male members of staff attended.  Feedback was positive and ideas for future events were discussed.

	Enhancing opportunities for mid-career females
	Retention and progression of mid-career female scientists
	Workshop (with lunch) was held in February 2013 for mid-career female scientists to consult with them to identify any issues or initiatives that could improve their work life balance and promotion prospects.

Senior Women’s Informal Lunchtime Meetings  have been re-established (An action brought forward from Workshop for mid-career female scientists). 

	18 attendees. Meetings will now take place termly.  Feedback indicated that the Senior Women’s Informal Lunchtime Meetings should be re-established.


	Impact, Career Development and Leadership


	Preparing staff as leaders


	£30k of EPSRC funding made available to STEMM Departments for Impact, Career Development and Leadership initiatives.

Research Team Leadership Programme (held Jan to March 2013)

 
	15 enquiries of which 12 have been from women. 8 applications received – all were funded, of which 7 were from women.

15 delegates attended, 11 of which were female ranging from grades FA6-FA9 (PDRA to Professor)

	Variation between maternity leave policies


	Clarification of University and funding councils maternity policies/funding


	Maternity leave has been raised at various management levels as well as national (Russell Group Diversity) meetings. As a consequence, Warwick will be attending a scheduled meeting with other Russell Group Universities with RCUK in April 2013 to seek clarification by the Research Councils on their latest E&D statement and to also discuss maternity issues, which seem to be the main concern raised as part of the Athena process by all Universities.   
	Year
	No. of STEMM staff taking Maternity Leave

	
	
	
	2008/09
	31

	
	
	
	2009/10
	26

	
	
	
	2010/11
	26

	
	
	
	2011/12
	26

	Lack of experience of both staff and line managers on managing maternity leave, including arrangements for staff returning from maternity leave.
	Maternity Checklists
	Resulting from consultation with the Returning Parents Network Group (RPNG), HR have produced two checklists, the first for staff about to go on maternity leave, so they are clear of any issues they need to be aware of and the second to be issued to the line manager about one month before the employee returns from maternity/ adoption leave. This enables the department to be ready to receive the employee back into the work place by ensuring logistical arrangements are in place so that the employee feels welcomed back to work at a time when their levels of confidence may be low. 
	Returning Parents Network will report on success of checklists once they have been in use for a sufficient period of time.

	(ii) Actions designed for women but open to men
	

	Conference attendance is essential for academics but difficult if staff have childcare responsibilities


	Conference Attendance Child Care Fund


	The University recognizes the importance for academic and research staff to attend conferences but also understands that this is often difficult for parents with childcare responsibilities.  An annual fund has therefore been established to assist with payments of extra childcare arrangements for individuals attending conferences/ workshops etc. (£100 per claim). For the first 2 years the fund was provided by the Research and Development Fund. From 2013 the fund has been integrated into the Science Faculty budget. 
http://www2.warwick.ac.uk/services/equalops/athena/warwickconferencesupportawards/ 

This initiative has also allowed us to develop experience of Early Career Researchers on financial decision-making (2 ECR’s are on the decision panel judging applications for conference support).
	Year
	No of Awards
	Amount

	
	
	
	2010/11
	2
	£151

	
	
	
	2011/12
	4
	£306

	
	
	
	2013
	8
	£574

	
	
	
	1 further submission has been supported but a claim has not yet been received

	Occasional childcare
	University nursery
	After consultation with staff and subsequent discussions with the University nursery and members of Network-AS, the nursery will now take a child on a one-off basis if a parent needs cover to attend a conference and their child does not usually use the facilities and there is space available. 
	2 in 2010

2 in 2011

	Visiting children at the University nursery can result in lost parking space at the Medical School and Life Sciences campus
	Parking reserved for parents visiting babies
	 A novel one year pilot project started in January 2013 to allow for dedicated parking spaces at WMS/Life Science campus for parents (in particular nursing mothers) of children in the University nursery located on main campus.  Travel between sites takes around 8 minutes by car. Parking is extremely limited at WMS/Life Science campus and if a mother needs to feed her baby, it is highly advantageous to have parking guaranteed on return to campus.   The uptake and effectiveness is being measured. 
The University has also initiated a campus shuttle bus to ease parking problems of staff moving their cars from one part of campus to another.
	WMS have a project officer who will work with Security Services to monitor usage.  An interim report will be delivered to the AS Network Group.


	Communication and Impact
	Improving communication skills
	Two day course on 15/16 March 2013 developed specifically for postdoctoral and early career researchers in the sciences. Run in partnership with BBC Radio Coventry.

	Only 2 attendees. Decision needs to be taken if course is to be re-run in a different format.

	In chemistry percentages of u/g, p/g and PDRAs are about 40% but percentage of Assistant professors decreases to under 20% nationally.
	Initiate an annual event for female chemists who want to move to an independent career
	First of the annual ‘Irène Joliot-Curie Conference: establishing an independent career in chemistry’ (http://www2.warwick.ac.uk/fac/sci/wcas/events/independentcareer/) which was targeted at women but welcomed and benefited from the men who attended. Inclusion of displays such as the role of Women in Biochemistry between 1906–1939 at relevant conferences reminds us that women have been successful in science. Imperial College has undertaken to hold the next conference. In light of the success of 2012, they have secured MP Esther McVey as the after dinner speaker.  Talks are in progress with the Royal Society of Chemistry to take over responsibility for the annual event.
	60 attendees (55 Female & 5 Male) from across 19 universities attended the first conference.


	Student Parents & Carers of young children, support network
	Students’ Union Student Parent & Carers Drop In Sessions
	The Students’ Union hold free coffee mornings for student parents where children are welcome, designed for parents to chat, network & get support.  In addition Warwickshire Young Carers run free and confidential drop in sessions for Carers to chat & find out about available support in the area.
	This group now has a dedicated mailing list and a Facebook Group of ~ 80 contacts and therefore a community is beginning to emerge.

5 coffee morning sessions (with ~ 12 participants at each session) have been run and were a great success.

	(iii) General support mechanism triggered by AS considerations
	

	Communication of AS principles and University initiatives
	Dedicated AS Website http://www2.warwick.ac.uk/services/equalops/athena/ 
	The website includes links to all AS submissions, a News Page, Details of both AS Steering and AS Network groups, Minutes of meetings, profiles and contacts. In addition AS Logo included on University’s ‘About’ Page, HR page & Job Vacancies page & all departments websites who have gained an award
	Awareness and provision of up-to-date information of AS Charter and progress on Warwick’s AS work across STEMM Departments and the wider University.  Sharing of best practice initiatives. 

	Communication of best practice identified through AS process
	AS Window on Warwick Workshop for Non-STEMM Departments
	Window on Warwick is a range of short, one hour sessions usually at lunch time, open to all University of Warwick staff.  This session was to inform non-STEMM staff about the principles of AS, how it benefits departments by identifying trends within data and raising awareness about common issues.  Sharing of best practice to ensure that other departments benefit from the initiatives resulting from the AS process.


	Non-STEMM departments have requested individual department meetings to understand and gain more information on the AS principles.   Non-STEMM staff have requested to attend the AS Network Group.

	Lack of general understanding of flexible working options
	Flexible Working Policy
	Flexible working hours are usually agreed between staff and Head of Department on an informal and local level. The Flexible Working Policy has been updated in May 2012 to give greater clarity to the fact that Parents of children under 17 or disabled children under 18 or carers do have a legal right to apply for flexible working and gives clear guidance and links to the government website. WMS are currently piloting a scheme to monitor flexible working arrangements. 
	WMS are piloting a scheme to monitor flexible working. There have been 9 requests in 2012 & 2013 – 7 of which have been granted & 2 of which are still being reviewed. WMS will feedback any increase in the numbers requesting and being granted flexible working hours.  

	Postdoctoral researchers often feel isolated


	Postdoctoral Newcomers Meeting (PNM) 


	A PNM (a Networking event across disciplines) has been established which links in with the Research Staff Forum (RSF). It creates networking opportunities for new postdoctoral researchers enabling them to meet with their representatives and other key people such as LDC and Library staff and also find out what support the RSF gives researchers.  
	Welcome Social event for all early career researchers is to be considered at the June 2013 Research Committee Meeting. Prior to this meeting members will find out what happens in individual departments as part of their induction programmes.

	Pay Equity 
	Equal Pay Audit
	The University undertook an Equal Pay Review in 2011 and reported that:
“there is no evidence revealed by the Review of inequitable disparities in base pay distribution within grades on the grounds of gender, ethnicity, disability, age (other than explained by incremental progression), contract type or full/part time working among employees in grades 1A–8. The conclusion reached by this Review is that there is equal pay for work of equal value, whether in relation to gender, ethnicity, disability or hours worked.”
The Review states:

· There is no statistically significant gender disparity by grade. The maximum base pay disparity is 2.89% in grade 7, which is not statistically significant.

· In five grades female average base salaries exceed that of male base salaries; in four grades male average salary exceeds female. Therefore there is no consistent pattern of gender bias.

· There is broad gender pay equity in jobs of similar seniority. The disparities, such as they are, are not statistically significant and are not consistently in favour of either gender. “
Subsequent Actions from Vice Chancellors Advisory Group (VCAG) :
· How can the University create a culture hospitable to women?

· Prompting, preparing and mentoring women for promotion
· Re-launch Women’s Network

· Undertaking Departmental action plans where pay gap is greatest

· Applying Athena SWAN principles throughout the University

· Encouraging mobility of women to accept appointments

· Developing benefits package attractive to women.


	A recent analysis of gender pay disparity amongst Professorial staff across the University and comparing subject disciplines with Russell Group data confirmed that in the STEM departments at Warwick the disparity between male and female salaries was 0.86% (at 1 October 2012) compared to 5.35% in STEM departments across the Russell Group (at 1 January 2012).


	Networking Opportunities


	To encourage more interdisciplinary networking


	Workshop on ‘Activity Monitoring for Behaviour, Health and Well-Being’ (27 February 2013). This workshop raised awareness about research undertaken within the Institute of Digital Health and to create a network of biomedical engineering researchers within the University and the NHS.
	32 Female and 33 Male attended (including some external delegates)

Positive feedback on:
“Discussion of active areas of research. I feel it is important to foster a collaborative approach to developing such technology.”

	
	
	Funding support for Research Active Staff Networks (for all Faculties) to support research/academic staff to set up or maintain an existing Research Active Staff Network.

Research Staff Forum has been established to serve a general networking function and to provide a focus for gathering research staff views on issues such as induction, training and development opportunities.


	· Improved structures for communication.

· Contributed to documentation for career reviews.

· Campaigned for an induction provision specifically for research staff.

· Contributed to shaping the focus of the careers service work for research staff.

· Facilitated involvement in national initiatives such as the Contract Researchers’ Online Survey.

	
	
	WMS Athena SWAN Workshop held on 14th June 2012 as a result of WMS becoming the first Medical School to achieve the Athena Bronze award. Warwick hosted a one day event to discuss how the WMS Athena submission was approached and the challenges faced.  


	Delegates: 41 Female & 8 Male.  23 Institutions (including Warwick)

Feedback from event: 
“I gained a better appreciation of how to achieve a good submission and good engagement”

	
	Funding for Research Active Staff Networks
	LDC has funding available to departments and faculties wishing to set up or maintain an existing research active staff network.

£10,000 in funds and to date £8,610 has been used on a variety of networks, e.g.

· WMG Researcher Forum & Leadership and Brainstorming meetings

· UK Data Archive Workshop for Researchers

· Network for Early Career Researchers within WMS

· IDH Network for Biomedical Engineering Researchers

· Researching Human Fatigue in the Workplace
	8 researchers applied for funding, 6 of which were female

	
	Special Interest Groups (SIGs)
	SIGs were established in an attempt to involve postdoctoral researchers to collaborate or lead on projects to enhance their research experience and contribute to their skills and knowledge base when applying for future academic positions. Members of SIGs and RSF have collaborated in arranging the PNMs at the start of each term. These meetings promote collaboration and networking amongst the entire postdoc community at the University. SIGS developed into Sandpit events which are designed to encourage researchers to work collaboratively.  The sandpits were developed in partnership with the Library, RSS, IAS, LDC, Careers & Skills & the Knowledge Centre and are funded by EPSRC. By participating in the Collaborative Sandpit researchers have an opportunity to make new cross-disciplinary connections, developing new research projects, coupled with real-time peer review which can lead to research funding.  The focus of the sandpit is thinking innovatively and creatively to solve problems.   It not only challenges participants to work collaboratively but also gives them the opportunity to do something which is CV worthy. 
	The initial pilot ‘Research Match’ saw 600 researchers sign up to introduce themselves to other researchers and their work.  The SIGs developed from this pilot with 900 research led events taking place in 2012/13. This has now transformed into ‘Sandpits’ events

Sandpits took place in December 2012.  Next one planned for July 2013 with 3 more for the academic year.

	Clarity on promotion and career progression
	Career progression information
	Central web information and communication on understanding career progression and promotion systems has been improved since our Bronze submission. LDC as part of the AS project  organized various focus groups in 2011, specifically 2 such focus groups on the challenges of career progression and in particular in promotion to leadership roles for women in STEMM departments. The outcome of the focus groups at the time was that the women felt that sufficient support and information was available at Warwick and that it was unnecessary to provide a female only leadership programme. Since that time, through further consultation it is becoming evident that it would prove useful to some female researchers that such a course would be of benefit and therefore LDC is currently investigating this requirement.  This will continue to be monitored and reviewed on an annual basis.

An Advanced Workshop day for ECR’s on Friday 1 February 2013 on Career Planning and Progression.  Guest speaker Dr Kate Sang (Acting Chair, Feminist and Women’s Studies Association UK) who spoke about gender and academic careers.  Workshop also held sessions on women in science at Warwick, work-life balance and planning career breaks. Feedback from event: 

	Initial consultation in 2011 indicated that a Women’s Leadership course was not required. Further consultation is now being undertaken to see if there is such a requirement going forward.

48 attendees (32 Female & 16 Male)

Feedback from event: 
“I found this event really interesting. Apart from the value in networking, it brought together some really good speakers who gave us insights into the academic career. I really enjoyed the discussions on the different dimensions of gender in academia.”

	
	Annual ‘Demystifying Promotion’ event
	An annual event has been instituted in April 2013, associated with the Annual Reviews, to provide information about what is needed for promotion at each career stage except Assistant to Associate Professor (tenure track stage, which is already very well organized). Breakout groups are titled to deal with issues women have identified during consultation including:  career break/other commitments; collaborative research and/or teaching; part-time work/short term contracts.
	40 staff attended the event on 9 April 2013 (20 males and 20 females). 10 speakers contributed to the event, including 2 PVC’s (both female) and the Chair of the Faculty of Science (female).

Feedback was excellent 


	Employability Skills and Careers 


	Training and development whilst at Warwick
	To ensure that research active staff have sufficient training and development to enhance their careers either at Warwick or elsewhere.  Range of courses include:

· Academic Careers and Employability Programme offering 1-1 support for PDRAs.

· Presenting your research to different audiences

· Being an Enterprising Researcher

· Technology for Researchers run in collaboration with Teaching & Learning

· Coaching and Mentoring including one to one coaching, three way coaching and Coaching through Reflective Writing.
· An Introduction to Entrepreneurship in collaboration with the Science Park.

· Activity Monitoring for Behaviour, Health and Well-being

· Policies and Practical Data Management for Researchers

· Effective writing for bids and grants

· Impact, Engagement and Dissemination

This list is not exhaustive and the design of the course content is a result of collaboration with academic departments via various fora to determine what is required by staff. 
Introduction of an online space designed to support PDRAs. The Portfolio offers both a portal to a wide range of opportunities and resources, as well as a personal portfolio enabling researchers to build a record of their training, experiences and achievements throughout their research degree. 
The IAS Open Access Journal for Early Career Researchers has been launched but also gives later stage research active staff the opportunity to be on the editorial board or to have peer review experience.

	Postdocs find this very useful. Funding has been extended to cover this as there is increasing demand for the support. 

Good representation of female staff at this event

1-1 sessions with research active staff (approx. 15 staff – 13 females, 2 males).  Increasing need for coaching. Funding £5K for 2 events, £2K for the pilot.  Very successful event with over 55 attendees with inter-department representations.  Networking opportunity has resulted in collaboration and an interdisciplinary bid being written.
A Learning and Development Adviser Post has been funded for the next 3 years for future Research Active Staff provision.



	Staff not feeling able to discuss impact of family issues on their work
	Acknowledgement of family issues
	In recent years Warwick has been developing a culture of encouraging staff to be open about family-related issues so that a collegiate solution to any issues can be developed that both supports the individual concerned and does not impose too much on colleagues who may have to cover for them. 
	STEMM departments Athena SWAN work has provided a mechanism for staff to raise issues, and whilst no formal impact is noted here, it is hoped that more staff will feel confident in requesting flexible working. STEM departments will be encouraged to follow the scheme currently being piloted in WMS to record flexible working requests to monitor if there is an increased uptake.

	Women on average prefer a more collaborative working style than their male colleagues
	Collegiality in Promotion and Annual Review
	After consultation with STEMM departments, Annual Review forms have been modified for 2013 to include a section on teamwork/collegiality in recognition of the importance to the University’s goal of becoming a top 50 university of the contributions of individuals in ways that are not REF-recognised. 
	STEMM departments to monitor feedback from staff to ascertain their preferred working style.

	Academics and the AS agenda
	Athena Administration - Staff remits
	At Warwick the AS agenda is academically driven, but the importance of administrative staff support to ensure regular meetings and communication across fora has been recognized. 
	Dates of meetings arranged and notified for six months at a time.

Continuous focus on Athena agenda

Employment of Athena Project Officer

Athena recognized within job role descriptions.

	PDRAs often do not know what is required of them
	Designed an accredited Postgraduate Certificate in Transferable Skills in Science for PDRAs
	It has been designed to be a career development tool that can be used to seek help required from mentor(s) while at the same time making it clear what skills a postdoctoral researcher will need to make the step to an independent career. The structure and mechanism have proved to be preferentially beneficial to women.
	593 attendees registered
 

	Parents of young children, especially mothers returning to work after maternity/adoption leave, were looking for a support network
	The Returning Parents Network Group (RPNG) 
	The RPNG (set up in 2012 for all parents returning to work from maternity, adoption and paternity/parental leave and supported by the University) gives staff an opportunity to discuss parenting and return-to-work experiences. The group seeks to represent parental needs and put across the views of this particular staff group through representation on the EDC and the Network-AS. http://www2.warwick.ac.uk/services/equalops/news/parents 
	There have been 8 meetings of the RPNG - the numbers of those attending varies from 4-25 people.  At a meeting where a Life Coach was invited to talk to working mothers 22 people attended.



	
	The Returning Parents Mentoring Scheme (RPMS)
	In parallel with the RPNG, LDC provides trained mentors to assist returning parents with the transition back into the workplace whilst trying to juggle family life.  The mentor is a member of staff who has recent experience of combining work and family life. The aim is to help staff anticipate some of the issues involved in baby-related leave and to manage these on their return. 
	Five members of staff have been trained as mentors for returning parents.  To date 2 members of staff have requested a mentor to help them with the transition of returning to work.  This will continue to be monitored. 

	Parents of young children, especially mothers returning to work after maternity leave, were looking for a support network

Network-AS has discussed the challenge of finding holiday child-care
	School holiday child-care provision
	School holiday child-care provision is an ongoing issue for staff with children. Warwick is working hard to enhance the opportunities available for children during school holidays, these currently includes: Tennis, Climbing lessons, Art Sessions and the Mad Science Club. Discussions are in progress to provide additional support. Recently, the Network-AS has highlighted that although the increased child-care provision over the school holidays was a positive step forward, there is still little provision for whole days during vacation for children of school age and it is often difficult to organize child-care and/or rearrange working hours to look after children. The University is actively examining possible ways to rectify this and is investigating the possibility of creating a Holiday Scheme for school aged children.

A project team is currently investigating potential options for school holiday childcare provision at the University. In response to Network-AS feedback, these options focus primarily on offering whole day childcare provision and encapsulating a range of activities from across the University. The project team is currently gauging internal interest, engaging stakeholders and potential contributors, and seeking to develop plans for a pilot Holiday Scheme to take place in July–August 2013.  
	Significant progress has been made within the evidence-based scoping exercise: (a) Initial Core Project Group established; (b) Desk based research on provision at other institutions and locally; (c) Liaison and early dialogue undertaken with those who have relevant existing provision and key service providers across the University; (d) On-line questionnaire to all staff and students (open until end of April 2013).  A significant number of responses have already been received:

· 343 responses

· Vast majority of respondents were staff (195 full time; 125 part time)

· 338 respondents felt that the Summer Holiday Scheme was a good idea

· 255 respondents were interested in their child attending the holiday scheme.

	To attract more females to apply for academic positions
	Exploration of changes to adverts for recruitment.
	Deputy Director of HR to explore possible changes to recruitment advertising in order to attract more applications to academic positions from females.  Adverts to include statements such as job share, part-time considered. 
	To attract more applications for academic positions from females.


[Type text]


