## Sheet1
HREiR Action plan - University of Warwick - May 2022-June 2024
Glossary of Terms
ECR CPD - Early Career Researcher Continuous Professional Development
HR - Human Resources
HREiR - HR Excellence in Research
IAS - Institute of Advanced Study
ICURe - Innovation to Commercialisation of University Research
PGR - Postgraduate Researcher
PI - Principal Investigator
PVC (Research) - Pro-Vice-Chancellor (Research)
R&IS - Research & Impact Services
RAS - Research Active Staff
RCF - Research Culture Forum
RDF - Researcher Development Framework
RSF - Research Staff Forum
UoW - University of Warwick
WIE - Warwick Institute of Engagement
Details
| Institution name: | University of Warwick | The institutional audience* for this action plan includes (complete or delete, as appropriate):
| Cohort number: | 8 | Audience (beneficiaries of the action plan) | Number of (as at 21/05/2021) | Comments
| Date of submission: | 30/4/2022 (resubmission from May 2021) | Research staff | 727
| Institutional context: |  | Postgraduate researchers | 95
|  |  | Research and teaching staff | 1133
|  |  | Teaching-only staff | 760
|  |  | Technicians | 345
|  |  | Clinicians | 77
|  |  | Professional support staff | 3960
|  |  | Other (please provide numbers and details): | 635 | Graduate Teaching Assistants
| Obligation | Action | Success measure (SMART) | Deadline | Responsibility | Progress update (to be completed for submission) | Outcome/ result | Action carried over from previous action plan?
Environment and Culture
Institutions must:
ECI1 | Ensure that all relevant staff are aware of the Concordat | (1) We will ensure that awareness is raised amongst researchers of the impact of the University's commitment to the principles of the Concordat, as this will be explicitly stated in the new Researcher Induction programme (see ER1). (2) We will also ensure that awareness is raised amongst PIs of their responsibilities to their research teams under the Concordat through post-award comms and support. | (1) 90% of new staff to attend researcher induction, consequentially raising awareness of Concordat. (2) 90% of PIs of externally funded grants to receive communication about the effects of the Concordat on research teams. | (1-2) year 1 | (1) Director of HR (2) Director of Research & Impact Services |  |  | New
ECI2 | Ensure that institutional policies and practices relevant to researchers are inclusive, equitable and transparent, and are well-communicated to researchers and their managers | (1) We will convene regular meetings of the existing Research Culture Forum, which reviews Institutional policies and practice from a research perspective. This meeting is chaired by the PVC (Research), and is attended by researchers at all levels, PGRs, technicians, HR and Social Inclusion (ED&I). The Research Culture Forum is developing a comms plan to ensure that information is disseminated to all communities. It is planned to disseminate the information through Research Staff Forum communications, Researcher Inductions and to PIs through post-award support, as well as other mechanisms (see ECI1). (2) The University has a 10 year Social Inclusion Strategy in place (2030), this is monitored by the Social Inclusion Committee, Chairs of the Race, Gender, LGBTQUA+, Disability and Faith taskforces all sit on the committee, along with key departments such as HR. All relevant policies and practice are monitored by the committee and issues of concern and good practice are discussed and actioned here. (3) HR policies on recruitment, selection and promotion are to be reviewed with a diversity lens to ensure that they are inclusive and promote diversity and equality. (4) A consultation process was undertaken with the Research Staff Forum and key stakeholders are redesigning the induction for new research staff to ensure all policies are communicated effectively to new staff. | (1) Development of email circulation list through the Research Staff Forum / Research Culture Forum to inform researchers of relevant policy and practice updates. Metrics to be set regarding circulation figures. (2) Social Inclusion committee meets termly to review relevant policies as part of its Terms of Reference. The Research Culture Forum will include as an agenda standing item a report from the Social Inclusion team. (3) HR will review all processes from an ED&I perspective, with resulting more inclusive processes in place. (4) Launch of newly redesigned induction incorporating pilot feedback September 2022. | (1) year 1, (2) on going, (3) year 1-2, (4) year 1 | (1) Chair and Secretary to Research Culture Forum (2) Director of Social Inclusion (3) Director of HR (4) Chair of Research Staff Forum |  |  | New
ECI3 | Promote good mental health and wellbeing through, for example, the effective management of workloads and people, and effective policies and practice for tackling discrimination, bullying and harassment, including providing appropriate support for those reporting issues | (1) The Workload Model Steering Group, led by the Provost, is working with key stakeholders with the aim of developing a workload framework / template. The aim is to develop a common institutional workload model with agreed target metrics. (2) Warwick has an Employee Assistance Programme and subscribes to and promotes Togetherall, an anonymous mental health and wellbeing support group. (3) The University's Report & Support system allows all staff to report discrimination, bullying and harrasment and provides support for those who are affected. Culturally sensitive support is available where needed. (4) Warwick runs 'Challenging Inappropriate Behaviour' workshops to ensure a working and learning environment in which all University members are treated fairly and with dignity and respect. (5) Warwick runs online courses to promote mental health and raise awareness about discrimination: "Mental Health: Stress Less", "Menopause at work", "Understanding Unconscious Bias", "Understanding Race Bias". "Understanding Unconscious Bias" is a required module for those who are on an interview panel for hiring. (6) We are in the process of establishing a new two-way engagement mechanism between the University and staff, regarding social inclusion and well-being. This mechanism can be used to promote and monitor good mental health and well-being and to raise awareness of discrimination. It can also be used to get feedback on the University's strategies from staff. (7) Bullying, harassment and discrimination will also be monitored through the newly established 'Inclusion Survey', helping the university better understand the number of incidents taking place and in which departments, monitoring will enable identification of postdoctoral researchers as a group. | (1) Workload has been identified in our insitutional survey as an area of concern that impacts on the mental health wellbeing of staff members. Target metrics to be established in year 1. (2) Review of EAP reports to identify areas of concern during year 1 and establish benchmarks / target metrics for action during year 2, noting that it is not possible to filter data by research staff only. (3) These are anonymous services and we cannot track engagement by research staff. (4) We are currently adapting the workshop to tailor it more closely to the needs of research staff. The new workshop will be launched in September 2022 to be rolled out twice termly. (5) "Understanding Unconscious Bias" module is taken by 100% of those who are on an interview panel to hire research staff, from year 1. For other relevant modules, we will establish a mechanism to track how many research staff are taking them in year 1 (currently, we do not have a break-down of participants by contract type). (6) We will establish the new two-way engagement system, which will be lead by HR Engagement Director who starts in May 2022. A revised approach will encompass the needs of related staff groups and will be in line with strategies such as Wellbeing and Social Inclusion. (7) Inclusion survey to monitor researcher feedback on key issues. Metrics to be set and monitored. | (1) year 1, (2) year 1-2, (3) n/a, (4-5) year 1, (6) years 1-2 (7) May 2022, then bi-annual | (1) Provost (2) Director of Wellbeing and Safeguarding (3) Director of HR (4-5) Learning and Development Manager, Organisational Development (6) HR Engagement Director (7) Director of Social Inclusion |  |  | New
ECI4 | Ensure that managers of researchers are effectively trained in relation to equality, diversity and including, wellbeing and mental health | (1) ED&I Moodle has been reviewed and an updated Warwick Principles and Social Inclusion (WP&SI) Moodle has been created in collaboration with Warwick's five Task Forces for protected characteristic groups (Gender, Race, Disability, LGBTQUA+ and Faith). It has been approved as a mandatory element of induction and Personal Development Reviews. (2) Workshops are being delivered to managers and team leaders on creating inclusive cultures and developing diverse talent. | (1) In collaboration with Strategic Planning and Analytics Office, establish a method to get the course completion stats for managers of researchers in year 1. 50% of managers of research staff complete the training in first year, 60% in the second year and 70% in the third year. As a mandatory element of the induction process for all new joiners, and as part of annual Personal Development Review, staff will be required to complete this training. The aim is to achieve 70% compliance in first year. (2) Impact to be measured through recruitment and promotion and inclusion survey. | (1) years 1- 3 (2) Year 1 establish benchmarks from outcomes of inclusion surveys, diversity targets for senior posts reported on annual basis | Director of Social Inclusion, Director of Strategic Planning and Anaytics Office. |  |  | New
ECI5 | Ensure that researchers and their managers are aware of, and act in accordance with, the highest standards of research integrity | All staff and students delivering research must complete the institutional mandatory research integrity training (as per the Research Integrity training policy). | 90% of research staff to complete the training (90% of new research staff and 90% of researchers including PGR students applying for research ethics in the first year. 100% of staff awarded research grants in year 2) | year 1-2 | Director of Research & Impact Services |  |  | New
ECI6 | Regularly review and report on the quality of the research environment and culture, including seeking feedback from researchers, and use the outcomes to improve institutional practices | One of the strands of the Institutional People Strategy is Culture, Values and Employer Ethos. Our strategic intent is to create an employer ethos based on our values, where people are at the heart of what we do and we focus on the employee, to create a culture where each person can thrive in their own way and our combined capability and talent grows as a result. (1) We will convene regular meetings of the Research Culture Forum to discuss the quality of the research environment and culture. Discussion is underway on the mechanisms for input and dissemination. (2) We will review the format and function of the Research Staff Forum and how it can be used more effectively. (3) We will be running a series of values workshops to inform our UoW values, with representations from across the University. We will ensure Research staff are included in these workshops. (4) Following the completion of a research project, taking place March - July 2022, on inclusion and diversity experience in research at the University, recommendations from the report will be put into an action plan to improve the experience of inclusion and improve diversity for researchers. (5) In May 2022, we will be carrying out our first culture survey which will look at all aspects of diversity, inclusion and opportunity. The outcomes will inform our work on improving inclusive culture. | (1) We will convene Research Culture Forum three times per year from year 1. (2) We will review the function of the Research Staff Forum in year 1. The Research Culture Forum will disuss the outcome of the review and take necessary action in years 1-2. (3) Workshops with engagement of researchers to be organised for year 1 (4) Diversity and Inclusion culture project recommendations for action year 1 completed and embedded into wider research culture action plan. (5) Culture survey measures to be assessed and acted upon to improve our inclusive culture. | years 1-2 | (1) Chair and Secretary to Research Culture Forum (2-3) Director of HR (4-5) Director of Social Inclusion and Director of HR |  |  | New
Managers of researchers must:
ECM1 | Undertake relevant training and development opportunities related to equality, diversity and inclusion, and put this into practice in their work | see ECI4 and ECI5 | Managers of research to complete the relevant training before being allowed to hire postdocs or supervise PGRs. |  |  |  |  | New
ECM2 | Ensure that they and their researchers act in accordance with the highest standards of research integrity and professional conduct | see ECI5 | [5 empty] | New
ECM3 | Promote a healthy working environment that supports researchers' wellbeing and mental health, including reporting and addressing incidents of discrimination, bullying and harassment, and poor research integrity | see ECI3 | [5 empty] | New
ECM4 | Consider fully, in accordance with statutory rights and institutional policies, flexible working requests and other appropriate arrangements to support researchers | (1) We will ensure that managers are fully informed of our flexible working policy, hybrid workjing policy etc. through managers training and induction. (2) Policies such as flexible working and hybrid woking policies are brought to the attention of HoDs through HoD communications and HoD forums. | (1) 90% of PIs of externally funded grants to receive communication about the effects of the Concordat on research teams, as a part of the post-award induction scheme to be developed in year 1 and 2. (2) Regular HR updates for HoDs include research focused information. | years 1-2 | Director of HR |  |  | New
ECM5 | Engage with opportunities to contribute to policy development aimed at creating a more positive research environment and culture within their institution | PVC (Research) and Research Executive will engage with Heads of Department, Research Directors and Research Managers through various mechanisms to discuss policies and research culture. The mechanisms include PVC (Research)'s visit to departments, and Heads-of-Department Forums. | Better engagement of Heads of Research with PVC (Research) and Research Executive - 100% of PVC (R) academic departments visited by the end of 2021-2022 academic year, and having a standing item on research in Heads-of-Department Forums by year 1. | year 1 | PVC (Research) |  |  | New
Researchers must:
ECR1 | Actively contribute to the development and maintenance of a supportive, fair and inclusive research culture and be a supportive colleague, particularly to newer researchers and students | (1) We will disseminate examples of best practice through the Research Culture Forum and use relevant communications to ensure that researchers feel empowered to make changes within their research groups. (2) We will encourage good research practices through the completion of research integrity training. (3) We will encourage researchers to take Dignitiy and Respect and Challenging Inappropriate Behaviour training, which encourages particpants to consider how to contribute to creation of a fair and inclusive environment. | (1) Development of email circulation list through the Research Staff Forum / Research Culture Forum to inform researchers of research culture initatives in year 1. Metrics will be set regarding circulation figures. (2) 90% of research staff to complete Research Integrity training. (3) 20% of research staff to complete the training by year 2 | (1) year 1, (2) year 1, (3) year 2 | (1) Chair and Secretary to Research Culture Forum, (2) Director of Research & Impact Services, (3) Learning and Development Manager, Organisational Development |  |  | New
ECR2 | Ensure they act in accordance with employer and funder policies related to research integrity, and equality, diversity and inclusion | see Induction (ECI1), Research integrity training (ECI5) | [5 empty] | New
ECR3 | Take positive action towards maintaining their wellbeing and mental health | see ECI3 | [5 empty] | New
ECR4 | Use available mechanisms to report staff who fail to meet the expected standards of behaviour, particularly in relation to discrimination, harassment, bullying, and research misconduct | see ECI3 | [5 empty] | New
ECR5 | Consider opportunities to contribute to policy development aimed at creating a more positive research environment and culture within their institution | (1) We will engage Research Staff in institutional and departmental Research Committees, including representatives on Research Culture Forum, Research Committee, Research Ethics Committees - and explore further options. (2) We will inform new research staff of these opportunities in the induction and the Research Staff Forum. | (1) By year 2, all the committees mentioned have a ECR representative. Technician representatives to also be appointed on appropriate Committees. (2) 90% of new staff to attend researcher induction, consequentially raising awareness of the opportunities. | (1-2) year 2 | (1) Chairs of Committees (PVC and Deputy PVC Research) (2) Director of HR |  |  | New
Employment
Institutions must:
EI1 | Ensure open, transparent and merit-based recruitment, which attracts excellent researchers, using fair and inclusive selection and appointment practices | We are currently reviewing our end-to-end recruitment and selection approaches and designing 'future state' approaches which embed inclusive practices. This will also include adopting tailored talent attraction approaches based upon roles and reviewing our recruitment advertising channels. Once a redesigned approach has been agreed we will identify appropriate diversity and inclusion measures. Phase 1: Current State Review - complete. Phase 2: Future State Design - Future approaches /options due to be completed for review at end April 2022. Detailed design - scheduled for completion December 2022. Phase 3: Development and Implementation is dependent upon HR system - Payroll implementation, therefore expected to start in 2023. | Improved end-to-end recruitment process - better candidate and hiring manager experience. Improved recruitment data analytics which will provide a mechanism for monitoring and tracking diversity of applicants and shortlists. These points will be achieved by December 2023. Diversity-focused workforce profile - annually reviewed in line with Pay Gap Reporting (Gender, Ethnicity, Disability, LGBTQ). https://warwick.ac.uk/services/equalops/learnmore/data/paygapreport | year 2 | Director of HR |  |  | New
EI2 | Provide an effective induction, ensuring that researchers are integrated into the community and are aware of policies and practices relevant to their position | A new induction for research staff was launched in autumn 2021. This aims to provide an overview of central services and departments important to researchers at Warwick, key contacts, and an opportunity to network with other new research staff. The current plan is to run x2 inductions during the autumn term, and one each during the spring and summer term, although this can be increased in response to the number of new research staff joining Warwick. | 90% of new research staff to attend induction. | year 2 | Director of HR |  |  | New
EI3 | Provide clear and transparent merit-based recognition, reward and promotion pathways that recognise the full range of researchers' contributions and the diversity of personal circumstances | (1) We have a clear academic promotions pathway and transparent framework based on four pillars - Research & Scholarship; Teaching & Learning; Impact, Outreach & Engagement; and Leadership & Collegiality. Promotion applications are reviewed by the Academic Staff Committee and/or University Professorial Promotion Committee based upon evidence submitted and decisions made based upon meeting set criteria. This approach has been updated in recent years to allow all academic staff to apply for promotions regardless of whether their application was supported by the relevant Head of Department or not. Feedback meetings and mentoring support have also been introduced. There is equality under the academic promotions process for those on T-focussed, R-focussed and T&R tracks. (2) Application forms have been updated to provide an opportunity for applicants to include input regarding the impact of Covid - e.g. delays in publishing, increasing caring responsibilities, illness etc. (3) Launch of ECR CPD Framework October 2022. | (1-2) We are now tracking promotion progress by grade and by protected charasteristics to gain insights into Academic career progression. In 2020/21 Academic Promotion Cycle we had a success rate of 90% (Female : 94%, Male : 86.2%), Research focused staff at all levels had 100% success rate, with the exception of 1 out of 15 applicants who applied for promotion to Assistant Professor, Staff on Fixed Term Contracts had a 90-100% success rate depending on grade. Ultimately we aim to monitor each stage of the academic career lifecycle by diversity to identify groups that are showing slower progression. We also aim to provide comparable promotion opportunities for technical specialists, not on academic T&Cs. (3) Successful launch of the framework. | (1-2) on going, (3) year 1 | Director - HR Strategy |  |  | New
EI4 | Provide effective line and project management training opportunities for managers of researchers, heads of department and equivalent . | Leadership & Management Development is one of the eight key strands of the People Strategy. Our strategic intent is to grow organisational capability and talent through excellent management and leadership skills, which in turn improves overall performance and delivers ambition. We have recently appointed a Director - Leadership & Management Development who will lead this strand of our People Strategy. (1) Piloted Project Management Essentials, aimed at early career researchers and Managing Complex Research Projects, aimed at mid- and senior-career researchers. Take-up for these pilots was very good and both series received excellent feedback from delegates. (2) Project Management Training: Managing Complex Research Projects This is a two-part series aimed at more experienced researchers from Research Fellows to Professors. It provides a toolbox of practical techniques to help manage complex collaborative research projects and introduces ideas, methods and tools that can be used both pre- and post-award. (3) Leadership Essentials Training: Leadership Essentials is a 5-day development programme for anyone who is a people manager. We run a Research-specific version of this programme (of up to 15 people) each term which is aimed at colleagues managing research teams. (4) We will establish a method to track completion rate of the above training programmes in Learning Management System. | (1) Double provision by December 2022. (2) Double provision by July 2023. (3) Double provision by December 2023. (4) Establishment of the method to track completion rate in years 1-2 | (1-4) years 1-2 | Director - HR Leadership & Management Development |  |  | New
EI5 | Ensure that excellent people management is championed throughout the organisation and embedded in institutional culture, through annual appraisals, transparent promotion criteria, and workload allocation | (1) Culture, Personal Development Reviews, promotion criteria and workload allocation will all be considered as part of the Research Culture Forum. (2) We currently run an annual Personal Development Review (PDR) process. Due to the pandemic, over the last 2 years we have taken a Personal Development Review light approach which has primarily been focused upon a wellbeing check-in. The new approach to Personal Development Review is being launched this year including a mandatory requirement to complete the Warwick Principles and Social Inclusion Moodle. The PDR process specfically asks about actions taken to promote diversity and inclusion. (3) Longer term (2023/24), one of the components of our People Strategy is Objectives Management. We will develop an approach to objectives management which will align the delivery of institutional strategic priorities to Department, Team and Individual objectives. Reviews will include a balance of 'What' is delivered and 'How' these are delivered which will be aligned to our culture and values. (4) Academic Promotion criteria are established and transparent (see EI3). At the beginning of the annual Academic Promotions cycle all staff are invited to attend a Promotions Explained event to talk through the process, framework and criteria. | (1) on-going. (2) Target - 70% compliance PDR in year 1. (3) Complete the review. (4) Mechanism in place to track participation of Research Staff in Academic Promotions Explained events in Year 1 | (1) on-going, (2) year 1, (3) years 2-3, (4) year 1 | Director of HR |  |  | New
EI6 | Seek to improve job security for researchers, for example through more effective redeployment processes and greater use of open-ended contracts, and report on progress | (1)This expectation is key to underpin the community and the commitment we wish to demonstrate to support researchers, but it is a complex situation which involves all stakeholders (funders etc.) and the need to recognise the balance between greater use of open-ended contracts and impact on opportunities for graduating PhDs. Issues are discussed at the Research Culture Forum and escalated to senior managers for further consideration. (2) We have recently updated our Redeployment processes so that redeployees are considered priority candidates for vacancies. (3) We will review our Fixed Term Contract policy to enhance the support for staff on fixed term contracts and transfer staff to indefinite contracts where there is every expectation that they will have a continuing role. (4) We will establish a mechanism to capture stats relevant to the above actions. | (1-3) Reduce number of researchers on fixed term contracts - piece of work to be done on establishing metrics and benchmarking (4) Establish a mechanism to measure number of Research staff that have: 1. been redeployed to other roles, 2. been recruited on indefinite contracts, 3. been moved from fixed term to indefinite contracts 4. fixed term contracts renewed 5. Fixed term contracts that have ended | years 1-2 | Provost, Registrar, Director of HR, Finance Director |  |  | New
EI7 | Consider researchers and their managers as key stakeholders within the institution and provide them with formal opportunities to engage with relevant organisational policy and decision-making | (1) Any researcher relevant policies to be presented for discussion at the Research Culture Forum and Research Staff Forum which will give opportunities for opinions to be raised and discussed, prior to formal approval of the policy/process, and thus researchers and their managers would feel more engaged with decision making and policy formation. (2) The representatives of researchers and managers of researchers will be invited to Research Culture Forum meetings. (3) Research staff represented on University Research Committee - plan to recruit a technician representative for this insitutional committee. (4) Review format and function of Research Staff Forum and how it can be used more effectively for staff engagement / informal consultation on policies. | (1-3) Representation of relevant groups in the Research Culture Forum and the Research Committee. (4) Measured by improved Research Staff Forum structure and reporting lines. | (1-3) year 1, (4) year 2 | (1) Chairs of Research Culture Forum and Research Staff Forum, (2) Chair of Research Culture Forum, (3) Chair of Research Committee, (4) Director of HR, PVC (Research) |  |  | New
Managers of researchers must:
EM1 | Undertake relevant training and development opportunities so that they can manage researchers effectively and fulfil their duty of care | (1) Promote and encourage participation in the Leadership Essentials training course for early and mid-career researchers. (2) Managers will take obligatory "Understanding Unconscious Bias" training. (See ECI3-5). (3) Managers will take obligatory ED&I training (see ECI4-2). (4) Ensure Managers of Researchers are fully aware of their duty of care - to be included in induction. | (1) Double provision by December 2022. (2) Obligatory for interview panel members - we aim for 90% of managers to have have taken the training. (3) All staff to undertake Warwick Principles and Social inclusion Moodle as part of Personal Development Review - target 70% compliance year 1. (4) 90% of PIs of externally funded grant to receive the induction. See ECM4. | (1-3) year 1, (4) years 1-2 | Director - HR Leadership & Management Development, Heads of Departments |  |  | New
EM2 | Familiarise themselves, and work in accordance with, relevant employment legislation and codes of practice, institutional policies, and the terms and conditions of grant funding | See ECM4. | 90% of PIs of externally funded grants to receive communication about the effects of the Concordat, relevant aspects of employment legislation and institutional policies, as a part of the post-award induction scheme to be developed in year 1 and 2. | years 1-2 | Director of Research & Impact Services, Director of HR, Directors of Research |  |  | New
EM3 | Commit to, and evidence, the inclusive, equitable and transparent recruitment, promotion and reward of researchers | See EI1 and EI3 - Ongoing end to end recruitment process review and recruitment training will be updated as required post recruitment review. | See EI1 |  | Director of HR, Heads of Departments |  |  | New
EM4 | Actively engage in regular constructive performance management with their researchers | See EI5 - Encourage all staff to take up Personal Development Reviews. | Completion of Personal Development Reviews - target 70% take up in year 1 | year 1 | Director of HR, Heads of Departments |  |  | New
EM5 | Engage with opportunities to contribute to relevant policy development within their institution | See EI7- Encourage managers of research staff to contribute to policies and engage with Research Staff Forum. | See EI7 |  | Chair of Research Staff Forum, Heads of Department |  |  | New
Researchers must:
ER1 | Ensure that they work in accordance with, institutional policies, procedures and employment legislation, as well as the requirements of their funder | See ECI2 and EM2. Induction has been redesigned to better fit the needs of new research staff. Including key policies and key messages from relevant institutional leaders. The induction includes; • Welcome message from Provost and PVC for Research • ‘Swift speeches’: committees and governance (R&IS), R&IS structure and departmental support (R&IS), HR elements tailored to researchers, IAS, library, WIE, RAS consultant (OD) • Information about the University's commitment to the principles of the Concordat • Networking • Followed up with PDF ‘cheat sheet’ showing list of key contacts for institution-wide services relevant to research staff, with short summary of each service’s offering as a reminder. | See ECI2 (3). The new approach has been successfully piloted with 75 research staff. Feedback was positive. Rollout of new induction for all research staff incorporating feedback September 2022. 70% completion rate year 1. | year 1 | Heads of Department |  |  | New
ER2 | Understand their reporting obligations and responsibilities | Researchers will learn about these in researchers induction programme and reinforced by Line Managers / Heads of Department. | See ECI2 (3), ER1 |  | Heads of Department |  |  | New
ER3 | Positively engage with performance management discussions and reviews with their managers | See EI5 - Researchers will learn about the process in the Researchers induction programme and reinforced by Line Managers / Heads of Department. There are dedicated webpages to provide support and resources for both reviewers and reviewees. | Personal Development Review completion rates 70% year 1 | year 1 | Heads of Department |  |  | New
ER4 | Recognise and act on their role as key stakeholders within their institution and the wider academic community | See ECI2. Researchers will be introduced to Research Culture Forum and Research Staff Forum in the researcher induction meeting. | See ER1 - Researchers to appreciate the benefits of joining in actively in University committees and be encouraged to volunteer when these opportunities arise. |  | Heads of Department |  |  | New
Professional and Career Development
Institutions must:
PCDI1 | Provide opportunities, structured support, encouragement and time for researchers to engage in a minimum of 10 days professional development pro rata per year, recognising that researchers will pursue careers across a wide range of employment sectors | (1) Workload Model Steering Group to consider how best to incorporate professional development allowance within workload model. (2) A new Early Career Researcher (ECR) Continuing Professional Development (CPD) Framework is under development. This is designed to integrate the needs of the Concordat, the Researcher Development Framework (RDF) and the Academic Promotions Pathway and enable ECRs to more readily evidence their professional development. This will form the basis of a proposed new probationary pathway for ECRs in the institution. (3) Develop a researcher development strategy which will outline the needs, benefits, opportunities and responsibilities for training for researchers at different career stages. This will outline the role of research line managers and Heads of Department etc to support and encourage the development of researchers. The strategy will outline: - A programme of development support covering key themes of career development, leadership, wellbeing - The co-creation of all materials - The development of the ECR CPD Framework based on 15 development day pa - Optional tools and portfolio templates will be provided to help record development. (4) Leadership and Management Development have recruited an Organisational Development consultant dedicated to Researcher Development. This will enable an institutional audit and gap analysis and the creation of dedicated innovative development opportunities for research staff. | (1) Measured by development of workload model and successful implementation of that model to incorporate 10 days of professional development. (2) Launch of CPD framework December 2022 (3) Development of a Researcher Development Strategy. November 2022 (4) Increased capacity to deliver tailored interventions for the research community May 2022 | (1) year 2 (2) Dec-22 (3) Nov-22 (4) May-22 | (1) Workload Model Steering Group and HR Engagement Director (to report) (2, 3) Director - HR Leadership & Management Development, Research Culture Forum lead with stakeholder input. (4) Director - HR Leadership & Management Development |  |  | New
PCDI2 | Provide training, structured support, and time for managers to engage in meaningful career development reviews with their researchers | (1) There are dedicated resources and training available to support both managers and researchers to engage in meaningful personal development reviews. (2) Consultation/survey with researchers to understand how they might better engage with Personal Development Reviews and then embed their suggestions into improving the process to suit their needs. (3) Existing provision in this area includes Research Career 5 series: A ‘mix-and-match’ set of five workshops aimed at early-career researchers. The five workshop titles in the series: • Enhancing Your Employability • Finding a Career that Fits You • Making an Impact in CVs and Applications • Making an Impact in Interviews • Managing Your Career | (1) Guidance, documentation and resources are provided via the Personal Development Review webpages. There are also Moodles for both reviewers and reviewees. (2) Review of existing provision August 2022 (3) A workshop series targeted to mid-career researchers. In recognition of the gap in career support for research active staff at various places in their career journeys, for Grade 7 or higher. Positive feedback roll out of workshop December 2022 | (1) Oct-22 (2) Aug-22 (3) Dec-22 | Director - HR Leadership & Management Development, Research Culture Forum lead with stakeholder input. |  |  | New
PCDI3 | Ensure that researchers have access to professional advice on career management, across a breadth of careers | (1) New careers support interventions will be developed with input from the Research community / and industry. Existing provision will be reviewed as part of the audit and gap analysis and the development of the ECR CPD framework. See PCDI1 (2,3,4) (2) Showcase a variety of careers journeys within and beyond academia | (1) See PCDI1 (2,3,4) (2) Showcase a variety of careers journeys within and beyond academic | (1) Mar-22 (2) Aug-22 | Director - HR Leadership & Management Development, with stakeholder input |  |  | New
PCDI4 | Provide researchers with opportunities, and time, to develop their research identity and broader leadership skills | (1) Research Identity is currently being considered and discussed within Careers 5 Series (see PCDI2) and through 1 to 1 coaching. The outcome of the work will form part of the plans for normalising research careers beyond academia. Researcher Identity is a key component in the development of the Researcher Development strategy and framework. (2) Forthcoming Leadership behaviour framework to be developed and specify requirements of research leadership; current provision reviewed as required. | (1) Improved induction. Increase in the numbers of 1 to 1 coaching. (2) Forthcoming Leadership behaviour framework to be developed and specify requirements of research leadership; current provision reviewed as required | (1) year 1 (2) year 2 | (1) Chair of Research Culture Forum (2) Director of HR |  |  | New
PCDI5 | Recognise that moving between, and working across, employment sectors can bring benefits to research and researchers, and support opportunities for researchers to experience this | (1) See PCDI4 (1) above. Plan for normalising ‘Research careers beyond academia’, including showcasing wider career options to the research community; especially in early years. (2) Warwick Innovations provide training for staff and students through: -Accredited PGCTS module for the STEM faculty in commercialisation (normally 24 researchers per year) -Innovation to Impact workshops (Wi2i) each term funded by EPSRC each typically 12 researchers in each. -Support PG students entering the national YES scheme. -Run ad hoc workshops for DTPs/DTCs – on innovation / commercialisation, to support wider career success. -VIBE workshops once a year (social sciences researchers) funded by ESRC, again typically 12 researchers -National Midlands ICURe scheme, funded by Innovate UK, twice a year for any UK researchers, typically 14 teams of 4 in each. | (1) See PCDI4 above (2) Measured by increased uptake of training; impact workshops and ad hoc workshops. Aim 25 % Research Staff participation in year 1 | (1) year 1 (2) year 1 | (1) Research Culture Forum to lead on development plan, input from community. (2) Warwick Innovations |  |  | New
PCDI6 | Monitor, and report on, the engagement of researchers and their managers with professional development activities, and researcher career development reviews | Personal Development Review conversations provide opportunity to discuss development. | See EM4 above |  | Heads of Department |  |  | New
Managers of researchers must:
PCDM1 | Engage in regular career development discussions with their researchers, including holding a career development review at least annually | Host an Induction day for Research managers, explaining the role and expectations in supporting development of others and importance of Personal Development Review meetings for career related discussions. | See EM4 above |  | Director - HR Leadership & Management Development, with stakeholder input from R&IS, HR, Depts |  |  | New
PCDM2 | Support researchers in exploring and preparing for a diversity of careers, for example, through the use of mentors and careers professionals, training, and secondments | (1) Promote coaching and mentoring to Research community . See PCD14 (2) Discussion with academic Heads of Department about role in encouraging and supporting researcher development. Research Culture Forum to consider how best to embed community wide learning within research culture. | (1) Improved communications on coaching and mentoring resulting in increased uptake. (2) Feedback from research community on development opportunities collated through the Research Culture Forum to demonstrate better engagement and impact. | Ongoing | Director - HR Leadership & Management Development, with stakeholder input from Heads of Department, Research Culture Forum |  |  | New
PCDM3 | Allocate a minimum of 10 days pro rata, per year, for their researchers to engage with professional development, supporting researchers to balance the delivery of their research and their own professional development | See PCDI1 (2,3,4) | See PCDI1 above. Measured by development of workload model and successful implementation of that model to incorporate 10 days of professional development. See also ECI1 (e) | year 1 | Workload Model Steering Group and HR Engagement Director (to report) |  |  | New
PCDM4 | Identify opportunities, and allow time (in addition to the 10 days professional development allowance), for their researchers to develop their research identity and broader leadership skills, and provide appropriate credit and recognition for their endeavours | We will establish a new post-award induction for PIs with external funding, and this induction will explain the importance of identifying opportunities and allowing time for their researchers to develop research identity and broader leadership skills. | 90% of the new PIs will receive the induction in year 2. See ECM-4. | year 2 | Director of Research & Impact Services |  |  | New
PCDM5 | Engage in leadership and management training to enhance their personal effectiveness, and to promote a positive attitude to professional development | EI4-3 | EI4-3 | EI4-3 | Learning and Development Manager, Organisational Development, with stakeholder input from Departments and Director of Research & Impact Services |  |  | New
Researchers must:
PCDR1 | Take ownership of their career, identifying opportunities to work towards career goals, including engaging in a minimum of 10 days professional development pro rata per year | See PCDM3 above. Engagement with provision outlined which will be promoted via the Research Staff Forum and continued messaging from induction onwards and reinforced at Personal Development Reviews and by Heads of Department. See also ECR CPD Framework. | See PCDM3 above |  | Departments, Research Staff Forum, Director - HR Leadership & Management Development |  |  | New
PCDR2 | Explore and prepare for a range of employment options across different sectors, such as by making use of mentors, careers professionals, training and secondments | See PCDM2 (1) and (2). Engagement with provision outlined which will be promoted via the Research Staff Forum and continued messaging from induction onwards and reinforced at Personal Development Reviews and by Heads of Department. | See PCDM2 (1) and (2) |  | Departments, Research Staff Forum, Director - HR Leadership & Management Development |  |  | New
PCDR3 | Maintain an up-to-date professional career development plan and build a portfolio of evidence demonstrating their experience, that can be used to support job applications | Development of a couple of different format portfolios for colleagues to store their development history. The portfolio design will enable easy cross referencing of experiences and activities against Warwick’s academic promotions criteria. The portfolios will also map to external job opportunities. | Development of a portfolios for colleagues to store their development history measured by usage of the career development plans. | 2022-12-01 | Director - HR Leadership & Management Development with stakeholder input |  |  | New
PCDR4 | Positively engage in career development reviews with their managers | Annual career conversations as part of the Personal Development Review, see also EI5-3. | Personal Development Review completion rate of 70% (EI5-2). see also EI5-3. | years 1-3 | Director of HR |  |  | New
PCDR5 | Seek out, and engage with, opportunities to develop their research identity and broader leadership skills | (1) The ECR CPD Framework will provide a range of opportunities see PCDI1 (2) (2) Research staff can already access leadership training – promote this and also wider promotion of institutional opportunities to demonstrate / build leadership experience | See PCDI (2) EI4 (4) | 2022-06-01 | Director - HR Leadership & Management Development, Heads of Department |  |  | New
PCDR6 | Consider opportunities to develop their awareness and experience of the wider research system through, for example, knowledge exchange, policy development, public engagement and commercialisation | (1) The Warwick Institute of Engagement will continue to offer a range of high quality training/ educative resources to support and prepare research staff and students for external / public engagement work. Their current offering includes: Introduction to Engagement – Moodle Course – Open to staff and students Storytelling for Research Online Course (externally run). Online Engagement Training They have established a learning circle to identify, scope and design new materials. (2) "Innovation to Impact" (Warwick i2i) is a development programme for Early Career Researchers (ECRs), PhD and masters students run by Warwick Innovations as part of the DeepTech Innovation Centre, offering the opportunity to develop commercial skills. We will promote this to researchers. | (1) See PCMD4 above. (2) We will establish a method to obtain stats regarding the research staff participation in collaboration with Warwick Institute for Engagement and Warwick Innovations. | (2) year 1-2 | (1) Director of the Warwick Institute of Engagement, (2) Warwick Innovations. |  |  | New
* The Concordat defines researchers as individuals whose primary responsibility is to conduct research and who are employed specifically for this purpose by a higher education institution or research institute. The primary audience is research staff, e.g. postdoctoral researchers, research fellows, research assistants. The Concordat encourages institutions to include other groups who actively engage in research as beneficiaries of their Concordat action plan. These could be postgraduate researchers; staff on teaching and research, or teaching contracts; clinicians; professional support staff; technicians.