University of Warwick – HR Excellence in Research & HR Excellence Action Plan

6 Year Review Action Plan – January 2019 – December 2020

To support the implementation of The Concordat to Support the Career Development of Researchers*

*Research Active Staff (RAS) include Research and Teaching Focussed, Research Focussed and Teaching Focussed Staff – Learning and Development Centre (LDC) have responsibility for staff learning and development and Student Career and Skills have responsibility for Research Students.  LDC actively promote the resources/courses mentioned throughout this action plan to all RAS in the monthly RAS Newsletter.

Many actions on the 2016-2018 Action Plan, are continued within this action plan as they are still relevant and will be continuously reviewed and reported on.  NEW actions are listed as NEW in the Action Number Column

The next two years will include the implementation of the HR and Learning Management System which will allow staff to take ownership of their learning and development and continuing to enhance the support the HR Excellence in Research accreditation.

VISION: Warwick’s commitment to research is that it will be internationally leading, impactful, and provocative.  It will change the world, making lives healthier, safer, more resilient and more enriched.  We will undertake through our research and its impact to produce transformative solutions to the multidisciplinary global challenges both of today and of the future.

Our research will maintain its foundations in disciplinary and interdisciplinary strengths, and will take place in innovative spaces that will define the frontiers of knowledge.  We will work in partnership with key collaborators from academia and industry regionally, nationally and around the world.

| ACTION NUMBER | KEY PRINCIPLES WITH DEFINED ACTIONS | ISSUE TO BE ADDRESSED | SUCCESS CRITERIA | RESPONSIBILITY FOR ACTION | TIMESCALE |
| --- | --- | --- | --- | --- | --- |
| - RECRUITMENT AND SELECTION |  |  |  |  |  |
| PRINCIPLE 1: Recognition of the importance of recruiting, selecting and retaining RAS with the highest potential to achieve excellence in research |  |  |  |  |  |
| 1.1 Continuation | An efficient, reliable and informed recruitment process to enable tracking of RAS applicants from application through to appointment. | The new HR Management System due to be launched in 2018 was delayed until early 2019 and will provide detailed recruitment/selection/retention information to inform the University and departments of the workforce profile with regard to RAS roles. With the data this can lead to streamlining and improved processes/policies and procedures. | Improved RAS recruitment/selection and retention through enhanced data analytics facilitating informed decision making. | HR Recruitment Team HR Engagement Team | Post implementation of new HR Management System – 1 January 2019 onwards. |
| 1.2 NEW | Ensure that recruitment supports the University strategy, providing information and improvement in diversity data by understanding the impact of internal and external changes for RAS. | Recruitment reflects local, national and international demographics. Highlighting data on protected characteristics. Highlighting and improving gender and race demographic distribution in relation to Charter Marks. | Improved recruitment of a diverse workforce. Metrics: Annual Workforce Equality Monitoring Report to report on statistical trends to measure increase/decrease of personal characteristics of staff. | HR Recruitment Team HR Engagement Team | 1 January 2019 onwards |
| 1.3 Continuation | Improve the diversity of recruitment and selection panels and ensure that Chair of Recruitment Panels training is carried out every three years and that new Chairs receive the same training. | Monitoring the composition of diversity of recruitment panels. Ensure new Chairs of Panels undertake training and others refresh training every 3 years. | Diversity of recruitment panels. Number of people trained and number of people retrained. | HR Recruitment Team Departments LDC | 1 January 2019 onwards and monitored annually |
| 1.4 Continuation | Increase staff disclosure rates for all protected characteristics for RAS. | Improved and timely communication to new starters on benefits for disclosing personal information. Encouragement for existing staff to take the opportunity to update personal information when the new HR Management system is launched in 2019. Timely communication and agreement with staff around recording and disclosure. | Increased disclosure rates which are reported in the Annual Equality Monitoring Report and discussed at strategic committees. Data provided. | HR Systems Team HR Engagement Team Equality, Diversity & Inclusion Team (ED&I) Departments | 1 January 2019 onwards |
| 1.5 Continuation | Unconscious Bias training for members on recruitment panels. | Encourage all staff, especially with recruitment responsibilities to take the Unconscious Bias Moodle and/or the face to face Unconscious Bias Training Review and offer a new shortened Unconscious Bias refresher moodle. | Annual Increase of % of staff involved in recruitment and who have undertaken the Unconscious Bias Moodle and/or training workshops. | HR Engagement Team LDC | 1 January 2019 onwards |
| 1.6 NEW | Warwick training opportunities for RAS staff | See Sections 3 and 4. Training and development opportunities of new RAS starters, e.g. Research Data Management, Research Integrity and Respect and Dignity at Warwick. | Reporting the number of RAS trained providing both qualitative and quantitative data. | LDC | 1 January 2019 onwards |
| 1.7 NEW | Investigate recruitment processes to ensure a good pipeline of entrants at FA6, FA7 and FA8 RAS. | Examine recruitment processes to ensure a good pipeline of entrants at FA6, FA7 and FA8 for RAS. | Annual increase in the numbers of RAS at FA6, FA7 and FA8 being recruited. Reporting data on gender split, ethnicity and grade and job titles. | Departmental Recruitment Teams HR Engagement Team | 1 January 2019 onwards |
| 1.8 NEW | Investigate progression routes at FA6, FA7 and FA8 RAS. | Progression routes for RAS at FA6, FA7 and FA8 who can then benefit from the implementation of the new academic promotions process from the 2018/19. | Annual increase in the numbers of RAS at FA6, FA7 and FA8 being promoted. Reporting data on gender split, ethnicity and grade and job titles. | HR Academic Processes Team HR Engagement Team | 1 January 2019 onwards |
| 1.9 NEW | Communication and guidance on the Promotion criteria for research active staff: Research and teaching Research focussed Teaching focussed | To proactively promote and communicate the new Warwick promotions process to ensure staff are aware of the process and its timeframe, criteria and the required paperwork, so that staff can prepare themselves for promotion. | Increased numbers of successful promotions. | HR Academic Processes Team | 1 January 2019 onwards |
| 1.10 Continuation | Personal and Development Reviews (PDRs) for RAS. | University to continue to provide appropriate L&D training on PDRs, and to update, monitor uptake of PDRs by RAS. To continue to embed quality expectations with existing RAS through objective setting including during PDRs, and to give RAS an opportunity to reflect on past performance as well as to look forward to new objectives. Measuring and monitoring the data and impact of PDRs to facilitate improvements for RAS. | Annual increase in the number of RAS participating in PDRs. | Departments Individuals LDC | 1 January 2019 onwards |
| 1.11 NEW | All RAS have allocated time for career development activities | To address the issue that RAS employed on fixed term contracts and who are funded by external contracts (other than Research Councils) are not explicitly afforded time to engage with career development activities. | That all RAS, regardless of funder are given time for career development activities. Sharing case studies and/or best practice. | R&IS Heads of Departments Research Staff Forum | 1 January 2019 onwards |
| B. RECOGNITION AND VALUE |  |  |  |  |  |
| PRINCIPLE 2: RAS are recognised and valued by their employment organisation as an essential part of their organisation’s human resources and a key component of their overall strategy to develop and deliver world-class research. |  |  |  |  |  |
| 2.1 NEW | Encourage and support RAS promotion submissions, sharing departmental best practice and demonstrate promotion routes, by informal opportunity of networking. | Share case studies from individuals who have successfully applied for promotion and to promote these case studies on the LDC and/or LDC web pages to demonstrate different job roles and routes. Noting that case studies may need to be anonymised. Providing one to one support and opportunities for local funded networks or promotion support mentor pairings. | Promotion of successful case studies from different individuals to encourage and give confidence to others seeking promotion. Metrics on one to one support and/or promotion pairings. | HR Academic Processes Team Head of Departments LDC | 1 January 2019 onwards |
| 2.2 Continuation | Promotion of support available for RAS taking maternity/adoption/paternity and any other long term leave (i.e. long term sickness absence or secondment). | Promote to RAS taking maternity/adoption/paternity and other long term leave what support is in place for them (including the availability of mentors) to support them with the transition back into the workplace. Continue to promote the option of ‘Keeping in Touch’ (KIT) Days. Collate feedback, sharing benefits and considering recommendations. | Informed staff. Increase of uptake of mentors to assist with the transition back into the workplace. Number of RAS taking up the opportunity of KIT days. | HR Advisers | 1 January 2019 onwards |
| 2.3 Continuation | Encourage positive attitudes towards flexible working for RAS. | Improve communications to encourage positive attitudes towards flexible working, by providing case studies for the web pages to demonstrate the benefits to both the individual and the University on flexible working. | More consistency with how flexible working requests are dealt with across the university. | HR Advisers Departmental Administrators | 1 January 2019 onwards |
| 2.4 Continuation | Research and Impact Services (R&IS) to work with academic departments to inform on research opportunities and provide learning and development support for RAS. | R&IS to work with academic departments to inform RAS of fellowships and funding opportunities. Recording by R&IS Research Strategy and Development Managers (RSDM) and Officers (RSDO) training, learning and development and one to one support provided; number of applications and success rates. | Increased number of Fellowship applications/success Metrics on one to one support, learning and development, number of applications and success rates. | R&IS RSDMs and RSDOs Departments | 1 January 2019 onwards |
| C. SUPPORT AND CAREER DEVELOPMENT |  |  |  |  |  |
| PRINCIPLE 3: RAS are equipped and supported to be adaptable and flexible in an increasingly diverse, mobile, global research environment |  |  |  |  |  |
| 3.1 Continuation | Career support initiatives are innovative, fit for purpose and communicated to all RAS (also applicable to Principle 4). | Continuously review University support structures to ensure the best possible support for researchers at all career levels, by consulting with the Research Staff Forum and ensuring appropriate communication channels across campus. Providing a range of one to one/face to face/online resources or workshops for RAS. | Increased numbers of RAS taking up career support training. Statistics provided Impact Report and/or Case Studies. Improved career and general support resources which RAs can access. | LDC Departments CSS | 1 January 2019 onwards |
| 3.2 Continuation | Development of case studies of RAS profiles from Warwick’s research community. | Career paths for researchers highlighted and showcasing different roles and grades. | Case studies available on the web as well as information provided on the LDC’s website. Feedback from RAS. | LDC with the Research Staff Forum | 1 January 2019 onwards |
| 3.3 Continuation | Provision of a range of Leadership and Management Development Opportunities for RAS (also applicable to Principle 4). | The University to continue to offer a range of Leadership and Management Development courses to equip RAS with key skills in leading/managing teams to meet project requirements. | Uptake on leadership and management programmes. Feedback from attendees. Annual Impact Report Data on Leadership and Management Development Opportunities and support provided and reported on. | LDC | 1 January 2019 onwards |
| 3.4 Continuation | Provision of a range of career development opportunities for RAS (also applicable to Principle 4). | The University to continue to offer a range of career development support, through workshops, courses and one to ones, to equip RAS with key skills to key transferable skills for their career development. | Uptake on career development provision, including feedback from attendees. Data on one to one support provided and reported on. | LDC | 1 January 2019 onwards |
| 3.5 Continuation | Fit for purpose Personal Development Reviews (PDRs) for RAS (also applicable to Principle 4). | Personal Development Reviews to enable discussions about career development/progression between RAS and their managers. | Increased uptake of PDRs by RAS per job role. | LDC PDR Sub-PULSE Group Departments | 2019/2020 academic year |
| 3.6 Continuation | Provision of good coaching and mentoring schemes for RAS (also applicable to Principle 4). | Encourage participation by RAS in coaching and mentoring schemes available through LDC (general schemes, HoDs provision, WLP). Providing a range of learning and development initiatives, i.e. on-line and face to face. | Feedback from attendees to identify whether the schemes have aided RAS in identifying and progressing their career path. Data on participation rates. Coaching and Mentoring Scheme – statistics RAS 1:1 Support – Impact Report | LDC | 1 January 2019 onwards |
| 3.7 Continuation | Provision of a range of courses to enable RAS to develop transferable skills to enhance their career development for a diverse, mobile global research environment (also applicable to Principle 4). | Development and delivery of a range of courses to develop transferable skills, delivered through embedded learning and development, in order to stay competitive in both internal and external job markets. | Provision and take up of a number of courses to aid RAS development. | LDC | 1 January 2019 onwards |
| 3.8 Continuation | Provision of Research Staff Forum as a supportive networking group (also applicable to Principle 4). | Continue to ensure that all new RAS are invited to the Research Staff Forum to engage and network with other RAS and to act as a consultation mechanism on research initiatives. To increase the membership and include RAS network leads. | Continued participation by RAS in the forum. | Departments and HR Recruitment Team Research Staff Forum LDC | 1 January 2019 onwards |
| 3.9 Continuation | Ensure that research students can access professional, independent advice on career management. | Provision of clear career guidance to all taught and research students, as well as application advice, mock interviews and workshops. Following feedback from a student survey in 2018 we will: - Increasing ‘hub & spoke’ delivery, in terms of both physical space and services offered centrally/in collaboration with departments; - Reviewing how we communicate our services to students; - Broadening our offer, both in scope (e.g . range of employers) and scalability (e.g. online services); - Reviewing academic, personal and professional skills needs and provision across the University for UG and PGT students. | Feedback from students Case studies Employability statistics Data on number of courses, one to ones, number of attendees and the different types of workshops that are offered. | Student Careers and Skills | 1 January 2019 onwards |
| 3.10 Continuation | Ensure that RAS can access professional, independent advice on career management (also applicable to Principle 4). | Provision of clear career guidance to all RAS, as well as application advice, mock interviews and workshops. Provision of learning and development support via one to ones, workshops and coaching. | Feedback from RAS Case studies and metrics | LDC | 1 January 2019 onwards |
| 3.11 Continuation | To broaden the ‘How Warwick Works’ Shadowing Programme for RAS (also applicable to Principle 4). | To continue to develop and promote the Shadowing Programme to enable more RAS to participate and gain leadership skills. | Ensure appropriate % of engagement of RAS participation rates Tracking succession data and impact. Data and metrics | LDC Senior Management | 1 January 2019 onwards |
| PRINCIPLE 4: The importance of RAS personal and career development, and lifelong learning, is clearly recognised and promoted at all stages of their career. |  |  |  |  |  |
| 4.1 Continuation | Development of opportunities for RAS on: Outreach Impact Public engagement. | Supporting RAS to increase their awareness and develop initiatives for sharing impact and/or public engagement opportunities. Measuring and monitoring impact. | Sharing best practice Data and metrics | Reported by: Outreach team R&IS/Impact Officers Public Engagement Team Regional and Business Engagement | 1 January 2019 onwards |
| 4.2 Continuation | Provision of a range of Leadership and Management Development opportunities for RAS personal and career development. (also applicable to Principle 3). | The University to offer a range of Leadership and Management Development courses to equip RAS with key skills in leading/managing teams to meet project requirements. | Uptake on leadership and management programmes. Feedback from attendees. Annual Impact Report | LDC | 1 January 2019 onwards |
| 4.3 Continuation | Develop and support RAS networks enabling personal and/or career development. | Continue to support RAS networks to assist with career and personal development, thereby building a research community and to meet university strategic objectives. | Annual Impact Report Number of networks supported. | LDC | 1 January 2019 onwards |
| 4.4 New | Develop dedicated support for RAS (specifically post-docs and research only staff) to work towards Associate Fellowship or Fellowship of the HEA as appropriate. | A growing number of post-doctoral staff are keen to enhance their teaching skills and achieve recognition for this through HEA fellowship – there has been growing demand for support particularly within the Science Faculty. | Number of successful HEA submissions. | LDC (T&L) | 2020 |
| D. RAS RESPONSIBILITIES |  |  |  |  |  |
| PRINCIPLE 5: Individual RAS share the responsibility for and need to pro-actively engage in their own personal and career development, and lifelong learning |  |  |  |  |  |
| 5.1 Continuation | Focus on the relationships between research and excellence, education, innovation and capacity building for RAS. | To bring together universities that have demonstrable excellence in education, research and policy formation from across Europe to collaborate on the creation of innovative solutions to some of Europe’s most intractable scientific and social challenges. Sharing practice and showcasing various initiatives. | Demonstration of excellence in educating, research and policy formation. Discovery of innovative solutions to scientific and social challenges. Metrics | PVC Research PVC for External Engagement | 1 January 2019 onwards |
| 5.2 Continuation | RAS to be familiar and to be able to map their development to competency framework, e.g. researcher development framework (RDF) or the Concordat to support the career development of researchers (also for Principles 3 and 4). | To promote the RDF/Concordat to RAS staff by signposting and embedding the competencies in learning and development provision. | Increased awareness and ensuring our provision is mapped to research competency framework | LDC R&IS and Research Committee Departments RAS individuals | 1 January 2019 onwards |
| 5.3 Continuation | Publicise and encourage engagement with Warwick Ventures and the Regional and Business Engagement Team by RAS. | Develop mechanisms for identifying, developing and supporting research leaders to head up new large-scale research initiatives and funding applications. Promotion of the initiatives through case studies/showcasing opportunities. Measuring and monitoring impact. | Increased number of research initiatives and funding applications/successes Metrics | Warwick Ventures Regional Business and Engagement Team R&IS | 1 January 2019 onwards |
| 5.4 Continuation | Generate impact and a commercial return from research from RAS where applicable. | Continue to provide assistance with generating impact and a commercial return from research. Warwick will be hosting the British Science Festival 2019, in partnership with The British Science Association. This is one of Europe’s longest-established science festivals, and is aimed at an adult audience with a broad but non specialist interest in science. RAS from Warwick and across the UK, will present, discuss and debate cutting-edge science from across the scientific disciplines. | Increase in commercial return and reputation of Warwick RAS | Warwick Ventures R&IS | 1 January 2019 onwards |
| E. EQUALITY, DIVERSITY AND INCLUSION (ED&I) |  |  |  |  |  |
| PRINCIPLE 6: ED&I must be promoted in all aspects of the recruitment and career management of RAS |  |  |  |  |  |
| 6.1 Continuation | Ensure that our strategic partner institutions have at least the same ED&I standards to match Warwick’s. | Formalise a process for assessing the values and ED&I standards of partner institutions where our RAS and students go to work on our behalf where we have members of university staff. | Warwick RAS are treated with the same standards at partner institutions as they are at Warwick. | Departments/Individuals Equality and Diversity Committee | 1 January 2019 onwards |
| 6.2 Continuation | Enhance Equality Objectives 2016-2020 in line with University strategy. | Create a measurable objective on Equality and Diversity that will be embedded into all six goals of the University Strategic Plan. | All six goals of the University Strategy to have Equality and Diversity elements. | The Provost (as Chair of the Equality and Diversity Committee) | 1 January 2019 for one year until Equality Objectives reviewed again in May 2020. |
| 6.3 Continuation | All ED&I papers are above the line at University meetings. | Ensure that ED&I appears as an “above the line” agenda item at all relevant university committees, including Senate and Council. | Council and Senate membership to have an appreciation of all equality and diversity activities. Continuing implementation of this action. | The Provost (as Chair of the Equality and Diversity Committee) | 1 January 2019 onwards |
| 6.4 Continuation | By continuing participation in Charter Marks we aim to embed ED&I. | Ensure ED&I is embedded into all policies and procedures and training and development, i.e. examples/scenarios. Provision of resources and participation from institutional representatives to the Charters | Continued success in Charter Mark submissions. Metrics | ED&I HR LDC | 1 January 2019 onwards |
| F. IMPLEMENTATION AND REVIEW |  |  |  |  |  |
| PRINCIPLE 7: The sector and all stakeholders will undertake regular and collective review of their progress in strengthening the attractiveness and sustainability of research careers in the UK |  |  |  |  |  |
| 7.1 NEW | Highlighting Warwick’s University strategy as well as the research strategy. | Alignment and promotion of RAS career opportunities. | Awareness and support of strategy initiatives affecting RAS. | PVC Research Research Committee | 1 January 2019 onwards |
| 7.2 Continuation | Engagement and participation of internal stakeholders who support and develop RAS. | Monitoring, evaluating and improving the provision for research active staff in a dynamic and demanding research environment. | Successful collaborations Showcasing Profile Warwick | PVC Research Research Committee HR R&IS Institute of Advanced Studies Institute of Advanced Teaching and Learning Warwick Ventures Library LDC | 1 January 2019 onwards |
| 7.3 Continuation | Engagement and participation of external stakeholders who support and develop RAS. | Monitoring, evaluating and improving the provision for RAS in a dynamic and demanding research environment. | Successful collaborations Warwick RAS profiling opportunities. | Midlands Researcher Development Forum Funding Bodies Appropriate regional and national research related stakeholders | 1 January 2019 onwards |