University of Warwick – HR Excellence in Research and HR Excellence Action Plan

Progress against the 4 Year Action Plan – January 2017 – December 2018

To support the implementation of The Concordat to Support the Career Development of Researchers*

*Research Active Staff include Research, Teaching and Academic Staff – LDC responsibility for learning and development and for Research Students – Student Careers and Skills

** As a result of the new academic promotion process (18/19 academic year), Reasearch Active Staff titles have now changed to Research-focussed, Teaching-focussed and Research and Teaching Contract

NOTE: Progress against this action plan is monitored and up-dated annually and shared with the Research Staff Forum for comment, discussion and feedback, this is then shared with the Research Committee for oversight, support and strategic input.  Timescales will be amended accordingly with progress, so it should be noted that currently the plan only comments on activity up until December 2018, after which the reviews will take place and timescales updated as appropriately to the action plan from January 2019.

| ACTION NUMBER | KEY PRINCIPLES WITH DEFINED ACTIONS | ISSUED TO BE ADDRESSED | PROGRESS | SUCCESS CRITERIA | RESPONSIBILITY FOR ACTION | TIMESCALE |
| --- | --- | --- | --- | --- | --- | --- |
| A. RECRUITMENT AND SELECTION |  |  |  |  |  |  |
| Principle 1: Recognition of the importance of recruiting, selecting and retaining researchers with the highest potential to achieve excellence in research |  |  |  |  |  |  |
| 1.1 NEW | Fast, reliable and informed recruitment process to enable tracking of applicants from application through to appointment. | The new HR Management System** (which becomes operational in 2018) to provide detailed recruitment/selection/ retention information to inform the University and departments of the workforce profile. With the data this can lead to streamlining and improved processes/policies and procedures. | Current HR system continues to provide recruitment data to inform the Equality Monitoring Annual Report. The launch of the new HR System has been delayed until early 2019 but moving forward will provide more detailed analysis of staff data. The table below shows recruitment data as published in the annual Equality Monitoring Report 2017/2018 produced from data as at 01.08.2018 for research and teaching, research focussed and teaching focussed staff. Recruitment data is also analysed by different protected characteristics to ensure that the University continues to attract and employ a diverse workforce. The University recognises that more work needs to be done to attract staff from under-represented groups but is pleased to see that some groups are seeing an increase in representation, for example, we have seen an overall increase in the number of BAME employees from 734 in 2013/14 to 1059 in 2017/18 from a total staff population of 6633. To further communicate the Equality Monitoring Annual Report, booklets are produced entitled ‘Know Your Numbers’, which portrays Warwick’s statistics in infographics. This booklet is issued to HoDs, and at other strategic committees and is available at all ED&I events and welcome meetings. It is also available to access/download from the ED&I website. The University has successfully renewed its Silver Institutional Athena Swan Charter Mark in 2018, which is heavily focused on data collection and analysis and therefore the ability to produce data reports has been evident in this successful submission. Recruitment statistics for research focussed, teaching focussed and research and teaching staff – 2017/18 Female; Male; Prefer not to disclose. Applied; Shortlisted; Offered; Applied; Shortlisted; Offered; Applied; Shortlisted; Offered. Teaching & Research; Level 6; 45; 9; 1; 85; 9; 1; 4; 0; 0. Level 7; 840; 102; 18; 1823; 150; 37; 113; 7; 0. Level 8; 59; 3; 0; 171; 22; 1; 5; 1; 0. Level 9; 95; 7; 0; 241; 7; 1; 13; 1; 0. Research Focussed; KTP*; 3; 1; 0; 8; 3; 0; -; -; -. Level 4; 4; 2; 1; 5; 1; 0; -; -; -. Level 5; 264; 55; 10; 118; 18; 2; 3; 0; 0. Level 6; 804; 182; 32; 1900; 359; 69; 107; 14; 3. Level 7; 61; 11; 2; 144; 26; 7; 10; 0; 0. Level 8; -; -; -; 4; 1; 1; -; -; -. No Grade**; 106; 13; 4; 146; 8; 5; 8; 0; 0. Other; 18; 4; 0; 54; 7; 3; -; -; -. Teaching Focussed; Level 5; 33; 4; 1; 17; 4; 0; -; -; -. Level 6; 395; 78; 15; 457; 53; 5; 29; 3; 0. Level 7; 180; 42; 11; 227; 49; 5; 10; 4; 0. Level 8; 45; 9; 3; 94; 16; 2; 5; 1; 1. No Grade**; 6; 0; 0; 32; 4; 1; -; -; -. Total; 2958; 522; 98; 5526; 737; 140; 307; 31; 4. *Knowledge Transfer Partnerships **No Grade stated | Improved recruitment/selection and retention through improved data analytics facilitating Informed decision making and reporting for appropriate Charter Marks. | HR Recruitment Team HR Engagement Team | Post implementation of new HR Management System January 2018. |
| 1.2 NEW | Ensure the recruitment strategy is informed by diversity data by understanding the impact of internal and external changes. | Recruitment reflects local as well as national demographics. Highlighting data on protected characteristics Highlighting and improving gender and race demographics distribution in relation to Charter Marks. | Equality Monitoring Annual Report produced and presented to strategic committees annually in October to inform on diversity data of workforce (based on previous year’s data so this data refers to 2017/18). Key data: Total number of all staff: 6,633 with 5,301 working on indefinite contracts and 1,332 working on fixed term contracts; Gender Split among staff is : Males : 47%; Females : 53%; Number of disabled staff employed remains static, representing 2.4% of female staff and 2% of male staff declaring a disability; the University employs 1059 staff from a BAME background. The University data is benchmarked against the local and sector population. The Table below shows the breakdown according to thef research active staff contracts. Contract type; Teaching and Research; Research Focussed; Teaching Focussed; Clinical; Total. FT; FTC; 26; 551; 60; 14; 651. OEC; 952; 93; 296; 28; 1369. PT; FTC; 26; 103; 45; 14; 188. OEC; 81; 22; 100; 27; 230. Total; 1085; 769; 501; 83; 2438. Staff Networks exist to support staff with protected characteristics as well as groups that support staff who are carers and working parents. Staff Networks are: BAME; Disability, LGBTUA+, Working Parents and Carers. The Staff Networks are promoted to new members of staff on the University’s Recruitment web pages. All new members of staff receive a welcome letter and a Diversity and Inclusion Guidance booklet. The ED&I team also have a presence at the University Welcome meetings and more recently is offering an ED&I Induction meeting to new staff. Warwick has a multi-faith chaplaincy who offers a welcome to both staff and students of all faiths and none. Some departments are using statements such as ‘applications welcome from females (or other protected characteristics), as they are underrepresented in this area’. The Institutional Athena Silver award logo can also be used on adverts to encourage more applications from all genders. In line with a recruitment and Working at Warwick web overhaul in May 2016, the following statement is included on the applicant information job page: ‘We will consider applications for employment on a part-time or other flexible working basis, even where a position is advertised as full-time, unless there are operational or other objective reasons why it is not possible to do so’. There is also a statement welcoming applications from those individuals who may identify with different protected characteristics. The ED&I team produced a booklet ‘Working, learning, living’, which is a booklet profiling a number of Warwick staff who have shared their daily work/life balance responsibilities and how they make use of the flexible working options available at Warwick. Analysis of trends will be undertaken to inform recruitment strategy in line with our Gender, Race, Disability, Sexual Orientation and Religion and Belief work. All data will be benchmarked against local/sector population. The University is developing regular and active channels of communication/ information sharing with local community centres and is routinely represented at local job fairs. With the recruitment of a Social Inclusion Director, more engagement will be initiatied within the West Midlands community. Ethnicity is a key diversity indicator in recruitment for senior roles and therefore we will ensure that Search Firms used by the University have strategies to support this. A number of informative booklets have been produced to support staff: - ‘Working, learning, living’, which is a booklet profiling a number of Warwick staff who have shared their daily work/life balance responsibilities and how they make use of the flexible working options available at Warwick, 2017. - Trans Awareness Guide, a guide to inform and raise awareness on trans people, 2017. - ‘The most important things people want you to know about Disability & Caring’, a book of quotes from university staff and students who are either disabled or have caring responsibilities, 2018. - ‘Pronouns: Let’s Get it Right’, booklet to raise awareness around the use of pronouns, 2018 - Guidance and Support for Disabled Staff, 2018 - Checklist for Line Managers of Disabled Staff, 2018 - Frequently Asked Questions for Disabled Candidates and Prospective Employees, 2018 | An improved diverse workforce by analytics and benchmarking. | HR Recruitment Team HR Engagement Team | Annually |
| 1.3 NEW | Improve the diversity of recruitment and selection panels and ensure that Chair of Recruitment Panels training is carried out every three years and that new Chairs receive the same training. | Monitoring the composition of diversity of Recruitment panels. | Chairs of Recruitment Panels have all received training on Equality and Diversity and Unconscious Bias and all members of staff involved in recruitment encouraged to take the ‘Diversity in the Workplace’ as a precursor to the ‘Recruitment and Selection’ module and ‘Unconscious Bias’ moodle. A ‘How to Guide’ has been created to assist panel chairs in creating the right panel composition and ensuring fair selection methods are used throughout the process. As part of the Chair of Panels Recruitment and Selection training, Chairs have a responsibility to ensure that recruitment panel compositions are diverse, with the appropriate gender balance and required skills. This information is documented for panel chairs, recruiting departments and panel members in various formats including checklists as helpful prompts. Panellists are expected to refresh their recruitment and equality* training every 3 years. * Refers to equality, diversity, inclusion as well as respect training. | Diversity of recruitment panels. | HR Recruitment Team Departments | Commenced 2017. Annual monitoring July 2017 and July 2018 |
| 1.4 NEW | Increase staff disclosure rates for all protected characteristics. | Improved and timely communication to new starters on benefits for disclosing personal information. Encouragement for existing staff to take the opportunity to update personal information when the new HR Management system is launched. Timely communication and agreement with staff around recording and disclosure. | Numerous communications and events have been published across the University to help raise awareness and to inform staff of the different protected characteristics and what support is available to staff and students that identify with any of those protected characteristics. In the 2017/18 Equality Monitoring Annual Report, the overall number of staff disclosing a disability has remained fairly static and it is hoped that with the launch of the new HR system in 2019 that there will be an increase in the number of staff who will feel more comfortable in disclosing their characteristics. Going forward with the new HR system, we will be able to provide a breakdown of statistics for research active staff only in relation to protected characteristics. WORKFORCE PROFILE (data taken at 01.08.2018) TOTAL NUMBER OF EMPLOYEES (All Staff Categories) Warwick's Staff Population has Grown by over 970 Staff in the Past 4 Years Of the overall staff population of 6633 staff, 2438 are on research and teaching, Research Focussed, Teaching Focussed and clinical grades (921 females and 1517 males). DISABILITY The University has 280 staff who have declared a disability as at 1 August 2018, making up 4.2% of employees, compared to the sector average of 4.72%. However only 76 of the 280 staff are on research and teaching, research focussed and teaching focussed contracts. The number of staff disclosing a disability has remained fairly static and it is hoped that with the launch of the new HR system early in 2019 and the increased number of events/talks on different disabilities and caring that staff will feel encouraged and empowered to disclose any protected characteristics they may have and help the University to achieve our 5% target. In April 2018, the University commenced work on self-assessing against the Business Disability Forum Standards with a view to creating a plan of actions to improve processes/procedures for staff/students with disabilities. Again through the communication of this work and consultation with staff, it is hoped that more research active staff will feel empowered to disclose their disabilities, in order that the appropriate reasonable adjustments can be put in place for them. RACE The University employs 1059 employees with a BAME background (988 in 2017) which is equivalent to 16% of the total employee population. This is the highest proportion of BAME employees that the University has employed to date. SEXUAL ORIENTATION Sexual orientation and religion and belief are fairly new data collections, only starting in September 2015. Whilst the data is still in its infancy, there has already been a slight increase in disclosure rates. Sexual orientation; 2015/16; 2016/17; 2017/18. No. employees; % of total; No. employees; % of total; No. employees; % of total. Bisexual; 45; 0.8%; 51; 0.9%; 66; 1%. Gay man; 43; 0.8%; 44; 0.8%; 56; 0.8%. Gay woman/ lesbian; 20; 0.4%; 24; 0.4%; 36; 0.5%. Heterosexual; 2940; 52.6%; 3238; 55.5%; 3720; 56.1%. Other; 27; 0.5%; 32; 0.5%; 32; 0.5%. Unknown/ Prefer not to say; 2511; 45%; 2447; 41.9%; 2723; 41.1%. In October 2017, a Trans awareness Guide was also produced and is circulated at events throughout the year. Religion; 2015/16; 2016/17; 2017/18. No. employees; % of total; No. employees; % of total; No. employees; % of total. Buddhist; 54; 1%; 54; 0.9%; 53; 0.8%. Christian; 1381; 24.7%; 1477; 25.3%; 1635; 24.6%. Hindu; 67; 1.2%; 85; 1.5%; 102; 1.5%. Jewish; 11; 0.2%; 13; 0.2%; 13; 0.2%. Muslim; 88; 1.6%; 105; 1.8%; 131; 2%. Sikh; 82; 1.5%; 99; 1.7%; 96; 1.4%. Spiritual; 35; 0.6%; 38; 0.7%; 44; 0.7%. Any other religion or belief; 66; 1.2%; 70; 1.2%; 77; 1.2%. Unknown/No religion; 3802; 68.1%; 3895; 66.7%; 4482*; 67.6%. Religion and Belief disclosure rates have improved since 2016, but two thirds of staff still fall into the category – ‘Unknown/no religion/prefer not to say’. However as this option contains essentially three categories in one, there is no insight into how staff are split amongst these categories. In July 2017 the LGBTUA+ Supporter Programme was launched which may have contributed to the increased number of people disclosing their sexual orientation. In October 2017, a Trans awareness Guide was also produced – this guide will be circulated at ED&I events throughout the year, and in 2018 a trans supporter lanyard became available as well as a rainbow lanyard for supporters to wear. In April 2018, the University commenced work on self-assessing against the Business Disability Forum Standards with a view to creating a plan of actions to improve processes/procedures for staff/students with disabilities. Again through the communication of this work and consultation with staff, it is hoped that more staff will feel empowered to disclose their disabilities, in order that the appropriate reasonable adjustments can be put in place for them. It is also anticipated that once the new HR system is rolled out to departments, staff will feel empowered to disclose any protected characteristics, as they will have the autonomy to up-date their own personal records, including adding any disclosures not previously documented. A comparison of disclosures will be made (before the new HR system and after roll out) in the 2019 Workforce Profile Report. | 5% improvement on current disclosure rates, which are monitored and reported annually in the work force profile. | HR Systems Team Departments | August 2017 and reported annually. |
| 1.5 NEW | Unconscious Bias training for members on recruitment panels | Encourage all staff especially with recruitment responsibilities to take the newly launched Unconscious Bias Moodle | Progress on numbers of staff taking the modules are monitored and there has been a significant increase in staff taking the modules since 2012 as demonstrated in the table below: A dedicated resource bank webpage for research active staff on Unconscious Bias has been developed and includes training, current articles on UB as well as other useful resources and information, that is regularly updated with new additons eg on tenure; https://warwick.ac.uk/services/ldc/researchers/resource_bank/unconscious_bias/ The number of web hits between 1 January 2018 and 3 December 2018 has been 2,350 with 956 unique page views. Module; 2012; 2013; 2014; 2015; 2016; 2017; 2018. Recruitment & Selection; 54; 141; 257; 462; 589; 600; 324. Diversity in the Workplace; 104; 202; 496; 890; 1008; 1391; 607. Unconscious Bias*; 11; 102; 613. *Only launched in November 2016 In addition to the on-line resource for Unconscious Bias, there are also supplementary open programme face to face sessions run once per term. 77 staff (including HR staff) have participated in these sessions (gender split : 55 females and 22 males). Three bespoke sessions; x 1 for the Engagement Team (9F), the Academic Resourcing Committee members at the request of the Provost (12 attendees – 5M/7F) and one department for their departmental Athena SWAN action plans – 9 attendees – 2M/7F). A UB session to the Humantarian Engineering Residential Course to 57 young people for the School of Engineering (52 scholars & 5 staff – (2M/55F). | Increase in % of staff involved in Recruitment who have taken the Unconscious Bias Moodle | Learning and Development Centre (LDC) | Commenced November 2016. 50% by Term 1 2018. |
| 1.6 NEW | Investigate progression routes at FA6 and FA7 researchers in the STEMM Faculty | Examine recruitment processes in STEMM to ensure a good pipeline of entrants at FA6 and FA7 for research and research and teaching staff, who can then benefit from the good progression mechanisms already in place as a result of Athena SWAN work. | Research staff obtaining Assistant Professorships - Moving from Grade FA6 to FA7 2016/17; 2017/18. Male; 3; 5. Female; 2; 3. Total; 5; 8. STEMM Research staff being promoted to Senior Research Fellow - Moving from Grade FA6 to FA7 2016/17; 2017/18. Male; 6; 8. Female; 3; 5. Total; 9; 13. STEMM Senior Research staff promoted to Principal Research Fellow Moving from Grade FA7 to FA8 2016/17; 2017/18. Male; 6; 0. Female; 0; 1. Total; 0; 1. | Reporting on the number of research staff at FA6 and FA7 who have progressed. | Departmental Recruitment Teams with HR Adviser | October 2017 and October 2018. |
| 1.7 CONTINUATION | Development and Performance Reviews (DPRs) (now renamed Personal Development Reviews (PDR) | University to provide L&D training on DPRs. To continue to embed quality expectations with existing staff through objective setting including during Development and Performance Reviews and throughout the recruitment process. Giving staff an opportunity to reflect on past performance as well as to look forward to new objectives and L&D needs. Measuring and monitoring the data and impact of DPRs to facilitate improvements. | Warwick is committed to providing every member of staff with the opportunity to take part in a PDR. The PDR process was reviewed in 2017 and renamed as Personal Development Review to emphasis the focus on individual support and development. Full details of the process and training are provided on the LDC website on Personal Development Reviews: https://warwick.ac.uk/services/ldc/personal/ Additionally In May 2018, the Vice Chancellor made a personal statement on the importance of PDRs, stating that these should be ongoing conversations between reviewees and their reviewers and these should focus on development, achievements, goals, where support is needed and longer term aspirations. The VC encouraged all staff to actively engage with PDRs. The Provost and Registrar also send personalised emails to colleagues asking for their engagement with the PDR process. The PDR cycle aligns with the academic year, with the formal review taking place in the Spring /Summer term. For 2016/17 ( review taking place April – July 17) the overall completion rate was 69.43% of colleagues across Warwick. At this point of time we are still awaiting completion rate data from a number of departments. Training and education resources are developed and delivered as appropriate by the LDC team, with local support and queries answered by HR colleagues. In 2017 training was provided in a blended format, a number of face to face sessions were run for reviewers and Moodle presentation set up for reviewees. Short ‘byteable’ videos were used to provide a refresher for existing staff. In 2018 all provision was moved on line. See point 1.8 for levels of engagement with training. | Reporting by departments the number of DPR* undertaken, and monitoring low up-take areas for action *DPR is now called PDR (personal development review) | LDC (DPR team) HR Departments Individuals | Annual monitoring July 2017 and July 2018 |
| 1.8 CONTINUATION | Development and Performance Reviews Training (now renamed Personal Development Reviews (PDR) | Online resources will be developed to support staff in DPR completion. | Resources are available from LDC to refresh knowledge and skills on how to conduct PDRs, both for the reviewer and the reviewee. In 2017 the PDR for Reviewers training was predominantly face-to-face, with 95 staff members attending over 9 sessions. PDR for Reviewees was made into an online presentation (in advance of the courses created for 2018), which was viewed by 171 people. In 2018 the PDR website was redeveloped to provide a clear route to resources for staff: guidance for reviewees, guidance for new reviewers and refresher guidance for more experienced reviewers: https://warwick.ac.uk/services/ldc/personal/pdr/ To enable training to be made available to a greater number of staff, 2 online courses were created: PDR for Reviewees and PDR for Reviewers. PDR for Reviewees was accessed by 539 staff, completed fully by 208, of which 80 were research active staff. PDR for Reviewers was accessed by 144 staff, completed fully by 91, of which 29 were research active staff. The resources/online courses are also available year round to support regular and mid-year PDR conversations. | Measure the impact of the training by web site hits, numbers of reviewers and reviewees trained. | DPR Team/LDC | End of each academic term (3 per annum) |
| 1.9 CONTINUATION | Communication and guidance on the Promotion criteria for research active staff: Research Academic Teaching | To continue to host the Warwick ‘Demystifying Promotion process’ event to clarify the promotion process and required paperwork, so that staff can prepare themselves for promotion. Improved communication and promote information on the promotions process. Measure and monitoring the impact of the data and impact to facilitate improvements. | #### Actions from previous staff surveys and Athena SWAN work to provide clarity on Promotion and Career Progression has resulted in Senate (key University Committee) approving a new framework for academic promotions to be implemented for 2018/19 promotions round. This work was led by the Provost, supported by the Promotion Staff Engagement Group and the Gender Taskforce. #### It is the University’s intention that this promotions framework is fairer and more transparent for all staff than before. It is equally intended that in so-doing, it will be of significance in addressing previous inequities for female staff. We believe this to be the case because the new framework: - has clearly set-out requirements for promotion and gives assessment criteria with a marking scheme against them, thus reducing the power of subjectivity and qualitative comments that may be prone to bias; - has parity of esteem for research and teaching and properly scores contributions to leadership, management, collegiality, outreach and impact inter alia that were previously often dismissed as “other activities”; - gives threshold scoring against the criteria for promotion to confirm eligibility for promotion. Properly used, this can encourage female staff to see themselves as promotable relatively earlier in their careers than currently. #### To support the implementation a ‘Promotions Explained’ event was held on 11 May 2018, supported by guidance on the website. This replaced the annual ‘Demystifying Warwick Promotion Process’ workshop which has been held annually since 2013, to inform and guide on process/criteria. Hosted by the Provost and members of Warwick’s Promotion Committee, the event format has evolved following feedback from attendees. Information was requested for Teaching Focussed and Research Focussed staff, which has subsequently been included since the 2016 event. In order to assess impact, attendance is monitored by gender, to ascertain if some attendees go on to submit for promotion and their subsequent success rate. Since 2013 to 2017, 191 staff have attended the Demystifying Promotion events – 93 female and 98 males. A high promotion success rate has been noted amongst attendees (of 39 attendees submitting for promotion, 35 were successful). We intend to follow this up with a focus group to gather qualitative data to share with other potential attendees. #### The work on the promotions framework may have contributed to a 9% increase in positive answers (2018PULSE) to the statement ‘The University’s academic promotion procedures are fair’. This can be attributed to staff consultation on the new framework and we would expect a further increase in the next PULSE Staff survey. #### Research active staff promotion statistics are monitored and reported annually to EDC, Senate and Council, with data broken down by gender, ethnicity, disability and age, to enable intersectionality analysis. Due to the work being done around promotions and the subsequent consultations and communications, we are already seeing an impact on the revision to the promotions criteria as this year (2018) for the first time, more women have been promoted to Professor than men. As we are developing from the old process to the new process, there is an opportunity for staff to engage with the Provost and the Promotions team. | Numbers of staff attending the event and subsequently submitting for promotion. Feedback from attendees. | HR Promotions Team | March 2017 and March 2018 for event. |
| B. RECOGNITION AND VALUE |  |  |  |  |  |  |
| PRINCIPLE 2: Researchers are recognised and valued by their employment organisation as an essential part of their organisation’s human resources and a key component of their overall strategy to develop and deliver world-class research. |  |  |  |  |  |  |
| 2.1 NEW | Create a work package on career-making and culture change by developing supportive actions to promote the career development of researchers (especially women) and contribute to addressing gender inequalities in decision making processes. | Creation of a Research Task force to provide evidence and best practice from Warwick departments to inform a work package on career decision making and culture change. Measure and monitoring the impact of the data and impact to facilitate improvements. | A Warwick social scientist, Charikleia Tzanakou, is leading a Horizon 2020 Work package on gender equality and culture change for a EU consortium called PLOTINA. Charikleia has been involved in the Gender Equality work that Warwick is undertaking, both as part of the Institutional Athena work but also as a member of the Warwick Gender Taskforce. As part of her research on PLOTINA, PLOTINA has contributed to catalysing new actions, monitoring old actions and embedding some activities that were piloted or were used ad hoc at Warwick. A key deliverable for PLOTINA is to develop an online Library of Actions that can be accessed by the wider community in the higher education sector and beyond so that other organisations can take ideas and/or transfer actions and measures in their own context. The PLOTINA Consortium is comprised of different institutional contexts that have provided useful testing grounds for various gender equality measures and this variety will be reflected in the library providing tips and lessons to be learnt. The PLOTINA Summer School on ‘How to be a Peer Reviewer’ took place at the University of Warwick, 10-14th of September 2018. The Summer School targeted PhD candidates and early career researchers and there was an overwhelming response with 70 participants registering for the event. The objectives of the Summer School were: to understand what different review processes entail (e.g. article reviews, funding proposals); learn how to be a constructive and effective reviewer; learn about important aspects of reviewing, including biases in knowledge production and sex/gender considerations and learn how to respond to reviewers. We were privileged to host an impressive line of speakers from various academic departments, from publishing houses and journals in natural sciences and social sciences. Feedback received from particpants was fantastic : Overall it was a very interesting workshop, giving different perspectives on the peer review process. Everything was very well organized. It was really interesting to hear from speakers from a variety of disciplines and backgrounds. The more practical exercises such as looking over example peer reviews/letters from the editors was useful, as was the final session looking at actual pieces of work from people attending the summer school. There were several points made throughout the summer school that I think people may think are obvious, but I actually didn't know - i.e. not to write the recommendation in your response to the author. I think having presentations on both doing peer reviews and responding to peer reviews was particularly useful. I was very intrigued by the discussion about gender imbalance in the research context and it has shifted my thinking since the workshop. I now consider it much more than I did previously. It was also really useful to hear about grant writing from the other side. Thank you for organising a very important and insightful course. “Upon reading about PLOTINA, I was intrigued so I immediately signed up to the summer school, and I am glad I did! For three days, we had the honour of listening to esteemed speakers. The selection of speakers was carefully crafted to give us ideas from a wide range of specialists from academics to publishers. The diverse content of the presentations was spectacular for two reasons: First, the speakers backed up their statements with impressive research (such as Sex and Gender Equity in Research), which was made accessible at the end of the school. Second, the speakers equipped us with practical tools to write better reviews, such as the distilled wisdom of thirty years by Professor Mike Ward. I enjoyed meeting brilliant scientists both from the speakers and the attendees. The workshops gave us a collaborative atmosphere to exchange ideas. The overall experience of the summer school exceeded by expectations. I would highly recommend it to all my friends and colleagues. I sincerely hope that it continues to happen every year. You can find out more about the PLOTINA Summer School: https://warwick.ac.uk/fac/soc/pais/research/projects/plotina/summerschool/programme Other career development opportunities have included: - Workshop on peer review – June 2018 (12 participants) – advertised on Skills Forge - Founded a Faculty of Social Science Early Career Forum https://warwick.ac.uk/fac/soc/staffresources/fssearlycareerresearchers/ - Delivered a seminar on objectivity and bias for PhD students (approximately 40 attendees – June 2018) | Showcasing and sharing of best practice between departments. Reported quarterly. | PLOTINA Project Lead: Dr C Tzanakou | Quarterly updates |
| 2.2 NEW | Extension of probation periods for early career research staff who have taken period of maternity/adoption leave. | Early career researchers/academics (Probationers on Assistant Professor contracts) to be given the opportunity to request an extension beyond the length of time they are absent due to maternity/adoption leave (up to 6 months (in addition to the period of time taken for maternity leave). | The Probation criteria now includes the following statement: Family Leave (e.g. maternity leave, adoption leave) In all cases of family leave, the period of academic probation will be extended automatically by one and a half times the period of absence (e.g. 12 months of maternity leave would equate to an 18 month extension to probation). Please note that this would not preclude a case for early completion of probation being put forward to the Probation Review Group in the event that the criteria for the completion of probation is met in advance of the extended time period. Since the introduction of the above in the Academic Year 2016/17, we have extended the probation periods by 1.5 times the period of leave in 12 cases in connection with Family Leave. Probationers who have been given this extension can still complete early (at their original probation end date) if they have met all the criteria. This information is included in the Annual Report on Promotion and Probation that is presented at the Equality and Diversity Committee at the first meeting of the academic year. Informally we connect people who have been or about to go on family related leave through our Working Parents Network or our Carers Network. A booklet entitled ‘Working, Learning, Living: Share Your Story’ was created in 2017, which provides case studies of staff (including research active staff) who have shared their daily work/life balance responsibilities and how they make use of the flexible working options available at Warwick. | Number of people who have extended their probation due to maternity/ adoption leave. Showcasing and sharing best practice as well as obtaining researcher/academic staff led recommendations. | Promotions Committee Chair and Secretariat | January 2017 and monitored termly and reported on annually – July 2017. |
| 2.3 NEW | Conduct a focussed promotion survey specifically targeted at research active staff. | To respond to feedback from the 2016 PULSE staff survey, a focussed survey on promotion for research active staff (particularly those on full academic contracts) to ascertain if the current process is fit for purpose. | See 1.9 ABOVE Responding to PULSE2016 responses that the academic (research active staff) promotion criteria was not clear, a focussed survey on promotions took place (issued in December 2016 with a closing date of January 2017). The survey had 413 respondents and was also disussed at the Gender Taskforce meetings. Subsequently, an Academic Processes Review Group (APRG) was formed, chaired by the Provost. The group met during a number of meetings in 2017 to discuss and propose actions following the comments/results of the survey. The Group proposed revisions to the criteria for Academic Promotions and amendments to the process for applying for promotion. This was done in consultation with all members of staff via the University’s communication tool, InSIte, and was approved by Senate at its meeting on 14 March 2018. The Group organised 2 events called ‘Promotions Explained’ which replaced the ‘Demystifying the Warwick Promotions process’ events that had been held in previous years. These were attended by 53 members of staff. Also: - The Academic Promotions website has been updated with the revised information for the 2018/19 round of promotions. - We have exemplar promotion cases using the new application form and revised CV templates from some members of the APRG. These will start to be published on the promotion pages in July 2018, starting with the Professorial examples being already available. Work on the promotions framework may have contributed to a 9% increase in positive answers (2018PULSE) to the statement ‘The University’s academic promotion procedures are fair’ since the 2016 PULSE survey. This can be attributed to staff consultation on the new framework and we would expect a further increase in the next PULSE staff survey. | Actions identified are implemented with a view to evaluated in relation to the next PULSE survey results in 2018/19. | PULSE Sub-Group on Promotions Promotions Committee Chair and Secretariat HR Promotions Team | Survey launched December 2016 and sent to 2400 staff with closing date January 2017. Report on response Term 2 2017. |
| 2.4 NEW | Case Studies on promotion to encourage and support promotion submissions, and to demonstrate promotion routes. | Collect case studies from individuals who have attended the annual ‘Demystifying Warwick Promotion process’ event, who then went on to successfully apply for promotion. Promote these case studies on the promotions web page of different job roles and routes to encourage and give confidence to other researchers seeking promotion. | Some case studies have been written and included in Departmental Athena Swan submissions. Once the submissions are awarded Athena status, these are shared more widely and also published on Warwick’s Athena web pages. | Number of case studies per job role per grade. | HR Promotions Team | Term 3 2017 Term 3 2018 |
| 2.5 NEW | Share departmental best practice on promotion. | Collect specific examples of departmental best practice around the promotion process to share amongst other departments for publication on the promotions webpage. Improving the communication of the promotions criteria to research staff. | As above in 2.4 | Number of best practice examples. Increased number of research active staff submitting for promotion. | HR Promotions Team | Term 1 2017 Term 1 2018 |
| 2.6 NEW | Promotion and monitoring of support available for staff taking maternity/adoption leave. | Promote to staff taking maternity/adoption leave what support is in place for them (including the availability of mentors) to support them with the transition back into the workplace. Continue to promote the option of ‘Keeping in Touch Days’. Collate feedback, sharing benefits and considering recommendations. | All departments have dedicated HR Advisers who support individuals taking any kind of parental leave. Web pages are clear and informative and individuals and their line managers are issued with maternity/adoption checklists to guide them through the process, things that might need to be considered and general support that can be put in place for them. Every effort is made to ensure that the member of staff has support before maternity/adoption leave, during such leave and transition back into work. There are HR policies on both types of leave that are accessible from the web pages. Mentors are provided upon request to individuals who may require such support. There is also a Working Parents Network Group and in 2018, the University employed an external company to deliver a number of workshops to parents on juggling family and work responsibilities and how to continue to develop their careers. A similar programme will be run for staff with caring responsibilities in 2019 as a 3 hour workshop (feedback indicated that attendees would prefer a longer session). Academic Returners Fellowship – available for research active staff on full academic contracts. Fellowship buys out teaching and administrative duties, so that the individual can focus on their research when they return from maternity/adoption/extended parental leave. Since the launch of the fellowship in 2015, 32 members of staff have been awarded fellowships. A quote from a member of staff awarded a fellowship is: ‘Receiving a Warwick Academic Returners Fellowship was instrumental (indeed, indispensable) in creating the conditions necessary for me to make substantial and significant progress in my research, not just in terms of preparation of outputs, but also in impact work and participation in conferences’. A number of Cases Studies have been collected to promote support available to researchers, see example below: I am a researcher in Physics and a mom of three kids, 5, 3 years and 2 months. Having childcare responsibilities means I need flexibility in when I work and how much I work. Since I had my first child, 5 years ago, I had lots of support from the department. Even before I started to explore what the options were, my supervisor offered a variety of ways in which my return to work can be the most positive experience. I came back working 2 days a week, with lots of trips to breastfeed my 5 month old in the University nursery (luckily, under 5 min walk away). I was also given a place to breastfeed in the department, if I ever needed that. After 3 months, I increased my workload to 3 days a week, and 3 months later went back full time to end the project I was working on. Since then I worked part time, ranging form 60% to 80% FTE. This arrangement was really helpful, as it eased the shock of coming back, and ensured a great balance between family and work commitments. Everyone has always been very supportive and flexible, and we managed to schedule things in such a way that I could attend work related meetings, conferences and other events with only minor adjustments to daily childcare if any. My supervisor also always managed to ensure my maternity leaves do not affect the research, and that work carries on even when I am away. As a result, my time out did not affect my publication record as much as it might have. Overall, the ability to work flexibly – both in “when” and “how much” means I can have a healthy balance between work and looking after my children. I truly appreciate the supportive environment in Physics Department. | Informed staff. Number of researchers taking maternity/paternity leave and increased uptake of mentors to assist transition back into the workplace. | HR Advisers | Throughout 2017 and 2018 |
| 2.7 NEW | Encourage, promote and monitor positive attitudes towards flexible working. | Improve communications to encourage positive attitudes towards flexible working, by providing case studies for the web pages to demonstrate the benefits to both the individual and the University on flexible working. Host an annual focus group to obtain feedback and recommendations and share practice. | Many of the flexible working arrangements are organised locally in departments and therefore not formally monitored. However when there is a change to contractual hours these are monitored and approved through HR and the employing department. A number of cases have been: - A senior member of Research staff requested to reduce her hours for a temporary period to support an elderly parent. The period on reduced hours was for 2 years and 9 months. - Two members of staff in another department requested a reduction in hours from 1.0 FTE to 0.6 FTE, both cases were approved. See also Case Study in Section 2.6. Flexible working has been discussed in many forums, especially for those departments working on an Athena Swan agenda (Gender Chartermark). Departments with Silver status have provided case studies of members in departments who have taken advantage of the availability of flexible working options and these are shared once the submission is successful. Staff also have the opportunity to discuss with their HR Advisers flexible working options. In the annual Equality Monitoring Report, the employee working patterns are reported. In 2017/18 out of 769 researchers, 125 worked part-time hours. However these are staff that have contracted hours, whereas at departmental level there are more staff working ad-hoc flexible hours. | Monitoring the number of researchers formally requesting flexible working versus those that have been approved, resulting in a change of contractual hours. | HR Advisers Departmental Administrators | Throughout 2017 and 2018 |
| 2.8 CONTINUATION | Research and Impact Services (R&IS) to work with academic departments to inform on research opportunities. | R&IS to work with academic departments to inform researchers of fellowships and funding opportunities. Recording by R&IS Link Officers of one to one support provided; number of applications and success rates. | R&IS has supported the academic departments to submit 1,814 applications totalling £481.5 million in 2017/18, this compares to £441.9m in 2016/17 and £378.1 million in 2015/16. In turn the University’s awards have also increased from £120 million in 2015/16 to £152.8 million (2016/17) and £146.5million (2017/18). This increase has seen the University’s research income grow from £108.5 million in 2015/16 to £120.3 million (2016/17) and £126.4 million (2017/18), a 5.1% increase year on year. R&IS has supported a number of early career researchers by providing 1:1 dedicated advice as well running bespoke training events. The number of fellowships applications in 2017/18 have increased to 406 compared to 336 submitted in 2016/17. An increase has also been seen in awards, the University securing 84 fellowships totalling £12.4 million compared to the previous year of 69 awards totalling £11 million. R&IS routinely meet with researchers to provide 1:1 dedicated support on individual applications, in addition we alert researchers to funding opportunities. The overall success rate for the University has increased year on year from 39% (2015/16) to 41% (2016/17) and 51% (2017/18). Throughout the year R&IS also host a number of training events, as well as presenting at departmental/faculty meetings and away days. An example of events hosted in 2017/18 are listed below: Faculty of Science, Engineering and Medicine: - Research training landscape (Science) – September 2017 (50+ attendees) - Workshop for NIHR applicants – 27 September 2017 (5 attendees) - WMS welcome event for new starters – 15 January 2018 and 1 May 2018 (approx. 15 attendees each time) - Presentation at Research Active Staff meeting – February 2018 (20+ attendees) - RCUK bid writing workshop – 15 March 2018 (50 attendees) - Fellowships in Science and Medicine – April 2018 (100+ attendees) - NIHR Fellowship Workshop - 18 June 2018 (10 attendees) - Mental Health Research Centre Networking Event – 20 June 2018 (approx. 60 attendees) - EPSRC CDT applicants workshop – June 2018 (20+ attendees) - NIHR Fellowship Day – 6 September 2018 (approx. 25-30 attendees) - Wellcome Trust PhD Roadshow – 17 September 2018 (approx. 20 attendees) - UKRI Fellowship applicants workshop – September 2018 (20+ attendees) - Regular presentations at departmental staff meetings - Funder visits: - EPSRC, BBSRC, RAEng, Royal Society, UKRO (EU), Alan Turing Institute Faculties of Arts and Social Sciences: - European Research Council Starting and Consolidator Grants – 13 October 2017 (10 attendees) - Global Challenges Research Fund and the ESRC – 20 October 2017 (20 attendees) - AHRC Leadership Fellowships – 17 November 2017 (10 attendees) - An Introduction to Research and Impact Services – 21 November 2017 (30 attendees) - Early Career Researcher workshop – 21 November 2017 (25 attendees) - Applying to the Leverhulme Early Career Research scheme – January 2018 (20 attendees) - Applying to the ESRC New Investigator scheme – February 2018 (15 attendees) - UKRO Visit (with European Engagement Team) – 21 March 2018 (50 attendees) - Marie Sklodowska Curie Individual Fellowships – 4 June 2018 (10 attendees) - EPSRC opportunities for Social Scientists (with RSDM for Science) – 6 June 2018 (5 attendees) - School of Modern Languages and Cultures Research away day- 6 June 2018 (20 attendees). - Visit of European Research Council President (with European Engagement Team) – 13 June 2018 (20 attendees) - Visit of European Research Council President (with European Engagement Team) – 13 June 2018 (20 attendees) - Artificial Intelligence Roundtable – 13 June 2018 (10 attendees) - Funding Opportunities for 19th Century Studies (with RFO for Arts) – 18 June 2018 (30 attendees) | Increased number of Fellowship applications made by researchers. | R&IS Departments | Throughout 2017 and 2018 |
| C. SUPPORT AND CAREER DEVELOPMENT |  |  |  |  |  |  |
| PRINCIPLE 3: Researchers are equipped and supported to be adaptable and flexible in an increasingly diverse, mobile, global research environment |  |  |  |  |  |  |
| 3.1 NEW | Career support initiatives are innovative, fit for purpose and communicated to all research active staff (also applicable to Principle 4). | Review University support structures to ensure the best possible support for researchers at all career levels, by consulting with the Research Staff Forum and ensuring appropriate communication channels across campus. Providing a range of one to one/face to face/online resources or workshops for research active staff. | See 1.9, 2.1, 2.4 and 2.8 above There are many resources and training in place for research active staff which are communicated on a regular basis by the LDC and the Research Staff Forum. At the Vitae International Research Development Conference, Sandy Sparks (LDC Adviser) gave a conference presentation and workshop on ‘Measuring Impact on Learning and Development Initiatives for Research Staff; Two University of Warwick Case Studies’, on 11 September 2017. The two case studies were: The Researcher Network Funding Report and the Leadership Programme. Typical courses are: Leadership Programmes - Preparing for Leadership (across 2 days) - Leadership in Action (across 2 days) Academic Writing Workshops: - Writing for Impact - Translating Research for Multiple Audiences - Becoming a prolific writer - Quantitative and Qualitative Argument Architecture - Raising your Article Quality - Writing Collaboratively Plus Writing Retreat Bootcamps Twitter Skills Workshops: - Research Data Management - Planning your Publication Strategy Career Development Workshops - Managing your research and academic career Unconscious Bias Update on attendees at workshops during 2017/18 Research Active Staff Workshops; Attendees. Academic Writing Workshops. - Writing for Impact; 17. - Translating Research for Multiple Audiences; 11. - Becoming a Prolific Writer; 18. - Quantitative and Qualitative Argument Architecture; 7. - Raising your Article Quality; 10. Career Development; 25. Preparing for Leadership; 19. Leadership in Action; 20. Leadership follow-up session; 10. Research Staff Forum; 63. Autism Workshop; 18. Unconscious Bias; 49. UB – bespoke x4; 85. Bespoke – Strength Profile; 17. Bespoke – Emotional Intelligence; 42. Bespoke – MBTI; 21. Collaboration. Twitter; 15. Public Engagement; 50. Research Data Management, Open Access, Planning your publication strategy; 15. Courses taken place in 2018/19 Term 1: Research Active Staff Workshops – Term 1; Attendees. Unconscious Bias; 7. Public Engagement: Engaging diverse audiences with your subject specialism and/or your research – Part 1; 10. Public Engagement: Engaging diverse audiences with your subject specialism and/or your research – Part 2; 6. Preparing for Leadership; 19. Managing your research and academic career; 15. Bespoke – Effective networking strategies for researchers; 24. Bespoke – Learning and Development Opportunties for PDRAs in Life Sciences; 10. Courses planned in 2018/19 Leadership in Action (across 2 days) Leadership course see Section 3.3 Academic Writing Workshops: - Becoming a Prolific Writer - Writing for Impact - Raising your Article Quality Plus Academic Writing Retreat Bootcamps & 1-1 support Managing your Research & Academic Career Unconscious Bias 1-1 support for research active staff There are a number of impact reports detailing the various courses with number of attendees and associated costs, which can be accessed here: https://warwick.ac.uk/services/ldc/researchers/opportunities/impact_reports The impact reports are on: - RAS Network Funding 2017/18 - reports since 2012 - RAS 1-1 support 2017/18 - new - Preparing for Leadership 2017/18 reports since 2016 to date - Leadrership in Action to be update & from 2015 to date - Academic Writing report 2016/17 | Increased numbers of research staff taking up career support training and one-to-one meetings. Increased representation of researchers from departments on the RSF. Impact Report and Case Studies | LDC Departments | Available for take-up throughout academic year and reported termly |
| 3.2 NEW | Development of case studies of researcher profiles from Warwick’s research community. | Career paths for researchers highlighted and showcased. Public engagement with Research involvement and activities showcased. | Case Studies have been written after interviewing research active staff and these will be shared from 2019. New for 2017/18 was a LDC RAS collaboration with the public engagement team for five workshops and resource bank webpages - 28.03.2018 - Beginner’s Guide to Public Engagement* – 18 attendees (5M/13F) with 14 departments having attendees, with 100% of attendees saying they would recommend the session to colleagues. - 25.04.2018 / 04.05.2018 – Giving Great Public Engagement Presentations* – 14 attendees (7M/7F) with 11 departments having attendees, with 100% of attendees saying they would recommend the session to colleagues. - 23.05.2018 - Evaluating your Public Engagement* – 14 attendees (3M/ 11F) with 11 departments having attendees, with 100% of attendees saying they would recommend the session to colleagues. - 08.06.2018 - Digital Techniques for Public Engagement - 13 attendees (5M/ 8F) with 11 departments having attendees, with 100% of attendees saying they would recommend the session to colleagues. - 21.06.2018 – Public Engagement Exhibitions: working with Museums and Galleries - 9 attendees (2M/ 7F) with 7 departments having attendees, with 66% of attendees saying they would recoomend the session to colleagues. Workshops marked with an asterisk (*) have been updated and will be repeated in 2018/19. A summary report on these public engagement workshops with the key highlights of 2017/18 was undertaken and shared with research active staff. Public Engagement Unit (PEU) organised Pint of Science, giving 30 academics from Warwick the chance to speak to a public audience about their research. Reached 328 members of the public (also see 4.1). | Number of Case studies available on the web. Feedback from researchers. Case Studies of research staff engagement with the public, regularly featured and updated on the Community and Public Engagement webpages. | LDC with the Research Staff Forum Regional and Business Engagement (Public Engagement Unit) | Term 3 2017 and Term 3 2018 Term 2 2017 and ongoing. |
| 3.3 CONTINUATION | Provision of a range of Leadership and Management Development Opportunities for research active staff (also applicable to Principle 4). | The University to offer a range of Leadership and Management Development courses to equip researchers with key skills in leading/managing teams to meet project requirements, e.g. Preparing for Leadership (PfL), Leadership in Action (LiA). | Also see 3.2 - Leadership Warwick offers the following Leadership courses for research active staff: Preparing for Leadership in 2017 Runs annually x 1 per academic year, term 1 2 days – 1 day per week, 1 week apart – for Preparing for Leadership course – face-to-face time. Open to Grade 5-9 staff on research, academic or teaching terms and conditions, i.e. all research active staff. 2017 there were 31 attendees with a gender split of 17 males and 14 females: x19 on grade 6; x 11 on grade 7 and 1x visiting academic. Attendees were from across 9 different departments. Impact/Benefits stated on feedback by attendees: - Ability to make useful international contacts in Paris, and raised personal profile in the international community - A £23,000 funding from Warwick Ventures for a proof of concept project - Assigned more students to supervise because of good performance - Leading a conference day for the whole cohort of the course - Leading, collaboratively, on a particular area of course delivery for the next academic year - Taking a leadership role in a number of new external engagement opportunities - Managing relationships with support staff from the centre - Supervison of PhD students - Several promising opportunities to work with external organisations. Leadership in Action Programme for 2017 Runs annually x 1 per academic year, term 2 3 days – 1 long half day per week, 1 week apart – for Leadership in Action course – face-to-face time, i.e. 15 contact hours. Open to Grade 5-9 staff on research, academic or teaching terms and conditions, i.e. research active staff. There have been 3 cohorts – February 2016, November 2016 and March 2017. 5 research active staff (3 male and 2 female) have gone from the ‘Preparing for Leadership’ programme to this ‘Leadership in Action’ programme. There have been a total of 47 attendees, with a gender split of 17 males and 30 females: with a grade split of x20 on grade 6; x 18 on grade 7, x6 grade 8 and x3 visiting academic/other. Attendees were from across 14 different departments from the 3 cohorts. The impact reports for 2017/18 will be shared in December 2018 with impacts mapped to an impact frameworks https://warwick.ac.uk/services/ldc/researchers/opportunities/impact_reports Impact/Benefits stated on feedback by attendees: - Proactively engaging in re-structuring of international body - More supervision responsibilities - Offered academic position in to 10 UK university (promotion) - Joint paper x 2 - Potential collaborative bid - Peer coaching - Collaborative bid for doctoral student - Potential to start a small research project - Intitial conversations about joint research project - Invitation to join committee of an international association (ISA) and successful bid application for funding from ISA. - Submitted collaborative bid for funding with colleagure for Leading in Action Programme - Invitations to joing collaborative project group - Successful application for promotion - Commence certificate in teaching and mentoring - Mentoring Masters students, PhD students and less experienced colleagues - Increased the number of research projects and collaborations - Applying for promotion to Senior Research Fellow - Giving everyone a chance to contribute to agendas and discussions in meetings - Applied and got new job. A new activity for 2017/18 was a 1-day follow-up session - 10 attendees (5M/ 5F) in response to feedback and requests from RAS. This was open to both attendees of PfL and LiA – the session included sharing impact but also inputing into the needs and future development of Leadership ptogrammes and the L&D provision to meet the RAS needs. 2018/19 – Leadership Programmes Preparing for Leadership (PfL) 19 RAS attendees (9M/10F) – Grade 6 x12 Grade 7 x2 Grade 8 x1 Other x4 The Impact reports for 2017/18 has been shared in October 2018 and the 2018/19 will be undertaken in 2019. https://warwick.ac.uk/services/ldc/researchers/opportunities/impact_reports Leadership in Action (LiA) This will be taking place in Term 2 and the impact report for 2018/19 will be undertaken in 2019. Academic HoDs Programme for new academic HoDs (11) ran in July and September 2018. | An increase uptake of researchers on leadership and management programmes. Feedback from attendees. Annual Impact Report | LDC | PfL - Term 1, 2017 and 2018 LiA – Term 2 2017 and 2018 |
| 3.4 CONTINUATION | Provision of a range of career development opportunities for research active staff, especially staff on fixed term contracts (also applicable to Principle 4). | The University to offer a range of career development support, through workshops, courses and one to ones, to equip researchers with key skills to key transferable skills for their career development. | LDC funding has provided a number of personal and career development sessions and training. Feedback from participants for 2016/17 on how they have benefitted are listed as: - Increased opportunity for networking and collaborations in the future - Reduced feeling of isolation and developed a sense of community - Careers development through staring a network or leading a network - Opportuniy for research staff who are not yet independent to obtain funding to pilot an initiative - Practice sharing via the research staff forum and between the network leads - Opportunity to highlight and showcase their research - Share best practice, develop skills and receive training through increased liaison with LDC and other University support departments. The courses have provided opportunities to develop skills in: Update for 2017/18 - See the latest Research Active Staff Research Funding Impact report https://warwick.ac.uk/services/ldc/researchers/opportunities/impact_reports Also see 3.1 - Managing your Research and Academic Career plus the resource bank webpages - The Network Funding including the impact report - 1-1 support Evaluation and workshop feedback New for 2017/18 was the introduction on collating the feedback from L&D events and adding in LDC RAS response and then sharing the collated feeback with all attendees and then the collated feedback being used to inform the development/ adaptation and adapt L&D provision. This collated feedback is added to the resource bank and events pages. RAS network funding for 2017/18 - £8 K budget allocations, this enabled a diverse range of RAS networks to be funded. This year 9 networks were funded. There is a impact reports for 2017/18 sharing the impact of the networks. https://warwick.ac.uk/services/ldc/researchers/opportunities/impact_reports This was also shared with all RAS via the monthly RAS e-newsletter to share practice and also the impact of the RAS network funding. RAS 1-1 support. See the impact report on 2017/18 of the benefits and the achievements by RAS as a result of the I-1 support. https://warwick.ac.uk/services/ldc/researchers/opportunities/impact_reports 2018/19 RAS 1-1 support is open and as at 1 October 2018 we already have 12 RAS 1-1 requests for support in career development, academic writing, emotional intelligence, coaching and mentoring etc For 2018/19 we have funded 11 research active staff networks supporting personal and career development of research active staff. | Uptake on career development provision, number attending one-to-one career development sessions. Feedback from attendees. | LDC | Available for take-up throughout academic year and reported termly |
| 3.5 CONTINUATION | Fit for purpose Personal Development Reviews (PDRs) (also applicable to Principle 4). | Personal Development Reviews to enable discussions about career development/progression between research active staff and their managers. | Staff participate in annual PDRs, set up and implemented in 2015 to replace Annual Reviews. The change aimed to emphasis focus on personal support and development and provide a structured opportunity to discuss career development. At the same time, PDR provides an opportunity for communicating our strategic priorities and discuss their alignment with staff members’ plans and goals for the future. The Pulse report shows 4 % increase in overall University positive response rate to the question ‘I believe PDR assists me with my longer term career development’ and 5% increase in overall positive response rate to question ‘ I believe I have the opportunity for personal development and growth at the University’. The response by Research colleagues shows a slightly higher increase of 6% for question on PDR and 10% increase in response to question on overall opportunities. The forward looking part of the PDR form for academic colleagues, including Research active staff, is now aligned to the new promotions criteria, this will make conversations more meaningful in terms of progression on career development routes. (See also 1.7 and 1.8 for PDR uptake and training information and 2.6 on academic promotions) . For 2018PULSE, departments are being asked to identify two key areas to focus for improvement, PDR is identified within many local plans. . Looking forward systems improvements will provide access to online PDRs this will provide extra functionality, including prompts, to encourage and support more regular PDR conversations. A new Learning Management System will also make it easier for colleagues to record notes of training and development to reflect the impact of these during PDR conversations. | Increased uptake of PDRs by researchers per job role. – we do not currently have this data but the new HR system should be able to provide this by 2020. Another measure of success is relevance and alignment with other processes and the 2018 forward facing form is now aligned to PDR objectives | LDC PDR Sub-PULSE Group Departments | July 2017 and July 2018 |
| 3.7 CONTINUATION | Provision of a range of courses to enable research active staff to develop transferable skills to enhance their career development for a diverse, mobile global research environment (also applicable to Principle 4). | Development and delivery of a range of courses to develop transferable skills, delivered through embedded L&D training and opportunities, in order to stay competitive in both internal and external job markets. | Coaching and Mentoring Scheme (PSS staff also) - set up in 2012, providing opportunities for career planning and personal work related issues with more senior staff outside of line management arrangements. It is particularly important for females who may lack access to informal networks. 60 of the 88 registered mentors being female. Staff on academic probation (Assistant Professors) automatically have a mentor as part of their probation. There is a steady increase in overall numbers volunteering to take part in the scheme as shown in the table below, although the number of pairings has dropped slightly. Number of staff on mentoring schemes by gender Programme/ Mentoring Scheme; 2016-2017; 2017-2018. WMS; Other depts; WMS; Other depts.. Warwick Coaching and Mentoring Scheme; 18 staff (5M/13F); 47 staff (11M/36F); 23 staff (6M/17F); 55 staff (12M/43F). Research active/academic staff; 18 staff (5M/13F); 10 staff (3M/7F); 7 staff (5M/2F); 9 staff (2M/7F). Coaching and Mentoring Pairings; 18 staff F:F 12 M:M 1 M:F 5 F:0; 25 Staff 9M/16 F; 14 staff F:F 8 M:M 1 M:F 5 F:M 0; 14 staff F:F 12 M:M 1 M:F 1. Completion of Coaching and Mentoring Skills Workshop; 50 Staff (11M/39F); 65 Staff (11M/54F. Series of 3 coaching sessions as part of the Warwick Leadership Programme; 12 M 18 F. Two of our staff are part of a collaboration of universities in the North East of England, to give strategic guidance on the support that leaders should be giving to develop researchers. A new blended learning approach to coaching and mentoring awareness and training went live in mid-July 2016. This included a Moodle for pre-workshop knowledge acquisition, followed by practice-based learning sessions to work through coaching/mentoring examples/scenarios. This flexible approach enables more staff to engage with the training and allow for practice-based sessions to be easily targeted to different roles/disciplines. It also provides an easy means for colleagues to refresh knowledge. 2017/18 – LDC Research Active Staff The 1-1 support is offered to all RAS. This includes 1-1 support for; - Academic Writing Support - x4 RAS/ 6 sessions - Career Development Support – x15 RAS/ 16 sessions - Coaching and Mentoring Support – x4 RAS / 8 sessions - Specialist support including Emotional Intelligence (EI), MBTI and Strenghs Profile - x2 RAS A total of 24 1-1 1’s with 21 RAS. In addition coaching a Professor on the Warwick Leadership Programme. Bespoke session were run for Research Centre, WMS Unit or departments on Emotional Intelligence (18 June 2018 – 42 attendees (31 F and 11 M), Strengths Profiling (10 July 2018 – 17 attendees (8 M and 9 F) and Myers Briggs Personality Type Indicator (20 March 2018 -16 attendees (10 F and 6 Male). New for 2017/18 an Impact report was written about the benefit of the support for RAS and what they had achieved / impact as a result of the 1-1 support https://warwick.ac.uk/services/ldc/researchers/opportunities/impact_reports For 2018/19 Term 1 The 1-1 support is offered to all Research Active Staff. This includes 1-1 support for; - Academic Writing Support - x4 research active staff - Career Development Support – x15 research active staff - Coaching and Mentoring Support – x7 research active staff - Specialist support including Emotional Intelligence (EI) x1 research active staff - A total to date (December 2018) is 27 1-1’s. | Provision and up take of a number of courses, number of researchers per grade/per faculty to enhance research active staff development. | LDC | Training available for take-up throughout academic year and reported termly. |
| 3.8 CONTINUATION | Provision of Research Staff Forum as a supportive networking group (also applicable to Principle 4). | Continue to ensure that all new research staff are invited to the Research Staff Forum to engage and network with other research active staff and to act as a consultation mechanism on research initiatives. | All new research active staff are invited to join the Research Staff Forum and also received the monthly Newsletter for research staff, which informs them of events/training. 2017/18 RSF – 18 attendees (6M / 2F) RSF – 20 attendees (9M / 11 F) RSF – 15 attendees (3M / 12 F) At each RSF a focus on a particular topic has been added, this year the three topics included Digitial Humanities IT support, R&IS on Bid and Grant support and also public engagement support within the University. The HR Excellence in Research draft document was shared at the research staff forum requesting comments and additions. The research staff forum had 11 attendees and the HR Excellence in Research draft document was shared with all them. We subsequently met with a representative from the forum to feed their comments into this final submission. | Number of research active staff attendees. | Research Staff Forum LDC | Meets once per term, 2017 and 2018 |
| 3.9 CONTINUATION | Ensure that students can access professional, independent advice on career management. | Provision of clear career guidance to all taught and research students, as well as application advice, mock interviews and workshops. | Student Careers and Skills have the responsibility for providing career guidance to all taught and research students and support them by: Building confidence and self-awareness Developing the skills graduate recruiters look for Advice and guidance on career options Preparing and applying for jobs, further study and work experience. In a response to a Student Survey, an Action Plan for 2018/19 has been created outlining what students have said about the Careers and Skills Service (SCS), why we think we do some things well and how we intend to building upon those actions. The top three successes are: When students find SCS services they are very satisfied with them, but our services are not visible enough and there are a number of longstanding misconceptions which deter some students from engaging. Based on student feedback from a number of sources, we are prioritising the following actions in line with the new Education Strategy: - Increasing ‘hub & spoke’ delivery, in terms of both physical space and services offered centrally/in collaboration with departments; - Reviewing how we communicate our services to students; - Broadening our offer, both in scope (eg range of employers) and scalability (eg online services); - Reviewing academic, personal and professional skills needs and provision across the University for UG and PGT students. The following plan highlights some of the work underway in response to student feedback. The forthcoming University Employability Strategy and implementation plan aims to transform the University’s approach to employability and will have a significant impact on our work with students. What students say (please cite the sources of feedback); Why we do well in this; How we’ll build on this. Students who use SCS services are very satisfied (programme evaluations; volunteering survey; unsolicited feedback; focus group feedback); Broad range of services; passionate staff; Review our communications so that more students are aware of our services. Advice is available where students are (growth in numbers of students seen; unsolicited feedback); Established visible presence in Oculus and growing ‘spoke’ spaces (Science; Social Sciences); Continue to campaign for dedicated main campus Hub to deliver appropriate student experience and broader range of services. High quality online provision (eg increased use of Careers Fair app; growth in YouTube channel from 9,010 views in 2014/15 to 124,124 views in 2017/18; growth in Careers Blog views from 67,427 views in 2013 to 258,821 in 2018 to date); Dedicated IT team with high-level skills; subject experts (eg skills development; careers advice; employer liaison); Review strategically development of future online resources. | Feedback from students Case studies Employability statistics | Student Careers and Skills | Available for take-up throughout academic year and reported termly |
| 3.10 CONTINUATION | Ensure that staff can access professional, independent advice on career management (also applicable to Principle 4). | Provision of clear career guidance to all research active staff, as well as application advice, mock interviews and workshops. Provision of learning and development support via one to ones, workshops and coaching. | The LDC website and Research Active Staff Newsletter promote a wide range of training and resources to advise on appropriate career development. A small project to update the online website resource on career development was undertaken and shared with research active staff. Also see 1-1 support on career development – see 3.7 Also the 1-1 support for research active staff and the Impact report – shared in September 2018 for period 2017/18. | Feedback from staff Case studies | LDC | Available throughout the academic term and reported termly. |
| 3.11 CONTINUATION | To broaden the Warwick Shadowing Programme (now known as ‘How Warwick Works’) (also applicable to Principle 4). | To continue to develop the Shadowing Programme to enable more research active staff to participate and gain leadership skills. Tracking succession data and impact. In response to need, to develop the financial planning workshop for 2016/17 academic year. | Warwick hosts an annual ‘How Warwick Works’ Shadowing and Development Scheme for Academic staff. The Scheme connects participants with people currently in management roles so that they can observe committees, gain practical insight into department financial planning and shadow a Head of Department, or senior academic (or equivalent on Teaching Focussed or Research Focussed contracts). The programme is aimed a Professors or Senior Associate Professors to prepare them for the possible next steps in leadership by providing them with opportunities for relevant and accurate understanding of what the senior roles involve. ‘How Warwick Works’ will provide up to 12 participants a year with the following: - A greater understanding of the structures at Warwick, including its management structure - Specific insights into operating in leadership roles and decision-making processes - Increased knowledge of the broader environment within which Warwick operates and the strategic management issues addressed by senior management - The opportunity to raise their profile among senior management - Increased confidence in operating at senior decision-making levels - Enhanced networking opportunities with members of the senior management team. The Shadowing programme consists of three half days of shadowing, a Financial Planning Workshop, a HR Engagement Workshop and attendance a Warwick institutional level committees. There are six Case Studies from staff that have participated in the Shadowing Programme: https://warwick.ac.uk/services/ldc/personal/careerprog/how_warwick_works/participant_feedback/ For the first two years, 2014/15 and 2015/16, the shadowing programing ran as 2 ssmall-scale pilots: In 2014/15 there were 5 participants, of which 3 have gained senior roles In 2015/16 there were 4 participants, of which 3 have gained senior roles In September 2016, this was refocused to ‘How Warwick Works’, with a cohort of 12 participants for 2016/17, which has exceeded the 40% increase as set out in the success criteria for this Action Plan. 4 have gained more senior roles, including one HoD, who is acting as a shadowee on the 2018-19 scheme. In 2017/18 there were a further 6 participants of which 3 have gained professorships. In 2018/19 11 participants have been accepted onto the scheme. Formal online feedback was received from 8 of the 2016/17 cohort as well as 4 Heads of Departments. There were also discussions at a final review session. Feedback was positive, with all the participants agreeing or strongly agreeing that the focus and opportunities in the scheme were appropriate and helpful. The Financial Planning workshop was very well received, with sessions exploring other central services suggested by participants and HoDs. A mid-scheme review was well received as an opportunity to share experiences to date amongst participants and advance further discussions within pairings. Interestingly, some participants liked the flexibility of judging for themselves how shadowing time should be spent, whilst others would appreciate a more structured approach set out. Similar positive feedback was received in 2017/18, noting the new session on Governance. As a result, further sessions on HR Engagement and a Q&A meeting with the Provost have been added for 2018/19. | Increased participation rates by 40%. | LDC Senior Management Team | Start Date October 2016. Review dates January and May 2017 and repeated 2018. |
| PRINCIPLE 4: The importance of researchers’ personal and career development, and lifelong learning, is clearly recognised and promoted at all stages of their career. |  |  |  |  |  |  |
| 4.1 NEW | Development of opportunities for research active staff on impact and public engagement. (also applicable to Principle 2) | Supporting research active staff to increase their awareness and develop initiatives for sharing impact and/or public engagement opportunities. Measuring and monitoring impact. | - Public Engagement Network (PEN) now has 236 members - Last PEN Conference in November 2017 hosted 44 members of staff. An upcoming repeat of this conference for 2018 has 51 attendees registered to attend. - Public engagement training scheme launched for 2018, 107 attendees over 7 sessions - 3 Ideas cafes run through the year, Energy, Cancer Research and Cell Biology, 18 academics involved. See the collaboration training initiative between LDC and the Public Engagement team – see section 3.2. | Development of a Public Engagement Unit (PEU) Participation in University wide Public Engagement Network (PEN – currently 180 members) Training in PE and media work Best practice/ knowledge sharing. Case studies | Regional and Business Engagement LDC R&IS and Impact Officers Press Office | PEU set up by March 2017 Annual PEN day workshop Available for take-up throughout academic year and reported annually. |
| 4.2 CONTINUATION | Develop and support research active staff networks providing ‘pump-priming’ funding enabling personal and/or career development. (also applicable to Principles 2 and 3) | Continue to support research active staff networks to assist with career and personal development, thereby building a research community. | The research active Staff Network Funding call is from 1 September to 31 July each year. Applicants for funding need to include budget/costings, plan of activity which should include expectations and reason for attending the course, with support required from their PI/Line Manager or HoD. The funding is open to research active staff (RAS) and/or those on teaching contracts. A 5 year review on RAS network funding states that: - 32 networks have been supported / 60 networks funded - 2 networks ran for 5 yrs / 2 ran for 4 yrs / 5 ran for 3 yrs / 4 ran for 2 yrs /19 ran for 1 yr - 4 collaborative / joint funding applications - X21 depts submitted applications - £56,890.90 / £45,393.42 used - Encourage inter-disciplinary / collaborations - 12 outside UK - Over 5 years – total 32 Network Funding networks supported - Gender split 35 males and 64 females. High % female-led initiatives - 23/32 proposal / networks submitted / led by females – Athena SWAN - Grades of participants: 43 – Grade FA6 20 – Grade FA7 23 – Grade FA8 4 – Readers 1 – Professor 2 – Research Associate 1 – PhD Research Student 1 – Professional Service - 4320 opportunities for peer-led/career development opportunities LDC Funding has provided a number of personal and career development benefits: - Increased opportunity for networking and collaborations in the future - Reduced feeling of isolation and developed a sense of community - Careers development through staring a network or leading a network - Opportuniy for research staff who are not yet independent to obtain funding to pilot an initiative - Practice sharing via the research staff forum and between the network leads - Opportunity to highlight and showcase their research - Share best practice, develop skills and receive training through increased liaison with LDC and other University support departments. The funding has also offered individuals the opportunity to develop skills in: - Event management - Administration - Project management and time management - Leadership and leading - Strategic and long term planning – in relation to thematic meetings or seminars - Persuasion and influence when requesting input from junior and senior researchers - Making connections with academics outside of usual network – expanding personal networks - Opportunities to chair or lead meetings - Confidence in leading and being authoritative in order to keep to time - Successful assertive behaviour - Excellent experience for future CV’s - Visibility within Department – Leading to career development opportunities (promotion) - Opportunity to utilise online tols (Skype) to work collaboratively to organise meetings. Research active staff network funding reports 2017/2018. Also a longitudinal report since 2012 of the impact has also been undertaken and updates included in the impact reports Updated information can be provide from the 2017/18 impact report when shared October 2018 Research active staff network funding In 2017/18 the LDC Research Active Staff (RAS) Network Funding, managed and supported by Sandy Sparks, funded nine Research Active Staff Networks, by awarding £8782 of which £8174.24 was spent by Research Active Staff network leads, creating 795 professional development opportunities at just over £10 per opportunity. The projects funded encouraged inter-disciplinary and collaborative working across the university and in many cases supported networks which fostered links with external partners or other universities both locally and nationally. Activities and projects ranged from a collaborative network exploring the links between exoplanets and habitability to a one-day conference sharing research on parenting, which attracted external parenting practitioners to learn about the research being carried out at the university. In 2017/18, 88% of the project proposals and subsequent projects/networks were submitted (individually or jointly) or run by women, ensuring that the LDC Research Active Staff Network Funding remains an important provider of opportunities for the university in their drive to encourage the development of women in research and contribute towards the University’s Athena Swan Award. In the impact report you will see the benefits referred to for: Organising Committee RAS members felt that the funding had enabled a number of additional benefits: increased opportunities for networking; useful preparation for future funding opportunities; experience with organising meetings, managing projects and budget handling; Attendees or members of the network: consider alternative research approaches / methodologies; links and potential collaborations with other UK universities / partners; keeping up-to-date with current research debates; Guest speakers and presenters identified the following benefits of involvement with the networks: opportunity to learn and share practice; the importance of pitching presentations to different audiences; opportunity to form and make links with other experts in the field; | Annual Impact Report Number of networks supported. | LDC | Launched annually in September 2016 for 2016/17 programme and 2017 for 2017/18 programme and reported in July each year. |
| D. RESEARCHERS’ RESPONSIBILITIES |  |  |  |  |  |  |
| PRINCIPLE 5: Individual researchers share the responsibility for and need to pro-actively engage in their own personal and career development, and lifelong learning – (please note that in the interest of not duplicating information see information on Career Development – Principle 3 and Principle 4) |  |  |  |  |  |  |
| 5.1 NEW | Focus on the relationships between research and excellence, education, innovation and capacity building. | To bring together universities that have demonstrable excellence in teaching, research and policy formation from across Europe to collaborate on the creation of innovative solutions to some of Europe’s most intractable scientific and social challenges. Sharing practice and showcasing various initiatives. | Warwick’s Pro-Vice Chancellor for Research works across all of Warwick’s departments to maintain research excellence. The PVC (Research) overseas departmental and inter-faculty developments, and heads Warwick’s efforts to generate the impact of Warwick’s research. The Global Research Priorities (GRP) programme, for which the PVC, Research provides leadership, has been a key platform to achieve the desired impact. In Autumn 2018 all academic staff and postgraduate research students were invited to contribute to the University’s review of the Global Research Priorities Programme through an online survey, as part of the research strategy refresh. The responses to the survey will contribute to how the GRP programme can support the University’s research going forward and align it to challenges of global significance. Once the responses have been taken into account, the programme will relaunch in August 2019. Warwick is also a key member of the Midlands Innovation Team, which is a partnership between Aston, Birmingham, Cranfield, Keele, Leicester, Loughborough, Nottingham and Warwick universities, which combines research, resources, skills and people to improve different sectors of the Midlands and beyond. We have close collaborations and partnerships with a number of universities, research organisations and institutions around the world. Some are international university partnerships, enhancing our position as a globally connected University, while others are UK collaborations covering a range of academic disciplines, research and other more specific endeavours. Warwick’s Pro-Vice Chancellor for External Engagement has responsibility for regional, national and international partnerships across the HE, private and public sectors, development of Warwick’s presence in London, triangulation of our research, impact, and public engagement interests between the West Midlands, London and Europe. | Demonstration of excellence in teaching, research and policy formation. Discovery of innovative solutions to scientific and social challenges. Report and promotion of research. | PVC (PG and Transnational Education) PVC for Research | Ongoing and reviewed termly at the Research Committee. |
| 5.2 NEW | Research active staff to be familiar and to be able to map their development to a competency framework, e.g. researcher development framework (RDF). | To promote the RDF to research active staff by signposting and embedding the competencies in learning and development provision. | All Learning and Development provision for research active staff is mapped to the research development framework but this is not overly promoted at Warwick. | Increased awareness and ensuring our provision is mapped to research competency framework | LDC | Annually at DPR Annual Reporting. |
| 5.3 CONTINUATION | Publicise and encourage engagement with Warwick Ventures and the Regional and Business Engagement Team. | Develop mechanisms for identifying, developing and supporting research leaders to head up new large-scale research initiatives and funding applications. Promotion of the initiatives through case studies/showcasing opportunities. Measuring and monitoring impact. | Public Engagement Fund (seed funding up to £1000) ran again in 2017/18, supporting 9 projects (10 initially awarded, with one declining the funding due to required changes to the project). This fund is open again for 2018/19 with applications closing on 31.10.18. The aim is to fund 8-10 activities. Warwick is delivering a new competition to university researchers who may be offered up to £35,000 to take their commercially-promising ideas out of the laboratory and into the marketplace. The Midlands ICURe programme is a one-year expansion of the Innovation to Commercialisation of University Research (ICURe) pilot programme, following a £7.65 million funding boost from the Department for Business, Energy and Industrial Strategy (BEIS). In 2018 Warwick and Queens University Belfast, supported by Innovate UK, are working alongside the programme’s original delivery partner SETsquared Partnership to run and grow the programme across the UK. The Midlands ICURe programme is open to universities cover the broad middle of the UK, from Wales to East Anglia. The Midlands ICURe programme will support up to 24 teams, and in line with the Government’s industrial strategy white paper, the programme funds early career researchers’ time and expenses to find the best route to commercialise their research outputs and help them develop the necessary business skills, connections and expertise to pursue their ideas. | Increased number of research initiatives and funding applications/ successes. Annual Public Engagement Fund to support at least 10 projects that show potential excellence in PE and ongoing learning and development. | Warwick Ventures Regional Business and Engagement Team Public Engagement Unit R&IS | Termly and reported bi-annually. PE Projects reported on annually (2016, 2017 ongoing) with follow up on progress after a year. |
| 5.4 CONTINUATION | Generate impact and a commercial return from research. | Continue to provide assistance with generating impact and a commercial return from research. | Warwick Ventures commercialises innovations produced from world-leading research carried out at Warwick. They offer advice and services to the University’s innovators and support them throughout the process of generating impact and a commercial return from their research, whilst they maintain their academic focus. Warwick Ventures works closely with industry providing businesses and investors access to the best of the University’s Intellectural Property. They support technology development, license IP and create spin-out companies that retain close ties to the University’s expertise. Since April 2000, Warwick Ventures have: Identified 1,500 innovations Agreed 156 licences with external companies Filed 750 patents Created 100 spin-out companies Raised £100 million of venture capital for those companies Achieved 4 successful exits, brining in over £2 million to Warwick | Increase in commercial return and reputation of Warwick researchers | Warwick Ventures R&IS | Available for take-up throughout academic year and reported annually |
| E. EQUALITY AND DIVERSITY |  |  |  |  |  |  |
| PRINCIPLE 6: Equality and Diversity must be promoted in all aspects of the recruitment and career management of researchers (Equality, Diversity and Inclusion underpins all activities) |  |  |  |  |  |  |
| 6.1 NEW | Ensure that our strategic partner institutions have at least the same Equality and Diversity standards to match our own. | Formalise a process for assessing the values and Equality and Diversity standards of partner institutions where our staff and students go to work on our behalf where we have members of university staff. | The Director of HR has visited Monash University, Australia, to discuss HR and ED&I practices. Contact has been made with Monash and the sharing of best practice, i.e. Warwick replicated the shadowing programme that was initially given at Monash. ED&I policies have been checked to ensure that standards match those at Warwick. Warwick acted as critical friend to Monash for their SAGE submission (this is a gender Charter Mark – similar to Athena SWAN). A member of staff from Monash visited Warwick to give a seminar on LGBTUA+ and discussions are also in progress on some joint initiatives. | Warwick staff are treated with the same standards at partner institutions as they are at Warwick. | Equality and Diversity Committee | Annually July 2017 and 2018 |
| 6.2 NEW | Enhance Equality Objectives 2016-2020 in line with University strategy. | Create a measurable objective on Equality and Diversity that will be embedded into all six goals of the University Strategic Plan. | The Equality Objectives were reviewed for 2016-2020 and progress is monitored annually and reported at the Equality and Diversity Committee, Sentate and Council. In line with the public duties of the Equality Act 2010, these ojectives are in the public domain and can be viewed: https://warwick.ac.uk/services/equalops/equalityobjectives The University strategy has been revised in 2018 and the equality objectives have been be reviewed, updated and aligned as necessary and will be further updated in 2020. | All six goals of the University Strategy to have Equality and Diversity elements embedded. | The Provost (as Chair of the Equality and Diversity Committee) | Annually July 2017 and 2018 |
| 6.3 NEW | All Equality and Diversity papers are above the line at University meetings. | Ensure that Equality and Diversity appears as an ‘above the line’ agenda item at all relevant university committees, including Senate and Council. | The Equality and Diversity Committee Reports have all been above the line at Steering since 2017. The Equality and Diversity Committee Reports have all been above the line at Council since 2017 except for one meeting in May 2018 where it was originally planned to be above the line but with the Chairs permission went below the line because the amount of business to be discussed. All of the Senate agendas from the start of 2017 have placed all Equality and Diversity papers above the line. 1 February 2017: Report from Equality and Diversity Committee, (S.33/16-17) 14 June 2017: Report from Equality and Diversity Committee (S.62/6-17) 5 July 2017: A report from the meeting of the Equality and Diversity Committee held on 12 May 2017 (S.90/16-17) 5 July 2017: The Annual Report on Equality and Diversity together with an oral report from the Provost (S.91/16-17) 24 January 2018: Report from the Equality and Diversity Committee (S.30/17-18) 13 June 2018: Report from the Equality and Diversity Committee (S.60/17-18) 4 July 2018: The Annual Report on Equality and Diversity together with an oral report from the Provost (S.68/17-18) | Council and Senate membership to have an appreciation of all equality and diversity activities. | The Provost (as Chair of the Equality and Diversity Committee) | Termly 2017 and 2018 |
| 6.4 NEW | By continuing participation in Charter Marks we aim to embed equality and diversity. | Ensure equality and diversity is embedded into all policies and procedures and training and development. Provision of resources and participation from institutional representatives to the Charters | Warwick continues to be proactive in working towards obtaining or maintaining various Charter Mark Status: Athena SWAN: Institutional Silver holder, plus 16 departmental awards between Bronze and Silver. Another 4 departments are working towards submissions for April 2019. Race Equality Charter Mark: Warwick’s Race Group, Chaired by Professor Pam Thomas, Pro-Vice-Chancellor (Research) has continued to meet regularly and a decision was made that until some of the key priority areas identified through our Race work have been addressed, the University would not submit for the Race accreditation at this time. Stonewall Workplace Equality Index: Warwick continues to submit to the Stonewall Workplace Equality Index and received a final ranking in the 2017/18 submittion of 163 out of 434 submissions (across all sectors). This was a rise of 64 places since the submission in 2016 and overall in the last 2 years Warwick has risen 181 places, which we see as a significant achievement. Indeed, Warwick scored the highest points in the new Trans Support Section of the Index (58%) compared to both Education (41%) and all Sectors (33%). The Stonewall Workplace Equality Index 2019 was submitted in September 2018 and the outcome will be known in January 2019. Workplace Wellbeing Charter: Warwick was successful in achieving the Workplace Wellbeing Charter Mark (renewble every 2 years) and was awarded this accreditation at an awards ceremony on Monday 22 May 2017. The Charter gives employers an opportunity to demonstrate their commitment to the health and well-being of their workforce, and gives clear guidance on how to make workplaces a supportive and productive environment in which employees can flourish. The Charter has three standards: Commitment, Achievement and Excellence and the University has achieved the following levels: - Leadership – Achievement - Absence Management – Achievement - Mental Health and Wellbeing – Commitment - Smoking and Tobacco related ill-health – Achievement - Physical Activity – Achievement - Healthy Eating – Commitment - Alochol and Substance Abuse – Commitment - Health and Safety - Excellence HR Excellence in Research: This document lists progress made against the HR Excellence in Research Action Plan. Disability Standards: Work has begun in April 2018 to work towards the Disability Standards. Warwick intends to undertake a self-assessment exercise against the criteria with a view to submitting for the accreditation in 2019/20. | Continued success in Charter Mark submissions by increasing the number of departments with Charter Mark awards. | HR LDC Research Committee | Athena April and November each year. Race February and July each year HR Excellence January 2017. Stonewall September each year. |
| F. IMPLEMENTATION AND REVIEW |  |  |  |  |  |  |
| PRINCIPLE 7: The sector and all stakeholders will undertake regular and collective review of their progress in strengthening the attractiveness and sustainability of research careers in the UK |  |  |  |  |  |  |
| 7.1 NEW | Engagement and participation of internal stakeholders who support and develop research active staff. | Monitoring, evaluating and improving the provision for research active staff in a dynamic and demanding research environment. | The Institute of Advanced Study (IAL) and International Strategy and Relations (ISR) secured funding to establish short-term fellowships (Rutherford Fellows) with four strategic internation partner institutions: Federal University of Minas Gerais (Brazil), Shanghai Jiao Tong University (China), University Paris Seine (France) and Vrije Universiteit Brussel (Belgium). 12 Early Career researchers from the four international partner institutions have been awarded three month placements at Warwick to catalyse long-term interdisciplinary collaborations and undertake training activities to support their career development. Warwick was awarded the highest number of Rutherford Fellowships of all universities who applied to the strategic grant scheme, which is managed by Universities UK International. The Fellows bring complementary skills and synergistic approaches to their Warwick colleagues in collaborating departments. By creating greater mpact for existing projects or establishing the feasibility of new projects, urther strengthening the breadth and depth of collaboration with our trategic international partners. Public Engagement team and Science Faculty supported ‘Voices of Young Science’ national media and engagement training in June 2018 for ECRS Post Docs and PhD students. Warwick hosts the Midlands workshop. We have had 6 foreign visiting academics attend our L&D training initiatives but also a number of visits for the University of Cape Town and Sri Lanka. | Successful collaborations Showcasing Profile Warwick | Institute of Advanced Studies Institute of Advanced Teaching and Learning Warwick Ventures Library LDC HR R&IS Public Engagement Unit Research Committee PVC for Research | Available for take-up throughout academic year and reported annually. |
| 7.2 NEW | Engagement and participation of external stakeholders who support and develop research active staff. | Monitoring, evaluating and improving the provision for research active staff in a dynamic and demanding research environment. | See 4.1 above | Successful collaborations Warwick research active staff profiling opportunities. | Midlands Researcher Development Forum Funding Bodies Appropriate regional and national research related stakeholders. | 2017 onwards |