## To be completed
Name of Project | Date | Completed by (name & company)
Awareness to Estates Office Environment Commitment
A copy of the University of Warwick Estates Office Policy has been emailed to the site manager t be retained and displayed on site | No | To be assessed
The link to the Estates Office Environmental staff induction is sent to the site manager. It will be expected the site manager confirm to the Estates project manager that the induction has been completed. The contractor should extend the induction to its staff and subcontrcators unless evidence of sufficient training is witnessed by the roject manager. | No | To be assessed
Water pollution & contaminated land |  |  | Yes
Is the work to be carried out near to or adjacent to rivers, lakes or streams? | Yes | Obtain written consent from Estate Office of authority to work in this area and obtain a copy of EA Works and maintenance in or near water PPG5 from The Estates Office | No
Will the work produce any discharge of water or silt into drains, watercourses, soakaways or sewers? | Yes | Obtain EA and Estates Office written consent for discharge of water to land or watercourse. Obtain Estates Office written consent for discharge of water to foul sewer | TBC
Have drains, sewers and soakaways been identified | Yes | Ask Estates Office for drawing showing these. Also, refer to Estates Office Env Procedures: 3 - Site Oil & Fuel Controls; 4 - Env Spill Controls | None on site
Will dewatering of excavations be required? | Yes | Obtain EA and Estates Office written consent for discharge of water to land or watercourse. Obtain Estates Office written consent for discharge of water to foul sewer | Unknown
Is fuel or oil stored on site? | Yes | Obtain COSHH assessments. Refer to Estates Office Env Procedures: 3 - Site Oil & Fuel Controls; 4 - Env Spill Controls. Produce documented emergency spill response plan for site.
Are there any known contaminants, including asbestos on site or in the ground? | Yes | Stop work an contact Estates Office project manager. If asbestos is suspected, stop work and contact Estates Office Asbestos Manager
Ecology
Are there any site specific environmental information from the University | Yes | Raise query with Estates Office prior to starting work and reflect any applicable instructions in methodology
Are birds nests or any visible ecological hazards present in the site? (state location) | Yes | Raise query with Estates Office prior to starting work and reflect any applicable instructions in methodology. Do not start work if there are suspected nesting birds and protected species
Are any grassed areas to be used for material storage? | Yes | Find alternative hardstanding storage areas. If not possible, gain authorisation to work from Grounds and Gardens Manager prior to occupation
Are works taking place near trees and in compliance to BS 5837 to provide sufficient tree protection areas? (refer to Protection of Trees – Environmental Guidance Note) | Yes | Check Contractor complies with any TPO & BS 5837:2012. Root protection areas (RPA) are calculated by qualified Arboriculturist. Implement Tree Protection Plan. Arboriculturist inspect site for possible root damage
Is there Japanese Knotweed on site? | Yes | Raise query with Estates Office prior to starting work and reflect any applicable instructions in methodology
Public nuisance
Will there be a noticeable increase in dust, smoke, odour or light to local residents? | Yes | Consider alternative working working methods which minimuse these. Seek advice from Estates Office
Will there be a noticeable increase in noise and vibration to local neighbours | Yes | Consider alternative working working methods which minimuse these. Seek advice from Estates Office
Material usage & waste
Is the contractor responsible for providing waste management (eg skips) on site? | Yes | Refer to Estates Office Env Procedure: 3 - Site Oil & Fuel Controls; 4 - Environmental Spill Controls. Provide copies of all waste transfer notes
Will there be potentially polluting materials & chemicals stored on site? | Yes | Refer to Estates Office Env Procedure 2 - Waste Management. Obtain and retain on site copies of all COSHH assessments
Will more hazardous waste be produced on the site? | Yes | Refer to Estates Office Env Procedure 2 - Waste Management. Provide proof of waste analysis to WM3 standard and copies of consignment notes (inc part E)
Carbon management
Is carbon being measured on this project? | Yes | Ensure all material, transport, energy and carbon data is calculated and retained
Signed on behalf of contractor | Signed on behalf of University Estates Office
Key to document prefixes: EE=Environmental Policy; EM=EMS Manual; ER=EMS Register; EP=EMS Procedure; EL=EMS Legal Register; EK=EMS KPI Objectives & Programmes; EO=Environmental Report; EF=Environmental Form; EA=Environmental Audit; ET=Environmental Training; EC=Environmental Record; EV=EMS Management Review