## Site Env Audits
Function | Date | Auditor(s) | NC/Obs | Details of NC/Obs | Type | Causation type | Action required | Responsibility | Date for | Completed | Date | Corrective action taken | Preventative action carried out | Causation type | Action with | Chased by email | 2nd Chase by email | Response to email |  |  | Continued action | Chased by email | 2nd Chase by email | Response | Further Response | Further chase by email | Response | Response
| Raised | [7 empty] | completion |  | Completed
Facilities | 2013-08-22 |  | 001 | The University Sports Ground new interceptor does not have an EA discharge permit. | NC | Water |  | S Hughes | 2013-12-23 | N | 2013-11-25 | The system has been tested but not in use. Roger to display memo to his staff. | Permit to be obtained prior to commissioning. Update; 13/05/14 Action: S.Hughes to confirm with Dave Inman. | Oil, fuel & chemicals | S.Hughes | 2014-05-29 | 2014-06-04 |  |  | ongoing | S.Hughes to confirm with Dave Inman. | 2014-06-23 | 2014-07-01 | June - S.Hughes has contacted David Inman regarding the University Sports Ground interceptor having an Environment Agency discharge permit. Roger Boxall is liaising with the Environment Agency to discuss this as there is no consent in place. The group stated that a permit is needed before the September Audit. SH to follow-up with Roger Boxall. | July - JC & David Inman spoke with Roger Boxall regarding above. The Environment Agency has visited the site and has stated verbally that they are happy for the discharge to go into the woodland. Roger Boxall will chase the Environment Agency regarding written confirmation of this and whether a permit is needed. The interceptor will need to be cleaned periodically and Roger Boxall will ensure this takes place through the Grounds team schedule. |  | August - The permit for water being discharged at the Grounds and Gardens depot is being progressed by David Inman and will pass the task to Facilities when sufficient information is gathered. Written confirmation from the Environment Agency as to whether a permit is needed for discharge has not been received as of yet. Action: Debbie Smith has been asked to speak to Roger Boxall regarding this and for him to check with the Environment Agency for written confirmation. A target date of before the 9 September Audit was given for this action to be completed | September - Roger Boxall stated: The EA do not require a Permit or a Consent for the water discharged from our wash down facility. They have asked for confirmation of the water purity which is discharged from the water treatment system. I have placed an order with Rochester Midland Corporation Ltd to take a water sample and analyse it. The sample was taken last week and we await the results. I will show the environmental auditor a copy of the Rochester Midland Corporation Ltd order tomorrow (9/9/14).
Facilities | 2013-08-22 |  | 001 | Drainage gulley's would benefit from colour coding to identify surface water and foul sewers. | Obs | Water |  | M Hubbard/ D.Stiles | 2013-12-23 | Y | 2014-01-30 |  | Colour code Boiler House and Westwood fuel store drainage in priority Estates project is being raised to develop and manage a comprehensive plan to 1) survey drainages and interceptors around the campus, and add to estates services database 2) identify and colour code surface and storm drainages 3) Implement a suitable preventive maintenance plan. Update 13/05/14 Action M.Hubbard to confirm that interceptors have been cleared out. Action; D.Stiles to progress items 1 and 2 with A.Powell and A.Piper for A.Bishop to progress through consultants. Item 3 D.Stiles to contact John Stranks. | Systems | M.Hubbard | 2014-05-29 |  | 29/5/14 Drainage gulley's would benefit from colour coding to identify surface water and foul sewers.[Mick Hubbard] in progress. | 29/5/14 M.Hubbard to confirm that interceptors have been cleared out.[Mick Hubbard] completed - see attached document | see sheet in Actions folder | M.Hubbard to confirm that interceptors have been cleared out | M.Hubbard confirmed that interceptors have been installed and J.Cardinal to update D.Inman. |  |  | 02/07/2014 David Inman updated by email.
As Above | [13 empty] | Systems | D.Stiles | 2014-05-29 | 2014-06-04 | Items 1 and 2 - D.Stiles emailed A.Powell 2/6/14 | Items 3 - D.Stiles emailed J.Stranks and Kevin Richardson – 4/6/14 | see email in Actions folder | D.Stiles to progress items 1 and 2 with A.Powell and A.Piper for A.Bishop to progress through consultants. Item 3 D.Stiles to contact John Stranks. | 2014-06-23 | 2014-07-01 | June - Items 1 & 2 Ongoing, Duncan in communication with Alan Powell. Item 3 MH to discuss programme for interceptors with JStranks
Facilities | 2013-08-22 |  | 002 | The campus interceptors would benefit from being included in planned preventive maintenance schedules. | Obs | Water |  | M. Hubbard | 2013-12-23 | Y | 2014-01-30 |  | Refer to above preventive action plan | Training | A.Lawry | [9 empty] | M.Hubbard confirmed that interceptors have been installed | Infrastructure drawings are with Alistair Lawry for update. Once all drawings will be updated it may not be necessary to paint drainage covers.
Facilities | 2013-08-22 |  | 003 | Spill kits are not located on site | Obs | Oil/Fuel |  | S Hughes | 2013-12-23 | Y | 2014-01-30 | Action Completed. Stephen is procuring additional kits, signs and granules as well as fire extinguishers | Additional spill kits are available and in the process of being allocated to electricians vans. A review of spill kits location around critical areas has taken place. Regular review will take place. Update 13/05/14 Action: S.Hughes to provide a list of fixed split kits and discuss with Katia Merine to set up a process for replenishing stock. Action: M.Hubbard to add onto Bob Mount's list of tasks to check all fixed spill kits. | Ecology | S.Hughes | 2014-05-29 | 2014-06-04 |  |  |  | S.Hughes to provide a list of fixed split kits and discuss with Katia Merine to set up a process for replenishing stock. | 2014-06-23 | 2014-07-01 |  | July - This action can be closed as SH has discussed with Katia Merine regarding fixed spill kits. There is a minimum number on the system and then they will get re-ordered. SH stated he would do a test purchase to check the system is working properly. SH also noted good practice, there are service labels at the boiler house, which are a good idea. The large spill kits have tie-wrapped sealed tops. Action: Discharged
As Above | [13 empty] | Ecology | M.Hubbard | 2014-05-29 |  | 29/5/14 M.Hubbard to add onto Bob Mount's list of tasks to check all fixed spill kits.[Mick Hubbard] completed |  |  | M.Hubbard to add onto Bob Mount's list of tasks to check all fixed spill kits. | complete
Facilities | 2013-08-22 |  | 005 | Clarification is required whether an EA exemption is required for composting | Obs | Waste |  | S Hughes/ R Boxall | 2013-12-23 | Y | 2013-11-28 | D Inman confirmed on EA public register that a T23 exemption (Ref EPR/KE5753XR/A001) is in place | Updated 13/05/14 Action: J.Cardinal to create a central location for this information. | Waste | J.Cardinal | 2014-05-29 | 2014-06-04 |  |  |  | J.Cardinal to create a central location for this information. | 2014-06-26 |  | June - Copies of permits will be obtained from the Environment Agency | July - Action: Discharged for composting exemption. All permits/exemptions are to be kept on the Shared drive in the EMS section. JC will speak to David Inman on 21 July regarding which Environment Agency permits/exemptions we need to keep/obtain a copy of.
Grounds & gardens | 2013-11-25 |  | 4.2 | Drains not colour coded | Obs | Water |  | M Hubbard | 2014-01-10 | N |  | Acs above see 001. | Refer to above preventive action plan | Water | [10 empty] | This has not been fully completed. SH/GH stated this should be a measured approach around areas of risk mainly, such as at the Boiler House. This will also need to be refreshed and is therefore ongoing.
Waste | 2013-12-05 |  | OBS001 | No waste transfer note for ad hoc skip at Argent Court | Obs | Waste |  | E Idundun | 2014-01-10 | Y |  | Skip removed | Update 13/05/14: Action J.Cardinal to arrange tool box talks with Dave Inman. | Waste | J.Cardinal | 2014-05-29 | 2014-06-04 |  |  |  | J.Cardinal to arrange tool box talks with Dave Inman |  |  | June - This will be discussed with Dave Inman on 24/06/14 to be delivered on date to be confirmed? | July - Toolbox talks have taken place with Clerk of Works and will be organised with other sections. On 21 July a toolbox talk will take place with the Small Works team and discussions with Senior Project Managers. This is ongoing for future sessions to be organised between JC and David Inman.
Waste | 2013-12-05 |  | OBS002 | Collector of cooking oil unknown | Obs | Waste |  | E Idundun | 2014-01-10 | Y |  | Contractor is known. This process is outside Estates EMS | Update 13/05/14: Action S.Hughes to check with Mark Potter. | Waste | S.Hughes | 2014-05-29 | 2014-06-04 |  |  |  | S.Hughes to check with Mark Potter | 2014-06-23 | 2014-07-01 |  |  | 2014-08-15
Waste | 2013-12-05 |  | OBS004 | Nilwaste – no competency checks on persons advising on hazardous waste | Obs | Waste |  | E Idundun | 2014-01-10 | N |  | Supplier to give evidence of technical competency related to the Environment Agency standard WM2 (http://a0768b4a8a31e106d8b0-50dc802554eb38a24458b98ff72d550b.r19.cf3.rackcdn.com/LIT_5426_acd22f.pdf). It could be via experience as well as qualifications. | Update 13/05/14: Action S.Hughes to discuss and confirm with E.Idundun. | Training | S.Hughes | 2014-05-29 | 2014-06-04 |  |  |  | S.Hughes to discuss and confirm with E.Idundun | 2014-06-23 | 2014-07-01 |  | July - Nilwaste, no competency checks on persons advising on hazardous waste. SH will check with Ebiyon Idundun for copies of qualifications. JC/SH to ensure that this is discussed with David Inman on 21 July. | 15/08/2014 chased SH & JC | August -The group stated that there should be competency checks/audits on contractors. Internal audits could take place on contractors training records through the EMS. Action: DS will check if there is an environmental section in the CHAS system, in order to see if contractors can be checked for code of conduct and the way that they work in an environmental manner. There may need to be a paragraph in information issued to contractors asking them to be environmentally aware/sensitive. This will await DS discussion regarding the CHAS system. A target of the group’s next meeting given for an update.
Maintenance | 2013-12-05 |  | NC002 | Oil storage not compliant with Control of Pollution (Oil Storage) England) Regulations 2001 | NC | Oil/Fuel |  | S Hughes | 2014-01-10 | Y |  | Boiler House, Westwood and Cryfield are compliant double skin tanks. | Update 13/05/14. Action D.Stiles to arrange annual checks of the diesel tanks as part of the PPM process (Discuss with K.Richardson). | Oil, fuel & chemicals | D.Stiles | 2014-05-29 | 2014-06-04 | D.Stiles emailed Kevin Richardson – 4/6/14 |  | see email in Actions folder | D.Stiles to arrange annual checks of the diesel tanks as part of the PPM process (Discuss with K.Richardson). | 2014-06-23 | 2014-07-01 | June - This is not part of the PPM. A specialist needs to be appointed to write a specification for this. Richard Howard is recommended. Any objections by the group on 08/07/14? | July - DS asked whether Richard Howard should process the specification for annual checks of the diesel tanks. MS stated that Richard Howard would be able to specify the contractor. DS to discuss with Richard Howard. | 15/08/2014 chase DS for update | 22/08/14 DS emailed RH to discuss inspection of diesel tanks & the frequency & whether a PPM/Service contract is needed.
Maintenance | 2013-12-05 |  | OBS004 | Uneven road gulley surrounding will not allow drain cover to fit. | Obs | Water |  | M Hubbard | 2014-01-10 | Y | 2014-01-23 | New drain cover installed | Update 13/05/14. Action: M.Hubbard to confirm that drain cover fits correctly. | Site Management | M.Hubbard | 2014-05-29 |  | 29/5/14 Uneven road gulley surrounding will not allow drain cover to fit. M.Hubbard to confirm that drain cover fits correctly.[Mick Hubbard] I don’t think this is relevant anymore as we have a new interceptor fitted and Aco drain alongside the boilerhouse. |  |  | M.Hubbard to confirm that drain cover fits correctly. | complete
ISOQAR | 2014-01-07 |  | 2 | A management review to be held to review all aspects / clauses of ISO 14001 2004 with objective evidence | Obs | Systems |  | M Stacey | 2014-02-04 | Y |  | Completed. Minutes issued to Director of Estates for approval | Update 13/05/14. Action: J.Cardinal to update the policy manual. | Systems | J.Cardinal | 2014-05-29 | 2014-06-04 |  |  |  | J.Cardinal to update the policy manual. | 2014-06-26 |  | June - complete but needs to be approved by a member of the Environment Group, look at next meeting. Copy of manual in M drive/EMS/Corrective actions | July - complete & on intranet
ISOQAR | 2014-01-07 |  | 3 | A full EMS system audit to be conducted with audit reports available for review. | Obs | Systems |  | J Cardinal | 2014-02-04 | Y | 2014-01-27 | Audit completed without NC / Obs. Record available | Update 13/05/14. This item will be discussed as part of a wider meeting scheduled for July 2014. | Systems
ISOQAR | 2014-01-07 |  | - | It is recommended that a review of waste carrier (internal) licensing requirements is undertaken. | Obs | Waste |  | S Hughes | 2014-02-04 | Y | 2014-01-16 | University registered as a waste carrier broker (registration number CB/NM3647XW, expires 15/01/17) | Update 13/05/14. Action: S.Hughes to set up a reminder process with E.Idundun to re-register Dec 2016. | Waste | S.Hughes | 2014-05-29 | 2014-06-04 |  |  |  | S.Hughes to set up a reminder process with E.Idundun to re-register Dec 2016. | 2014-06-23 | 2014-07-01 |  | July - S.Hughes to set up a reminder process with E.Idundun to re-register Dec 2016. | 15/08/2014 SH chased for update
ISOQAR | 2014-01-07 |  | - | The siting of enhanced catchment, containment, MDS, and emergency requirements is recommended in the critical storage areas of bulk oils and fuels and vehicle cleaning areas. | Obs | Oil/Fuel |  | S Hughes | 2014-02-04 | Y |  | Refer to items 001, 002 and 003 23/12/13 | Update 13/05/14. Action: S.Hughes to raise a docket to fix the spill kits within the boiler room. | Oil, fuel & chemicals | S.Hughes | 2014-05-29 | 2014-06-04 |  |  |  | S.Hughes to raise a docket to fix the spill kits within the boiler room | 2014-06-23 | 2014-07-01 |  |  | 15/08/2014 SH chased
Internal EMS Audit EA-EMS-Jan14-01 | 2014-01-21 |  | Obs001 | Allocation of responsibilities not defined in EF-05-Jan2014 Environmental Management Programme | Obs | Systems |  | J Cardinal | 2014-01-31 | Y | 2014-01-27 | Audit completed without NC / Obs. Record available | Update 13/05/14. Action: J.Cardinal to check and confirm. | Systems | J.Cardinal | 2014-05-29 | 2014-06-04 |  |  |  | J.Cardinal to check and confirm. | 2014-06-26 |  | June - To be progressed further by David Chapman at meeting on 11/08/2014 |  | Progress?
Internal EMS Audit EA-EMS-Jan14-01 | 2014-01-21 |  | Obs002 | Obsolete copies have been retained on the intranet page, but are not identified as being obsolete. | Obs | Systems |  | J Cardinal | 2014-01-31 | Y | 2014-01-27 | Duplicate copy withdrawn | Update 13/05/14. Action: J.Cardinal to contact Sam Boulby to remove from system. | Systems | J.Cardinal | 2014-05-29 | 2014-06-04 |  |  |  | J.Cardinal to contact Sam Boulby to remove from system. | 2014-06-26 |  | June - There is a section for older versions of EMS documents on the intranet page which can only be accessed by certain people.
Internal EMS Audit EA-EMS-Jan14-01 | 2014-01-21 |  | Obs003 | No test of the emergency plan has been carried out. | Obs | Systems |  | S Hughes | 2014-01-31 | y | 2014-01-30 | STAGE 1 A desktop emergency exercise has been organised with Security, maintenance, facilities and sustainability teams. A process has been identified and agreed for the reporting and response to emergency spills in critical locations. | Display procedures will be improved with pictures/pictograms. STAGE 2 (February 2014) Emergency procedures will be tested with staff to assess the process flow and effective communication. Update 13/05/14. Action: D.Stiles to organise stage 2 and hold an initial meeting with S.Hughes and M.Kennell, Head of Security. | Site Management | D.Stiles | 2014-05-29 | 2014-06-04 | 04/06/14 Meetings have been held with John Phillips, Health & Safety Systems and Audit Manager and Joy Findlay, Assistant Registrar (Risk, Continuity and Information Security) – See communication emails. |  | see email in Actions folder | D.Stiles had a Emergency testing meeting with Joy Findlay, Assistant Registrar (Risk, Continuity and Information Security) to consider a desk top stage 2 exercise. |  |  | June - Duncan in communication with Joy Findlay. Can the recent bus fire incident be used as an example of this? Duncan to further consult with Chris Mayfield. | July - Extract of information supplied by Chris Mayfield. A statement from Kevin Richardson of his actions on that day is needed to support with drainage plans and supporting the Environment Agency. DS to chase. | 15/08/2014 DS chased for K.Richardson update | 26/08/14 DS & KR added information to Chris Mayfield's report and this is saved on shared drive in corrective actions.
Cleaning | 2014-01-27 |  | None
Environmental Management Group | - |  | - | ef-02-environmental_work_planning_checksheet.xls to be added to construction projects tender documentation + guidance received from D. Inman | Obs | Systems |  | C. Carrington / Projects | 2014-07-16 | started |  |  | Action: To be added in Concerto check lists | Systems | Projects + J. Cardinal | [9 empty] | Concerto check lists for small and large projects are being updated
Environmental Management Group | - |  | - | Environment Management Plan to be issued to designers on appointment | Obs | Systems |  | C. Carrington / Projects + Purchasing | 2014-07-16 | from 24/02/14 |  |  | Action: To be added in Concerto check lists + necessary guidance, preliminaries and tender documentation | Systems | Projects + J. Cardinal | [9 empty] | Guidances and preliminaries to be developed Generic statement has been included in NAIC Employers Requirement.
Environmental Management Group |  |  |  | Environment Management Plan to be issued to contractors at tender stage as part of specification | Obs | Systems |  | C. Carrington / Projects + Purchasing | 2014-07-16 | from 24/02/14 |  |  | Contracts preliminary information packages could include a the check list in addition of statement. Final decision not made | Systems | Projects + J. Cardinal | [9 empty] | Guidances and preliminaries to be developed Generic statement has been included in NAIC Employers Requirement.
Environmental Management Group |  |  |  | Site waste management template to be issued | OFI |  |  | C. Carrington / Projects | 2014-07-16 | from 24/02/14 |  |  | Action: to be issued to designers and to contractors To be reviewed. No final decision not made | Site Management | Projects + J. Cardinal | [9 empty] | Guidances and preliminaries to be developed
Environmental Management Group |  |  |  | Clerk of work competencies enhancement: In view to better support contractors environmental awareness and commitment, University clerk of work should be conversant with all exceptations requested from suppliers in EF-02 Environmental Work Planning Checksheet | Obs |  |  | C. Carrington / Projects | 2014-06-24 | 2014-06-01 |  |  | To deliver tool box talk to Surveyors and Clerkof works Tool box talks delivered to part of clerk of works and surveyors. Rainng certificates awaited | Training | Projects + J. Cardinal | [8 empty] | Done for some clerk of works ne for Surveyors | Further material to be added to Moodle site
Environmental Management Group |  |  |  | The auditor was looking for evidences of a “thought process” linking Estates policy and Impacts & aspects register to project planning. This has been demonstrated for large projects (Bluebells, Sherbourne and WBS ph3b) through design team meeting minutes. | OFI |  |  | Environmental Management Group | 2014-11-01 |  |  |  | Environmental Management Group to consider when reviewing Impacts and Aspects | Systems | [10 empty] | Strategies and guidances incorporated in Concerto to be reviewed with Estates office consultant.
Environmental Management Group |  |  |  | Should the Environment Group be extended with a represented of the project team (Chris or senior project manager)? | OFI |  |  | Envt Group |  | Y |  |  | Action: To be discussed and assessed at Monthly meeting | Systems | Gez Hunter represents projects | [9 empty] | Gez Hunter seconded to the Group
Environmental Management Group |  |  |  | To make available Glycol COSHH data sheet Where are all COSHH data sheets stored? Who is responsible for COSHH data sheets? What procedure if there is a spillage of glycol in an AHU on a roof - plant room? Glycol and heating fluid inhibitor: to receive advice from David Inman on required action + guidance received from D. Inman | Obs |  |  | Envt Group to confirm |  |  |  |  | Action: to review starting by order of risks priority (risk register). Action: to assess risks before being planned. Action: Inhibitor fluid: to obtain COSHH data sheet from G. Lynex | Oil, fuel & chemicals | [10 empty] | No progress
Environmental Management Group |  |  |  | to clarify status and policy for PAT testing including fixed and mobile equipment (i.e. equipment in Argent Court Annex Pat testing certificate elapsed January 2014) | OFI |  |  | M. Hubbard | 2014-11-01 |  |  |  | To consider if there is a requirement to link PAT testing with ISO 14001 aspects & Impacts | Site Management
Environmental Management Group |  |  |  | ET-04 Environmental Induction Lesson Plan: list all names | Obs |  |  | Envt Group |  | Complete |  |  | M Stacey email 20/01 Jayne collects evidences | Training
Corrective action |  |  |  | Cogenco - OSL: to update their procedures to ensure temporary measures are in place until Boiler House tank is bunded and areas secured | Obs |  |  | J Cardinal |  | Update = Complete Display = to be done |  |  | Meeting held 28/01 | Site Management | Cogenco has issued new procedures that must be displayed on main and east site. + to organise tool box talks to ensure BST staff are aware of the procedure
Preventive action |  |  |  | To confirm storage location for CHP maintenance files | OFI |  |  | M. Hubbard + J. Cardinal | TBA |  |  |  | To be finalised when Energy Centres manager will be in post | Site Management
Environmental Management Group |  |  |  | OFI It is recommended that supplier review requirements / qualifications are reviewed on critical subcontractors, in particular applications that include gas and electrical installations and subsequent testing equipment calibrations. | OFI |  |  | J. Cardinal A.Gurney |  |  |  |  | To be discussed with A. Gurney during sustainable procurement meetings in association with actions in progress regarding vendor questionnaire | Systems | Opportunities for Improvement from certification audit. Member of Envmt Group to liaise with A.Gurney
Environmental Management Group |  |  |  | Verify Drain R Us supplier approval and improvement plan to progress vendor questionnaire return (invite for a progress meeting , perhaps adopting our “Environmental management Plan” | Obs |  |  | J. Cardinal + A. Gurney | [5 empty] | Systems
Environmental Management Group |  |  |  | define plan to continue collecting vendor questionnaire feedback from suppliers base in addition to the 10 already completed (waste, civil contractors…) | OFI |  |  | J. Cardinal + A. Gurney | [5 empty] | Systems | [9 empty] | List supplied to procurement team based on spend. | Order to be reviewed based on criticality of suppliers (see Excel line 48)
Environmental Management Group |  |  |  | Modify Policy Manual to reflect change of certification scope (see certificate) | Obs |  |  | D. Inman / J.Cardinal | 2014-06-24 | Y |  |  |  | Systems
Environmental Management Group |  |  |  | To clarify roles and responsibilities for all documentation management and actions/audits tracking | Obs |  |  | Envt Group |  | Y |  |  |  | Systems | Denise & Envmt Group
Environmental Management Group |  |  |  | M. Stacey requested that all Estates staff complete a refresher EMS training. | PFI |  |  | J.cardinal | 2014-09-09 |  |  |  | Action J.Cardinal to organise with support from Denise Clarke and Adrian Bishop to record a process of who within Estates have completed the training. | Training |  | 2014-06-26 | [8 empty] | July - Induction video to be updated after August management review and posted on Moodle | August - Denise and David Chapman to review how staff can be "subscribed" to Moodle
Environmental Management Group |  |  |  | J.Cardinal raised that he will contact Sam Boulby to obtain an update on the use of the ISO logos for the next meeting. | OFI |  |  | J.cardinal | 2014-09-10 |  |  |  |  | Site Management |  | 2014-06-26 |  | 02/07/2014 Joel emailed Sam Boulby to check. | [6 empty] | July - Current ISOQAR logos submitted to Facilities and rejected (insufficient quality) | August - Joel and Denise to contact ISOQAR to obtain master file to manufacture logos through facilities vehicles livery supplier | 6/9/14 JC emailed ISOQAR for advice as to whether can use logo on vehicles and be manufactured by a subcontractor.
Environmental Management Group |  |  |  | J.Cardinal raised that we need to embed the Environmental approach across the University, over it was agreed that Estates should obtain an update of Environmental business planning from departments. | OFI |  |  | J.cardinal | 2014-12-31 |  |  |  | Action J.Cardinal to contact Julie Brannon, Health and Safety Advisor to discuss. | Systems |  | 2014-06-26 |  | 02/07/2014 Joel not spoken with Julie Brannon, will update when he has. | [6 empty] | 02/07/2014 Joel not spoken with Julie Brannon, will update when he has.
6 month Management Review August 2014 | 2014-08-06 |  |  | List of permits | OFI |  |  | Environmental Management Group | 2014-10-14 |  |  |  | Review list f applicable legislation to review list of permits held |  | Action Environmental Management Group to identify list of possible permits that should be required (October 2014).
6 month Management Review August 2014 | 2014-08-06 |  |  | List of permits documentation improvement | OFI |  |  | J. Cardinal | 2014-10-31 |  |  |  | Improve format of legislation register if appropriate |  | Action JC: http://www2.warwick.ac.uk/about/environment/warwick/ems/er-02-v03-environmental_register_of_legislation.xls can be clarified to indicate when an existing legislation is amended (i.e. highlight the difference between lines 4 and 9 in the Water section). The document also needs a cover with the date
6 month Management Review August 2014 | 2014-08-06 |  |  | Emergency procedure update | OFI |  |  | D. Stiles | 2014-12-31 |  |  |  | Update emergency procedure with central university feedback and input |  | The recent bus fire incident will be used and debriefed to review and improve the emergency plan where appropriate. Action Duncan to recommend timing
6 month Management Review August 2014 | 2014-08-06 |  |  | Emergency management improvement | OFI |  |  | D. Stiles J. Cardinal | 2014-12-31 |  |  |  | train necessary staff on emergency procedure update using Moodle |  | The spill response emergency planning video relating to this, the link to which is held on the EMS section of the intranet can be used to help staff with this. Including security gatehouse staff in this would be of use since they deal with out of office hours emergencies, so such a test could check their awareness of the requirement to ring the on-call BST should a pollution incident occur out of hours. Action Duncan/Joel to liaise with Security team and advise if security staff should be added in Moodle to monitor availability and staff feedback.
6 month Management Review August 2014 | 2014-08-06 |  |  | Handling of contaminated land risks | OFI |  |  | D. Stiles J. Bunn | 2014-10-31 |  |  |  | It is possible some contaminated material remain in the ground around older campus buildings that could be revealed in the future. Jason Bunn to identify how to best inform Grounds staff |  | Action Jason (JB): to review HSE advice for grounds activities
6 month Management Review August 2014 | 2014-08-06 | [6 empty] | D. Stiles J. Bunn G. Hunter D> Mace | 2014-10-31 |  |  |  | It is possible some contaminated material remain in the ground around older campus buildings that could be revealed in the future. Dave Mace to inform contractors in the same way as Grounds staff |  | Action D. Mace + C. Mahony: to provide information on contamination risks in the ground to contractors in works specification packages
6 month Management Review August 2014 | 2014-08-06 | [6 empty] | D. Stiles J. Bunn | 2014-10-31 |  |  |  | Action Jason (JB) to consider Asbestos awareness toolbox talk for grounds staff. Foreman/Supervisors to provide formal training, in order for them to advise the grounds staff in the future. JB offers awareness training to all University departments, but only to specific people that head of department suggest. |  | Action Jason (JB) to consider Asbestos awareness toolbox talk for grounds staff. Foreman/Supervisors to provide formal training, in order for them to advise the grounds staff in the future. JB offers awareness training to all University departments, but only to specific people that head of department suggest.
6 month Management Review August 2014 | 2014-08-06 | [6 empty] | D. Stiles | 2014-10-31 |  |  |  | Action Duncan: to review roles & responsibilities for recording waste transfer processes and records. And whether Planning & Compliance should host all these notes/copies of notes in a central location. |  | Action Duncan: to review roles & responsibilities for recording waste transfer processes and records. And whether Planning & Compliance should host all these notes/copies of notes in a central location.
6 month Management Review August 2014 | 2014-08-06 | [6 empty] | J. Cardinal D. Stiles A, Gurney | 2014-12-31 |  |  |  | Action Procurement = to consider extending tender due diligences to professional and technical qualification and how to ensure it take place for critical services |  | Action Procurement = to consider extending tender due diligences to professional and technical qualification and how to ensure it take place for critical services
6 month Management Review August 2014 | 2014-08-06 | [6 empty] | J. Cardinal D. Stiles A, Gurney | 2014-12-31 |  |  |  | In association with the above as there is no formal legislation requirement within ISO 14001 it is recommended that competency records and qualifications for both internal and subcontracted maintenance personnel are regularly reviewed and maintained (reference clauses 4.4.2 –training and 4.4.7 –Emergency preparedness and Response) = Action Planning & Compliance to introduce sample random testing + aim to introduce a Planning & Compliance database module |  | In association with the above as there is no formal legislation requirement within ISO 14001 it is recommended that competency records and qualifications for both internal and subcontracted maintenance personnel are regularly reviewed and maintained (reference clauses 4.4.2 –training and 4.4.7 –Emergency preparedness and Response) = Action Planning & Compliance to introduce sample random testing + aim to introduce a Planning & Compliance database module
6 month Management Review August 2014 | 2014-08-06 | [6 empty] | D. Stiles M. Hubbard | 2014-12-31 |  |  |  | Action Environmental Group to review suppliers / contractors competencies in maintenance contract preliminaries documentation |  | Action Environmental Group to review suppliers / contractors competencies in maintenance contract preliminaries documentation
6 month Management Review August 2014 | 2014-08-06 | [6 empty] | G. Hunter D. Mace, C. Mahony | 2014-12-31 |  |  |  | Action D. Mace, C. Mahony to review suppliers / contractors competencies in preliminaries documentation |  | Action D. Mace, C. Mahony to review suppliers / contractors competencies in preliminaries documentation
6 month Management Review August 2014 | 2014-08-06 | [6 empty] | J. Cardinal M. Jarvis | 2014-10-31 |  |  |  | Provide information in time for October Environmental Group meeting |  | Action JC; to pursue action initiated with Severn Trent Water to review suitability discharge consents.
6 month Management Review August 2014 | 2014-08-06 | [6 empty] | D. Stiles | 2014-12-31 |  |  |  | Consider if contractors legal compliance should be audited by Estates office in addition of contractors commitment in contracts |  | The main waste contractors should be formally audited for legal compliance by the Waste and Recycling Manager. Action Duncan / Stephen Hughes to advise
Transport TL-14-01 | 2014-06-27 | E. Idundun | 3 points | Obs or NC ????? 001 Vehicle appears to have a valid MOT as indicated on the database; however the MOT certificate was not seen on file. |  |  | Ensure that all vehicle MOT certificates are filed for reference. | S. Hughes / G. Hine |  | ?????
|  |  |  | Obs 002 The designated washing bay used has no signage indicating that it is a washing bay and that washing and cleaning should only be carried out in the bay. |  |  | Provide appropriate signage to identify washing bay and instructions saying that washing and cleaning should only be carried out in the bay. | S. Hughes / R. Boxall |  | ?????
|  |  |  | Obs 003 There is no fence or barrier to prevent spray or wind drift out of the designated area |  |  | An assessment to be carried out to identify if a fence or barrier is required. | S. Hughes / R. Boxall |  | ?????
Transport TL-14-01 | 2014-06-27 | E. Idundun | 1 Obs | Obs001 No procedure for washing this vehicle and potentially vehicles utilised by the Electrical Section of the Estates Office. |  |  | An assessment into the washing of vehicles within this section as to where it can take place and the frequency. | [5 empty] | Alternative options to be considered as there is no local car wash facility
Cleaning & Housekeeping - Arts Centre | 2014-08-24 |  | None
Cleaning & Housekeeping - University House | 2014-08-24 |  | None
Grounds and Gardens | 2014-08-28 | D. Stiles | 4 Obs | Obs001 Grounds staff were instructed by tool box talk how to use spill kits and video on the Estates Web site was shown to staff. | Obs |  | Practical demonstration of spill kits for a future tool box talk. | S. Hughes / R. Boxall | 2015-05-31
|  |  |  | Obs002 Grounds and Gardens have a list of locations with spill kits but no Estates spill kit register was available for Roger to include his list. | Obs |  | Estates spill kit register required to facilitate replenishment | S. Hughes | 2015-05-31 |  |  |  | S. Hughes to design a memo for all supervisors to be aware of spill kits and replenishment
|  |  |  | Obs003 Roger confirmed that there is not a current process to replenish fuel spill kits. | Obs |  | Inspection and replenish fuel spill kit process required for Grounds and Gardens. | Procurement |  | Y |  | Minimum of 6 spill kits held in stores
|  |  |  | Obs004 We did discuss the location of the Grounds and Gardens machinery asset list, I checked with Kevin Richardson, PPM Surveyor and the list was on the Estates M Drive computer system. The process for servicing and maintenance of grounds equipment needs to be fully understood and where records are located on servicing. | Obs |  | Process to be clarified for maintaining gardening equipment through the PPM system and where service records are stored. | S. Hughes / R. Boxall |  | Y |  |  | Service are controlled by the Grounds & Garden team (hard copies at Grounds depot)
Post and Portering | 2014-12-22 | D. Stiles | 1 NC and 2 Obs | NC001 Induction process did not include environmental awareness as a subject. | NC |  | Induction process to be drafted to now include Environmental awareness. | S. Hughes / G. Hine | 2015-05-31 |  |  | Induction program amended | There is a draft Estates office induction template under review |  | D. Stiles / A. Dumper
|  |  |  | Obs001 The manager was not aware that an Environmental Management plan was available. | Obs |  | Joel Cardinal to forward a copy of the Environmental Management plan to Brendan Cassidy and David Smith | S. Hughes / G. Hine | 2015-05-31
|  |  |  | Obs002 It was discussed that he post team collect each day from the Wallsgrave Hospital and this service is not always required. | Obs |  | A review of the collection and delivery frequency at Wallsgrave Hospital required. | S. Hughes / G. Hine | 2015-05-31
Utilities | 2015-02-05 | D. Stiles | 1 Obs and 1 NC | Obs001 Invoices were provided by the officer going through files, the officer advised that the invoices are all kept electronically | Obs |  | Review in 3 months to check if the electronic system to record invoices are now in place. | J. Cardinal/M. Jarvis | 2015-06-10
|  |  |  | NC001 Water extraction license not available to inspect. | NC |  | Licences required from the Environment Agency and stored in a central accessible location. | J. Cardinal/M. Jarvis | 2015-06-10
Utilities | 2014-06-17 | M. Stacey | 5 Obs | Obs001 Billed electricity could be checked against consumption | Obs |  | To consider if regression analysis to be implemented | J. Cardinal | 2015-06-10
|  |  |  | Obs002 Billed gas could be checked against consumption | Obs |  | To consider if regression analysis to be implemented | J. Cardinal | 2015-06-10
|  |  |  | Obs003 Is all billed data actual and not estimated for last 6 months? | Obs |  | The University should implement a check annually | J. Cardinal | 2015-06-10
|  |  |  | Obs004 Billed water could be checked against consumption | Obs |  | To consider if regression analysis to be implemented | J. Cardinal | 2015-06-10
|  |  |  | Obs005 Water extraction licence in date | Obs |  | Details to be checked re location of bore hole and volume available | J. Cardinal | 2015-06-10 |  |  | Refer to NC raised 05/02/15
Waste Management | 2014-09-10 | A. Leeson | 1 NC | NC001 There is no evidence company EMR waste carrier EA Licence is up to date | NC |  | Apply for a new licence | S. Hughes / J> Watson |  | Y |  | Copy of the EA Certificate of Registration which expires on 21/08/2017
Estates Office (EMS Audit EA-EMS-Jan15) | 2015-01-27 | D. Inman | 5NCs and 1 Obs | NC001 No test has been carried out of the plan since an oil spill incident on 05th December 2013 | NC |  | n/a | D. Stiles | 2015-03-16 | Y | 2014-09-16 | It was agreed by the Environmental Management Group on 16/09/2014 and 11/11/2014 the Bus Fire incident would be part of the emergency response.
|  |  |  | NC002 The following audits had actions that were not classified as nonconformities or observations 28/0814 Grounds and gardens 22/12/14 Post and portering 17/6/14 Utilities | NC |  |  | D. Stiles | 2015-03-16 | Y | 2015-02-25 | Audits have been reviewed and findings classified as Observation or Non-conformity where appropriate. | • The structure of the action register will be reviewed to reduce time constraints during Environmental Management Group monthly meetings. • Training is approved to train resources to ISO14001 so some tasks can be delegated.
|  |  |  | NC003 No evidence of corrective and preventative actions seen for the NC raised on 10/09/14 during a waste audit | NC |  |  | D. Stiles | 2015-03-16 | yes | 2015-03-03 | The EA Certificate of Registration is in place and now expires on 21/08/2017 | • Additional resources have been made available to review records and update the action register of audits findings. • An extraordinary Environmental Management Group meeting is planned 11th March to review status of all non-conformities
|  |  |  | NC004 No review of audit observations and nonconformities has been carried out | NC |  |  | D. Stiles | 2015-03-16 |  |  | • Additional resources have been made available to review records and update the action register of audits findings. • An extraordinary Environmental Management Group meeting is planned 11th March to review status of all non-conformities | • The structure of the action register will be reviewed to reduce time constraints during Environmental Management Group monthly meetings • Training is approved to train resources to ISO14001 so some tasks can be delegated.
|  |  |  | NC005 Audit programme not met in terms of audits delivered | NC |  |  | D. Stiles | 2015-03-16 | yes | 2015-02-26 | A revised and updated internal audits programme has been published on the Estates Insite | • The internal audit procedure (policy manual 5.2) will be edited to authorise audits to be carried +/- 2 months around the date planned in the internal audit programme. • The procedure will confirm audits can be rescheduled at Environmental Management Group discretion within ISO14001 limits. • The management Review held 17th February 2015 acknowledge the change of staff during the year and the need for additional training to create a stable pool of auditors.
|  |  |  | Obs001 Non completed since initial certification in March 2014 | Obs |  |  | D. Stiles | 2015-08-30 |  |  | •Estates Office holds two Management Review per year generally in January/February and summer. Last review was August 2014 • It is proposed to modify the Management Review template to request key audits findings to be reported to senior management
Maintenance Workshops Yard | 2013-12-05 | D. Inman | 4NCs and 4Obs | NC001 Evidence of paper being burnt on site | NC |  | Change to fire training procedure | S. Hughes | 2014-01-31 | yes |  | Burnt paper not used for fire training
|  |  |  | NC002 Oil storage not compliant with Control of Pollution (Oil Storage) England Regulations 2001 | NC |  | Bring site in compliance | S. Hughes | 2014-03-31 | yes | 2014-02-27 | Non-compliant storage removed from site and bunded pallets added where necessary. Site cleaning and oil tanks inspection carried by contractor
|  |  |  | NC003 Discarded WEEE waste on site | NC |  |  | S. Hughes | 2014-03-31 | yes | 2014-02-27
|  |  |  | NC004 Unprotected unknown drain adjacent to fuel tank | NC |  | Identify drains | S. Hughes | 2014-03-31 | yes | 2014-02-27 | Colour coding of risk cover = complete Drainage improvement around boiler house = complete Implement oil interceptor in yard = complete | Refer to action to map site drainage
|  |  |  | Obs001 Andrews Boiler hire unit leaking unknown fluid | Obs |  |  | S. Hughes | 2014-03-31 | yes | 2014-02-27 | Hire unit removed from site
|  |  |  | Obs002 Vermin being attracted to campus | Obs |  |  | S. Hughes | 2014-03-31 | yes | 2014-02-27 | Installation was used for fire training. Installation removed
|  |  |  | Obs003 Untidy and oil-soaked oil tank | Obs |  |  | S. Hughes | 2014-04-01 | yes | 2014-02-28 | Site cleaning and oil tanks inspection carried by contractor
|  |  |  | Obs004 Uneven road gulley surrounding will not allow drain cover to fit | Obs |  |  | S. Hughes | 2014-04-01 | yes | 2014-02-28 | Drainage improvement around boiler house = complete
Construction | 2015-02-17 | J. Cardinal | 2 Obs | Obs001Hazardous waste containers seen on Student Union yard used by Warwick Retail are locked. It is not clear why the containers are present at Student Union location. | Obs |  | It is confirmed hazardous waste containers are required in the area and are regularly collected by qualified contractor. | S. Hughes / J. Watson |  | yes | 2015-03-05
|  |  |  | Obs002 Verges damaged by vehicles around campus. | Obs |  | To consider how paths and bollards could, be improved | S. Hughes / R. Boxall | TBA
Construction (WBS audit) | 2014-07-14 | J. Cardinal | 5 Obs | Obs001 Flooding Protection to be clarified | Obs |  | Refer to Concerto process review | G. Hunter | TBA |  |  | n/a |  |  | Projects Team
|  |  |  | Obs002 Water – to turn off water at night | Obs |  | discussed and agreed with construction company at the time. |  |  |  |  | n/a |  |  | Simon Fearn/Bowmer & Kirkland
|  |  |  | Obs003 Energy – to organise toolbox talk on energy/water instrumentation | Obs |  | Construction company to do | [7 empty] | Simon Fearn/Bowmer & Kirkland
|  |  |  | Obs004 Fit site floodlight with daylight sensor | Obs |  | Construction company to do | [7 empty] | Simon Fearn/Bowmer & Kirkland
|  |  |  | Obs005 Waste containers should be identified | Obs |  | Construction company to do | [7 empty] | Simon Fearn/Bowmer & Kirkland

## Corrective Action Archive
Function | Date Raised | NC/Obs | Details of NC/Obs | Type | Observation description | Responsibility | Date for completion | Completed | Date Completed | Corrective action taken | Preventative action carried out | Causation type | Action with | May Chased by email | May 2nd Chase by email | May Response | Continued action | June Chased by email | June 2nd Chase by email | June Response | July Response | August chase by email
Facilities | 2013-08-22 | 004 | The campus requires uncontroled waste materials to be removed | Obs | Waste | S Hughes | 2013-12-23 | Y | 2014-01-06 | Areas tidied up | Update 13/05/14 M.Hubbard confirmed that labourers check area's on a weekly basis. | Nuisance
Grounds & gardens | 2013-11-25 | 9.3 | Fuel can unbunded | Obs | Oil/Fuel | S Hughes/ R Boxall | 2014-01-10 | Y |  | Removed from site
Grounds & gardens | 2013-11-25 | 17.1 | External lights left on | Obs | Training | S Hughes/ R Boxall | 2014-01-10 | Y |  | Checked by Roger
Waste | 2013-12-05 | OBS003 | Part E not returned for consignment NFN117/03153 OK including inventory. | Obs | Waste | E Idundun | 2014-01-10 | y |  | Evidence received from supplier
Maintenance | 2013-12-05 | NC001 | Evidence of paper being burnt on site | NC | Waste | S Hughes | 2014-01-10 | Y | 2014-01-22 | believe the area is used for fire extinguisher training. To implement a procedure / label by engineer to indicate it is a restricted and controlled fire? | Area has been cleared. A specific controlled fire extinguisher training area will be established with appropriate signage and cordons. Update 13/05/14 M.Hubbard confirmed no further action required.
Maintenance | 2013-12-05 | NC003 | Discarded WEEE waste on site | NC | Waste | S Hughes | 2014-01-10 | Y |  | 1) Tool box talk to all estates teams 2) Issue tool bax talk to all campus facilities managers 3) Refresh signs in area 4) Issue brief on Insite | Update 13/05/14. M.Hubbard confirmed that microwave is removed and labourers carry out a weekly checks.
Maintenance | 2013-12-05 | NC004 | Unprotected unknown drain adjacent to fuel tank. | NC | Water | S Hughes | 2014-01-10 | Y |  | Renewal of drain is taking place | Update 13/05/14.M.Hubbard confirmed all works are completed.
Maintenance | 2013-12-05 | OBS001 | Andrews Boiler hire unit leaking unknown fluid | Obs | Oil/Fuel | S Hughes | 2014-01-10 | Y | 2014-01-06 | Area tidied up | Further inspections to area. Update 13/05/14.M.Hubbard confirmed that all works are completed.
Maintenance | 2013-12-05 | OBS002 | Vermin being attracted to campus | Obs | Ecology | S Hughes | 2014-01-10 | Y |  | Area cleared. Estates employs a contractor | Update 13/05/14.M.Hubbard confirmed that all works are completed.
Maintenance | 2013-12-05 | OBS003 | Untidy and oil soaked oil tank | Obs | Oil/Fuel | S Hughes | 2014-01-10 | Y | 2014-01-06 | Area tidied up | Further improvements to area implemented. Update 13/05/14.M.Hubbard confirmed all works are completed.
ISOQAR | 2014-01-07 | 1 | The scope within the EMS should be more specific to reflect the current activities | Obs | Systems | D Inman | 2014-02-04 | Y | 2014-01-15 | Amended EMS Manual (EM) | Internal EMS audit 21/01/14
ISOQAR | 2014-01-07 | - | A localised site drainage plan and drain identification is also recommended for the above locations. | Obs | Water | S Hughes | 2014-02-04 | y | 2014-01-30 |  | Refer to above preventive action plan. Update 13/05/14 see above.
Internal EMS Audit EA-EMS-Jan14-01 | 2014-01-21 | NC001 | No evidence that the Estates Office has communicated relevant procedures and requirements related to the identifiable significant environmental aspect of goods and services used by the organization to suppliers and contractors? | NC | Systems | J Cardinal | 2014-01-31 | Y |  | All non conformities are closed. Some observations are being progressed. | Update 13/05/14. J.Cardinal confirmed that we have written to all our suppliers to advise of the ISO 14001 and Adrian Gurney completes a 10% audit check.
Internal EMS Audit EA-EMS-Jan14-01 | 2014-01-21 | Obs004 | Corrective actions outstanding and overdue for closure | Obs | Systems | J Cardinal | 2014-01-31 | Y |  | All non conformities are closed. Some observations are being progressed.

## Overall graph
Archaeology | 0
Contaminated land | 0
Ecology | 1
Materials | 0
Oil, fuel & chemicals | 6
Site management | 0
Training | 1
Waste | 9
Water | 7
Systems | 8
Total | 32

## Status of closed audit findings
N | 1 | 3.125%
Y | 31 | 96.88%
32